## MasterSheet
CRQ Number | CRQ Description | CRQ Status | CRQ Start Date | CRQ End Date | Linux Tasks in CRQ | Task Description | Task Status | Task Status 1 | Task Start Date | Task End Date | Xen/VMWare | Assignee
CRQ000002139200 | SAN_MIG ¦ AAR401 ¦ li16db002 | Implementation In Progress | 02.12.2022 09:00:00 | 04.01.2023 17:00:00 | TAS000006761961 | MIG_SERVER: Verification during SAN migration | Assigned |  | 15.12.2022 08:00:00 | 15.12.2022 11:00:00 | os-unix-std-06:global:2nd | Tushar Lohia (EXT)
CRQ000002152388 | #P#DE#Downtime#NONE#AL Claims - Change AVL scan version | Scheduled | 15.12.2022 11:00:00 | 15.12.2022 17:00:00 | TAS000006793207 | server-unix-std:global¦06¦100a-VirusProtection-Installation-(NSTC) | Assigned |  | 15.12.2022 11:00:00 | 15.12.2022 17:00:00 | os-unix-std-06:global:2nd | Christian Basler
CRQ000002147935 | *DB_MOVE* *GMA* MOVE to lpdbs103/104 | Scheduled | 15.12.2022 06:00:00 | 09.01.2023 23:00:00 | TAS000006783152 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Assigned |  | 15.12.2022 12:00:00 | 17.12.2022 12:00:00 | os-unix-std-06:global:2nd | Vinayak Awasthi (EXT)
CRQ000002139706 | SAN_MIG ¦ BRE401 ¦ li16db001 | Implementation In Progress | 02.12.2022 09:00:00 | 05.01.2023 17:00:00 | TAS000006761979 | MIG_SERVER: Verification during SAN migration | Assigned |  | 15.12.2022 13:00:00 | 15.12.2022 16:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002151554 | Shutdown empty ORACLE GMA Server until 03/2023 - ORACLE POOL Server | Implementation In Progress | 13.12.2022 12:00:00 | 31.03.2023 12:00:00 | TAS000006793517 | Shutdown empty ORACLE GMA Server until 03/2023 - ORACLE POOL Server Disable Monitoring | Assigned |  | 15.12.2022 13:00:00 | 16.12.2022 06:00:00 | os-unix-std-06:global:2nd | Nanda Padala (EXT)
CRQ000002151825 | Reboot the xenfarm node- lpxenppg072 | Scheduled | 15.12.2022 00:00:00 | 20.12.2022 00:00:00 | TAS000006792074 | Reboot the xenfarm node ¦ lpxenppg072 | Assigned |  | 15.12.2022 22:00:00 | 16.12.2022 00:00:00 | os-unix-std-06:global:2nd | Rohit Varmani (EXT)
CRQ000002144449 | #SK Decom<lpdkpga00175vm>VM | Implementation In Progress | 02.12.2022 08:00:00 | 22.12.2022 18:00:00 | TAS000006774396 | Return/Change SAN-Storage | Assigned |  | 16.12.2022 08:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd | VinodKumar Uppara (EXT)
CRQ000002144449 | #SK Decom<lpdkpga00175vm>VM | Implementation In Progress | 02.12.2022 08:00:00 | 22.12.2022 18:00:00 | TAS000006774398 | Clear virtual instance | Assigned |  | 16.12.2022 08:00:00 | 19.12.2022 18:00:00 | os-unix-std-06:global:2nd | Sushmitha R (EXT)
CRQ000002144455 | #SK Decom<lppgb03689vm>VM | Implementation In Progress | 02.12.2022 08:00:00 | 22.12.2022 18:00:00 | TAS000006774578 | Return/Change SAN-Storage | Assigned |  | 16.12.2022 08:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd | Paras Chhabra (EXT)
CRQ000002144455 | #SK Decom<lppgb03689vm>VM | Implementation In Progress | 02.12.2022 08:00:00 | 22.12.2022 18:00:00 | TAS000006774579 | Clear virtual instance | Assigned |  | 16.12.2022 08:00:00 | 19.12.2022 18:00:00 | os-unix-std-06:global:2nd | Saeed Mansoorie (EXT)
CRQ000002144442 | #SK Decom <lpdkpgb00175vm>VM | Implementation In Progress | 02.12.2022 08:00:00 | 22.12.2022 18:00:00 | TAS000006773660 | Return/Change SAN-Storage | Assigned |  | 16.12.2022 08:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd | Chimaladinne Ramesh (EXT)
CRQ000002144442 | #SK Decom <lpdkpgb00175vm>VM | Implementation In Progress | 02.12.2022 08:00:00 | 22.12.2022 18:00:00 | TAS000006773661 | Clear virtual instance | Assigned |  | 16.12.2022 08:00:00 | 19.12.2022 18:00:00 | os-unix-std-06:global:2nd | Ravneet Bagga (EXT)
CRQ000002144452 | #SK Decom<lppga03689vm>VM | Implementation In Progress | 02.12.2022 08:00:00 | 22.12.2022 18:00:00 | TAS000006774728 | Return/Change SAN-Storage | Assigned |  | 16.12.2022 08:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd | Nagarjuna Medarametla (EXT)
CRQ000002144452 | #SK Decom<lppga03689vm>VM | Implementation In Progress | 02.12.2022 08:00:00 | 22.12.2022 18:00:00 | TAS000006774730 | Clear virtual instance | Assigned |  | 16.12.2022 08:00:00 | 19.12.2022 18:00:00 | os-unix-std-06:global:2nd | Chandrakant Dumma (EXT)
CRQ000002144927 | $1 "Colo Group Project" Moving server <lpdbs130> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775255 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Assigned |  | 16.12.2022 08:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002149528 | IPS-I-P09-PROD - Update Masterrelease | Scheduled | 16.12.2022 10:00:00 | 16.12.2022 22:00:00 | TAS000006789242 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 16.12.2022 11:00:00 | 16.12.2022 13:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002149528 | IPS-I-P09-PROD - Update Masterrelease | Scheduled | 16.12.2022 10:00:00 | 16.12.2022 22:00:00 | TAS000006789243 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 16.12.2022 11:00:00 | 16.12.2022 13:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002149528 | IPS-I-P09-PROD - Update Masterrelease | Scheduled | 16.12.2022 10:00:00 | 16.12.2022 22:00:00 | TAS000006789526 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 16.12.2022 11:00:00 | 16.12.2022 13:00:00 | os-unix-std-06:global:2nd | Nanda Padala (EXT)
CRQ000002149528 | IPS-I-P09-PROD - Update Masterrelease | Scheduled | 16.12.2022 10:00:00 | 16.12.2022 22:00:00 | TAS000006789828 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 16.12.2022 11:00:00 | 16.12.2022 13:00:00 | os-unix-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002149528 | IPS-I-P09-PROD - Update Masterrelease | Scheduled | 16.12.2022 10:00:00 | 16.12.2022 22:00:00 | TAS000006789829 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 16.12.2022 11:00:00 | 16.12.2022 13:00:00 | os-unix-std-06:global:2nd | Nanda Padala (EXT)
CRQ000002151868 | IBM Integration Bus - Operational activities for the month December 2022 | Implementation In Progress | 13.12.2022 11:30:00 | 15.01.2023 06:30:00 | TAS000006793186 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 16.12.2022 12:15:00 | 16.12.2022 18:15:00 | os-unix-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002149528 | IPS-I-P09-PROD - Update Masterrelease | Scheduled | 16.12.2022 10:00:00 | 16.12.2022 22:00:00 | TAS000006789630 | server-unix-std:global¦06¦070-OS-config-check_IPS_I | Assigned |  | 16.12.2022 13:00:00 | 16.12.2022 17:00:00 | os-unix-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002149277 | Update TIM GF4 INT C:D node | Scheduled | 16.12.2022 14:00:00 | 16.12.2022 18:00:00 | TAS000006787225 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 16.12.2022 14:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002149655 | Update GAMMA GF4 PROD C:D node | Implementation In Progress | 16.12.2022 14:00:00 | 16.12.2022 18:00:00 | TAS000006786783 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 16.12.2022 14:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd | Nanda Padala (EXT)
CRQ000002035384 | GTZ SAP System | Implementation In Progress | 05.07.2022 13:56:18 | 08.07.2022 13:56:18 | TAS000006518807 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 16.12.2022 19:00:00 | 16.12.2022 23:00:00 | os-unix-std-06:global:2nd | Alok Pai (EXT)
CRQ000002147984 | ORA-OFFMIG* ltbkdbtde038vm VM from ltbkxendb31_32 to ltbkxendb53_54 | Implementation In Progress | 11.12.2022 14:00:00 | 20.12.2022 15:00:00 | TAS000006782916 | server-unix-std:global¦06¦082c-move-vm-exec | Assigned |  | 16.12.2022 20:00:00 | 16.12.2022 22:00:00 | os-unix-std-06:global:2nd | Manvendra Singh (EXT)
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778216 | server-unix-std:global¦06¦085c-move-farm-exec | Assigned |  | 17.12.2022 00:00:00 | 17.12.2022 04:00:00 | os-unix-std-06:global:2nd | KumaraSwamy Nasika (EXT)
CRQ000002128803 | *SLES12 SP5* *GMA* upgrade to the new Version of SuSE SLES12 SP5 | Implementation In Progress | 27.11.2022 07:00:00 | 17.12.2022 17:00:00 | TAS000006747256 | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (VM) | Pending | Assignment | 17.12.2022 02:00:00 | 17.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778217 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 17.12.2022 04:00:00 | 17.12.2022 08:00:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778218 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 17.12.2022 08:00:00 | 17.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002145643 | *ORA-OFFMIG* lpdboctanevm from lpxendb410 to lpxendb409 | Scheduled | 17.12.2022 08:00:00 | 17.12.2022 11:00:00 | TAS000006777107 | [OS VM offline Migration] lpdboctanevm from lpxendb410 to lpxendb409 | Pending | Assignment | 17.12.2022 08:00:00 | 17.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002151877 | *PKG-MOVE* *GMA* MOVE package plfasi01 from lpdbfips01/02 to lpdbfips001/002. | Implementation In Progress | 13.12.2022 19:00:00 | 26.12.2022 23:00:00 | TAS000006792367 | server-unix-std:global¦06¦023c-cluster-migrate-package | Pending | Assignment | 17.12.2022 08:00:00 | 17.12.2022 11:00:00 | os-unix-std-06:global:2nd
CRQ000002124612 | MR Update on SolMan servers | Implementation In Progress | 25.11.2022 05:30:00 | 31.01.2023 18:30:00 | TAS000006758222 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 17.12.2022 10:00:00 | 17.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778219 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 17.12.2022 12:00:00 | 17.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002147984 | ORA-OFFMIG* ltbkdbtde038vm VM from ltbkxendb31_32 to ltbkxendb53_54 | Implementation In Progress | 11.12.2022 14:00:00 | 20.12.2022 15:00:00 | TAS000006782917 | server-unix-std:global¦06¦083c-move-vm-cleanup-(NSTC) | Pending | Assignment | 17.12.2022 14:00:00 | 20.12.2022 14:00:00 | os-unix-std-06:global:2nd
CRQ000002128803 | *SLES12 SP5* *GMA* upgrade to the new Version of SuSE SLES12 SP5 | Implementation In Progress | 27.11.2022 07:00:00 | 17.12.2022 17:00:00 | TAS000006736858 | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (VM) | Pending | Assignment | 17.12.2022 15:00:00 | 17.12.2022 17:00:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778656 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 17.12.2022 16:00:00 | 17.12.2022 20:00:00 | os-unix-std-06:global:2nd
CRQ000002134463 | IPS-I-P34-PROD - Update Masterrelease | Scheduled | 17.12.2022 19:00:00 | 18.12.2022 06:00:00 | TAS000006750323 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 17.12.2022 19:30:00 | 17.12.2022 21:30:00 | os-unix-std-06:global:2nd
CRQ000002134463 | IPS-I-P34-PROD - Update Masterrelease | Scheduled | 17.12.2022 19:00:00 | 18.12.2022 06:00:00 | TAS000006750324 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 17.12.2022 19:30:00 | 17.12.2022 21:30:00 | os-unix-std-06:global:2nd
CRQ000002134463 | IPS-I-P34-PROD - Update Masterrelease | Scheduled | 17.12.2022 19:00:00 | 18.12.2022 06:00:00 | TAS000006750325 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 17.12.2022 19:30:00 | 17.12.2022 21:30:00 | os-unix-std-06:global:2nd
CRQ000002134463 | IPS-I-P34-PROD - Update Masterrelease | Scheduled | 17.12.2022 19:00:00 | 18.12.2022 06:00:00 | TAS000006750326 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 17.12.2022 19:30:00 | 17.12.2022 21:30:00 | os-unix-std-06:global:2nd
CRQ000002134463 | IPS-I-P34-PROD - Update Masterrelease | Scheduled | 17.12.2022 19:00:00 | 18.12.2022 06:00:00 | TAS000006750327 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 17.12.2022 19:30:00 | 17.12.2022 21:30:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778943 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 17.12.2022 20:00:00 | 18.12.2022 00:00:00 | os-unix-std-06:global:2nd
CRQ000002145851 | [OS Online/Offline Migration] | Scheduled | 17.12.2022 20:00:00 | 31.12.2022 00:00:00 | TAS000006777812 | [OS Online/Offline Migration] lpxensor17 | Pending | Assignment | 17.12.2022 20:00:00 | 17.12.2022 21:00:00 | os-unix-std-06:global:2nd
CRQ000002134463 | IPS-I-P34-PROD - Update Masterrelease | Scheduled | 17.12.2022 19:00:00 | 18.12.2022 06:00:00 | TAS000006750328 | server-unix-std:global¦06¦070-OS-config-check_IPS_I | Pending | Assignment | 17.12.2022 21:30:00 | 18.12.2022 01:30:00 | os-unix-std-06:global:2nd
CRQ000002120037 | *MR+Veritas* *ESP* lp34d53/54 install Masterrelease | Scheduled | 17.12.2022 22:00:00 | 18.12.2022 05:00:00 | TAS000006716745 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 17.12.2022 22:00:00 | 18.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778944 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 18.12.2022 00:00:00 | 18.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002137598 | *MR+Veritas* *GMA* lpdbs117/118 install Masterrelease | Scheduled | 18.12.2022 01:00:00 | 18.12.2022 08:00:00 | TAS000006757790 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 18.12.2022 01:00:00 | 18.12.2022 07:00:00 | os-unix-std-06:global:2nd
CRQ000002151602 | Critical BTRFS Balancing (lpszmq01vm) | Scheduled | 18.12.2022 01:00:00 | 18.12.2022 03:00:00 | TAS000006789858 | Critical BTRFS Balancing (lpszmq01vm) | Pending | Assignment | 18.12.2022 01:00:00 | 18.12.2022 03:00:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778945 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 18.12.2022 04:00:00 | 18.12.2022 08:00:00 | os-unix-std-06:global:2nd
CRQ000002132514 | *MR+Veritas* *GMA* lpdbs115/116 install Masterrelease | Scheduled | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | TAS000006744297 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002137992 | *MR+Veritas* *GMA* install Masterrelease | Scheduled | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | TAS000006758400 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002136190 | SAN #Data: SAN_MICROCODE_UPDATE AAR401 / BRE401 | Scheduled | 18.12.2022 08:00:00 | 18.12.2022 16:00:00 | TAS000006755447 | NTT Unix: SAN #Data: SAN_MICROCODE_UPDATE AAR401 / BRE401 | Pending | Assignment | 18.12.2022 08:00:00 | 18.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002151877 | *PKG-MOVE* *GMA* MOVE package plfasi01 from lpdbfips01/02 to lpdbfips001/002. | Implementation In Progress | 13.12.2022 19:00:00 | 26.12.2022 23:00:00 | TAS000006792368 | server-unix-std:global¦06¦024c-cluster-migrate-cleanup-(NSTC) | Pending | Assignment | 18.12.2022 08:00:00 | 26.12.2022 08:00:00 | os-unix-std-06:global:2nd
CRQ000002133911 | *MR* *GMA* VMs install Masterrelease | Implementation In Progress | 10.12.2022 10:00:00 | 18.12.2022 18:00:00 | TAS000006748476 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 18.12.2022 15:00:00 | 18.12.2022 17:00:00 | os-unix-std-06:global:2nd
CRQ000002120065 | *SLES12 SP5* *ESP* *lp34d51/52* upgrade to the new Version of SuSE SLES12 SP5 | Scheduled | 18.12.2022 20:00:00 | 19.12.2022 03:00:00 | TAS000006716797 | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Cluster) | Pending | Assignment | 18.12.2022 20:00:00 | 19.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002140000 | Postgres VMs Online Migration / MR + Firmware Update for Q4 2022 | Implementation In Progress | 29.11.2022 12:00:00 | 31.12.2022 00:00:00 | TAS000006768164 | [MR + Firmware Update + Reboot] | Pending | Assignment | 18.12.2022 20:00:00 | 19.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002137992 | *MR+Veritas* *GMA* install Masterrelease | Scheduled | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | TAS000006766509 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 18.12.2022 21:00:00 | 18.12.2022 23:00:00 | os-unix-std-06:global:2nd
CRQ000002148920 | DAM16 PROD - Upgrade SLES12 SP2 to SLES12 SP5 | Scheduled | 19.12.2022 03:30:00 | 19.12.2022 10:00:00 | TAS000006785243 | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (VM) | Pending | Assignment | 19.12.2022 04:00:00 | 19.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002126431 | $1 "Colo Group Project" Moving server <lpsbdbs012> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006730898 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Pending | Assignment | 19.12.2022 08:00:00 | 19.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002135229 | SAN GS 3: SAN_MICROCODE_UPDATE GMA3S1 (BGs) | Scheduled | 19.12.2022 08:00:00 | 19.12.2022 16:00:00 | TAS000006750593 | NTT Unix: SAN GS 3: SAN_MICROCODE_UPDATE GMA3S1 (BGs) | Pending | Assignment | 19.12.2022 08:00:00 | 19.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002144399 | $1 "Colo Group Project" Moving server <lpdbs140> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006774915 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Pending | Assignment | 19.12.2022 08:00:00 | 19.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002145308 | $1 "Colo Group Project" Moving server <lpsbdbs014> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006775315 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Pending | Assignment | 19.12.2022 08:00:00 | 19.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002145522 | $1 "Colo Group Project" Moving server <lpsbdbs016> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006776778 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Pending | Assignment | 19.12.2022 08:00:00 | 19.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127216 | Planned Power shutdown 16.47 Miramas - UPS Replacement | Scheduled | 19.12.2022 06:00:00 | 21.12.2022 19:30:00 | TAS000006746565 | server-win:emea¦Shutdown_Server_Unix | Pending | Assignment | 19.12.2022 08:30:00 | 21.12.2022 17:30:00 | os-unix-std-06:global:2nd
CRQ000002134715 | Farm replacement <lp02xenmq03/04> VM's Offline Migration | Scheduled | 19.12.2022 11:00:00 | 31.12.2022 11:00:00 | TAS000006749615 | server-unix-std:global¦06¦084c-move-farm-prep-(NSTC) | Pending | Assignment | 19.12.2022 11:00:00 | 22.12.2022 11:00:00 | os-unix-std-06:global:2nd
CRQ000002139916 | VMs Offline Migration from xenfarm node- ltxen1033 | Scheduled | 19.12.2022 20:00:00 | 21.12.2022 20:00:00 | TAS000006781657 | [VMs Offline Migration] | Pending | Assignment | 19.12.2022 20:00:00 | 20.12.2022 00:00:00 | os-unix-std-06:global:2nd
CRQ000002144907 | ##T##D## Preparation for decommissioning EDBIC PROD&INT-Server | Implementation In Progress | 02.12.2022 20:00:00 | 05.12.2022 20:00:00 | TAS000006774206 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Pending | Assignment | 19.12.2022 21:00:00 | 21.12.2022 21:00:00 | os-unix-std-06:global:2nd
CRQ000002144907 | ##T##D## Preparation for decommissioning EDBIC PROD&INT-Server | Implementation In Progress | 02.12.2022 20:00:00 | 05.12.2022 20:00:00 | TAS000006774207 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Pending | Assignment | 19.12.2022 21:00:00 | 21.12.2022 21:00:00 | os-unix-std-06:global:2nd
CRQ000002144907 | ##T##D## Preparation for decommissioning EDBIC PROD&INT-Server | Implementation In Progress | 02.12.2022 20:00:00 | 05.12.2022 20:00:00 | TAS000006774208 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Pending | Assignment | 19.12.2022 21:00:00 | 21.12.2022 21:00:00 | os-unix-std-06:global:2nd
CRQ000002144907 | ##T##D## Preparation for decommissioning EDBIC PROD&INT-Server | Implementation In Progress | 02.12.2022 20:00:00 | 05.12.2022 20:00:00 | TAS000006774209 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Pending | Assignment | 19.12.2022 21:00:00 | 21.12.2022 21:00:00 | os-unix-std-06:global:2nd
CRQ000002146628 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor19/20> | Implementation In Progress | 12.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006780342 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 19.12.2022 22:00:00 | 20.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002146592 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor17/18> | Implementation In Progress | 12.12.2022 10:00:00 | 27.12.2022 00:00:00 | TAS000006779991 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 19.12.2022 22:00:00 | 20.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002139916 | VMs Offline Migration from xenfarm node- ltxen1033 | Scheduled | 19.12.2022 20:00:00 | 21.12.2022 20:00:00 | TAS000006781836 | [VMs Offline Migration] | Pending | Assignment | 20.12.2022 00:00:00 | 20.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002146963 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor15/16> | Implementation In Progress | 12.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006780821 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 20.12.2022 00:00:00 | 20.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002146592 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor17/18> | Implementation In Progress | 12.12.2022 10:00:00 | 27.12.2022 00:00:00 | TAS000006781222 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 20.12.2022 02:00:00 | 20.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002147341 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor15/16> | Implementation In Progress | 13.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006782493 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 20.12.2022 02:00:00 | 20.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002148748 | DAM16 PROD - Upgrade SLES12 SP2 to SLES12 SP5 | Scheduled | 20.12.2022 04:00:00 | 20.12.2022 08:00:00 | TAS000006785730 | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (VM) | Pending | Assignment | 20.12.2022 04:00:00 | 20.12.2022 08:00:00 | os-unix-std-06:global:2nd
CRQ000002135781 | SAN GS 3: SAN_MICROCODE_UPDATE GMA311 (BGs) | Scheduled | 20.12.2022 08:00:00 | 20.12.2022 16:00:00 | TAS000006754377 | NTT Unix: SAN GS 3: SAN_MICROCODE_UPDATE GMA311 (BGs) | Pending | Assignment | 20.12.2022 08:00:00 | 20.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002139916 | VMs Offline Migration from xenfarm node- ltxen1033 | Scheduled | 19.12.2022 20:00:00 | 21.12.2022 20:00:00 | TAS000006781650 | [OS Re-installation ¦¦ SLES-12 SP5] | Pending | Assignment | 20.12.2022 10:00:00 | 20.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002146592 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor17/18> | Implementation In Progress | 12.12.2022 10:00:00 | 27.12.2022 00:00:00 | TAS000006781224 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 20.12.2022 10:00:00 | 25.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002147341 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor15/16> | Implementation In Progress | 13.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006781704 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 20.12.2022 10:00:00 | 26.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002136172 | SAN GS 3: SAN_MICROCODE_UPDATE GMA312 (BGs) | Scheduled | 21.12.2022 08:00:00 | 21.12.2022 16:00:00 | TAS000006754406 | NTT Unix: SAN GS 3: SAN_MICROCODE_UPDATE GMA312 (BGs) | Pending | Assignment | 21.12.2022 08:00:00 | 21.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002139722 | SAN_MIG ¦ BEJ401 ¦ lt19xen23/24_lt19xen31/32_lt19xens11/12 | Implementation In Progress | 08.12.2022 09:00:00 | 12.01.2023 17:00:00 | TAS000006762529 | MIG_SERVER: Verification during SAN migration | Pending | Assignment | 21.12.2022 08:00:00 | 21.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002147303 | $1 "Colo Group Project" Moving server <lpdbs142> to new location | Implementation In Progress | 07.12.2022 09:00:00 | 31.01.2023 18:00:00 | TAS000006780687 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Pending | Assignment | 21.12.2022 08:00:00 | 21.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778220 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 21.12.2022 09:00:00 | 26.12.2022 09:00:00 | os-unix-std-06:global:2nd
CRQ000002146963 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor15/16> | Implementation In Progress | 12.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006781822 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 21.12.2022 10:00:00 | 28.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002152309 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensdi21/22> | Implementation In Progress | 14.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006792533 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 21.12.2022 20:00:00 | 22.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002151581 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensdi21/22> | Implementation In Progress | 14.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006791352 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 22.12.2022 02:00:00 | 22.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002136178 | SAN GS 3: SAN_MICROCODE_UPDATE GMA313 (BGs) | Scheduled | 22.12.2022 08:00:00 | 22.12.2022 16:00:00 | TAS000006754663 | NTT Unix: SAN GS 3: SAN_MICROCODE_UPDATE GMA313 (BGs) | Pending | Assignment | 22.12.2022 08:00:00 | 22.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002151581 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensdi21/22> | Implementation In Progress | 14.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006791622 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 22.12.2022 10:00:00 | 29.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002152309 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensdi21/22> | Implementation In Progress | 14.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006792346 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 22.12.2022 10:00:00 | 29.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002151039 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensdi21/22> | Implementation In Progress | 14.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006790740 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 22.12.2022 20:00:00 | 23.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002127032 | $1 "Colo Group Project" Moving server <lpdbs132> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 23.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731384 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 15.12.2022 08:00:00 | 15.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127117 | $1 "Colo Group Project" Moving server <lpdbs136> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 23.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006732018 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 15.12.2022 08:00:00 | 15.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127120 | $1 "Colo Group Project" Moving server <lpdbs138> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 23.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006732260 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 15.12.2022 08:00:00 | 15.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127319 | $1 "Colo Group Project" Moving server <lpdbs137> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006732336 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 15.12.2022 09:30:00 | 15.12.2022 15:00:00 | os-unix-std-06:global:2nd
CRQ000002127317 | $1 "Colo Group Project" Moving server <lpdbs135> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006732238 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 15.12.2022 09:30:00 | 15.12.2022 15:00:00 | os-unix-std-06:global:2nd
CRQ000002150106 | *PKG-MOVE* *GSP* MOVE package dbprof50 from lp07db003/004 to lp07db001/002 | Scheduled For Approval | 15.12.2022 12:00:00 | 27.12.2022 23:00:00 | TAS000006786884 | server-unix-std:global¦06¦022c-cluster-prepare-migrate-package | Staged | Staging in Progress | 15.12.2022 12:00:00 | 18.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002127319 | $1 "Colo Group Project" Moving server <lpdbs137> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006732340 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 16.12.2022 08:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127321 | $1 "Colo Group Project" Moving server <ltdbs006> to new location | Implementation In Progress | 24.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731412 | readyops:global¦Pre-check-OS-team_unix-single-san-complex | Staged | Staging in Progress | 16.12.2022 08:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127317 | $1 "Colo Group Project" Moving server <lpdbs135> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006732242 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 16.12.2022 08:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144834 | #PROD - Informatica NA migration from Xen to VMWare Status | Implementation In Progress | 16.12.2022 18:30:00 | 18.12.2022 22:30:00 | TAS000006774976 | server-unix-std:global¦06¦070c-modify-system | Staged | Staging in Progress | 16.12.2022 23:30:00 | 18.12.2022 23:30:00 | os-unix-std-06:global:2nd
CRQ000002128060 | *MR+VERITAS* *ESP* lpkrd04/05 install Masterrelease | Scheduled For Approval | 17.12.2022 16:30:00 | 17.12.2022 23:00:00 | TAS000006735035 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Staged | Staging in Progress | 17.12.2022 16:30:00 | 17.12.2022 22:30:00 | os-unix-std-06:global:2nd
CRQ000002127753 | *MR+VERITAS* *ESP* lpkrd07/08 install Masterrelease | Scheduled For Approval | 17.12.2022 16:00:00 | 17.12.2022 23:00:00 | TAS000006735046 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Staged | Staging in Progress | 17.12.2022 16:30:00 | 17.12.2022 22:30:00 | os-unix-std-06:global:2nd
CRQ000002132205 | Farm replacement - Source Farm lp34xen23/24 to Target Host lp34xen27/28 | Rejected | 13.12.2022 09:00:00 | 24.12.2022 08:00:00 | TAS000006743905 | server-unix-std:global¦06¦085c-move-farm-exec | Staged | Staging in Progress | 17.12.2022 20:00:00 | 17.12.2022 22:00:00 | os-unix-std-06:global:2nd
CRQ000002148411 | Host: lplogstash1vm.bmwgroup.net Service: os_linux_fs_check_btrfs State: CRITICAL | Planning In Progress |  |  | TAS000006783769 | BTRFS Balance | Staged | Staging in Progress | 17.12.2022 22:30:00 | 18.12.2022 02:30:00 | os-unix-std-06:global:2nd
CRQ000002152772 | M2P/M6P/M7P: Master Release Patch M22Q04 | Scheduled For Approval | 18.12.2022 02:00:00 | 18.12.2022 07:00:00 | TAS000006793751 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Staged | Staging in Progress | 18.12.2022 02:00:00 | 18.12.2022 06:00:00 | os-unix-std-06:global:2nd
CRQ000002152772 | M2P/M6P/M7P: Master Release Patch M22Q04 | Scheduled For Approval | 18.12.2022 02:00:00 | 18.12.2022 07:00:00 | TAS000006793753 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Staged | Staging in Progress | 18.12.2022 02:00:00 | 18.12.2022 06:00:00 | os-unix-std-06:global:2nd
CRQ000002152772 | M2P/M6P/M7P: Master Release Patch M22Q04 | Scheduled For Approval | 18.12.2022 02:00:00 | 18.12.2022 07:00:00 | TAS000006793754 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Staged | Staging in Progress | 18.12.2022 02:00:00 | 18.12.2022 06:00:00 | os-unix-std-06:global:2nd
CRQ000002152772 | M2P/M6P/M7P: Master Release Patch M22Q04 | Scheduled For Approval | 18.12.2022 02:00:00 | 18.12.2022 07:00:00 | TAS000006793755 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Staged | Staging in Progress | 18.12.2022 02:00:00 | 18.12.2022 06:00:00 | os-unix-std-06:global:2nd
CRQ000002152772 | M2P/M6P/M7P: Master Release Patch M22Q04 | Scheduled For Approval | 18.12.2022 02:00:00 | 18.12.2022 07:00:00 | TAS000006793756 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Staged | Staging in Progress | 18.12.2022 02:00:00 | 18.12.2022 06:00:00 | os-unix-std-06:global:2nd
CRQ000002152772 | M2P/M6P/M7P: Master Release Patch M22Q04 | Scheduled For Approval | 18.12.2022 02:00:00 | 18.12.2022 07:00:00 | TAS000006793757 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Staged | Staging in Progress | 18.12.2022 02:00:00 | 18.12.2022 06:00:00 | os-unix-std-06:global:2nd
CRQ000002142494 | Farm replacement - Source Farm lp10xen13/14 to Target Host lp10xen1031/32 | Rejected | 14.12.2022 05:00:00 | 25.12.2022 05:00:00 | TAS000006770818 | server-unix-std:global¦06¦085c-move-farm-exec | Staged | Staging in Progress | 18.12.2022 06:00:00 | 18.12.2022 08:00:00 | os-unix-std-06:global:2nd
CRQ000002132205 | Farm replacement - Source Farm lp34xen23/24 to Target Host lp34xen27/28 | Rejected | 13.12.2022 09:00:00 | 24.12.2022 08:00:00 | TAS000006743906 | server-unix-std:global¦06¦085c-move-farm-exec | Staged | Staging in Progress | 18.12.2022 08:00:00 | 18.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002142494 | Farm replacement - Source Farm lp10xen13/14 to Target Host lp10xen1031/32 | Rejected | 14.12.2022 05:00:00 | 25.12.2022 05:00:00 | TAS000006771543 | server-unix-std:global¦06¦085c-move-farm-exec | Staged | Staging in Progress | 18.12.2022 08:00:00 | 18.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002136410 | [ OS MR Update ] lp34xen32 | Rejected | 18.12.2022 13:30:00 | 18.12.2022 17:30:00 | TAS000006754527 | [ OS MR Update ] lp34xen32 | Staged | Staging in Progress | 18.12.2022 13:30:00 | 18.12.2022 17:30:00 | os-unix-std-06:global:2nd
CRQ000002150106 | *PKG-MOVE* *GSP* MOVE package dbprof50 from lp07db003/004 to lp07db001/002 | Scheduled For Approval | 15.12.2022 12:00:00 | 27.12.2022 23:00:00 | TAS000006786885 | server-unix-std:global¦06¦023c-cluster-migrate-package | Staged | Staging in Progress | 19.12.2022 01:00:00 | 19.12.2022 03:00:00 | os-unix-std-06:global:2nd
CRQ000002142494 | Farm replacement - Source Farm lp10xen13/14 to Target Host lp10xen1031/32 | Rejected | 14.12.2022 05:00:00 | 25.12.2022 05:00:00 | TAS000006771544 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Staged | Staging in Progress | 19.12.2022 05:00:00 | 24.12.2022 05:00:00 | os-unix-std-06:global:2nd
CRQ000002132205 | Farm replacement - Source Farm lp34xen23/24 to Target Host lp34xen27/28 | Rejected | 13.12.2022 09:00:00 | 24.12.2022 08:00:00 | TAS000006743907 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Staged | Staging in Progress | 19.12.2022 08:00:00 | 24.12.2022 08:00:00 | os-unix-std-06:global:2nd
CRQ000002142661 | #DK Decom <lpdkpga00173vm>VM | Implementation In Progress | 30.11.2022 08:00:00 | 20.12.2022 18:00:00 | TAS000006770585 | Check SAN-Storage return | Staged | Staging in Progress | 19.12.2022 08:00:00 | 19.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002126580 | $1 "Colo Group Project" Moving server <lpdbs133> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731394 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Staged | Staging in Progress | 20.12.2022 08:00:00 | 20.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127315 | $1 "Colo Group Project" Moving server <lpdbs131> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731817 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Staged | Staging in Progress | 20.12.2022 08:00:00 | 20.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002126431 | $1 "Colo Group Project" Moving server <lpsbdbs012> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006730901 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 20.12.2022 09:30:00 | 20.12.2022 15:00:00 | os-unix-std-06:global:2nd
CRQ000002144399 | $1 "Colo Group Project" Moving server <lpdbs140> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006774918 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 20.12.2022 09:30:00 | 20.12.2022 15:00:00 | os-unix-std-06:global:2nd
CRQ000002144927 | $1 "Colo Group Project" Moving server <lpdbs130> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775258 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 20.12.2022 09:30:00 | 20.12.2022 15:00:00 | os-unix-std-06:global:2nd
CRQ000002145308 | $1 "Colo Group Project" Moving server <lpsbdbs014> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006775318 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 20.12.2022 09:30:00 | 20.12.2022 15:00:00 | os-unix-std-06:global:2nd
CRQ000002150106 | *PKG-MOVE* *GSP* MOVE package dbprof50 from lp07db003/004 to lp07db001/002 | Scheduled For Approval | 15.12.2022 12:00:00 | 27.12.2022 23:00:00 | TAS000006786886 | server-unix-std:global¦06¦024c-cluster-migrate-cleanup-(NSTC) | Staged | Staging in Progress | 20.12.2022 23:00:00 | 27.12.2022 23:00:00 | os-unix-std-06:global:2nd
CRQ000002126431 | $1 "Colo Group Project" Moving server <lpsbdbs012> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006730905 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 21.12.2022 08:00:00 | 21.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144399 | $1 "Colo Group Project" Moving server <lpdbs140> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775722 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 21.12.2022 08:00:00 | 21.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144455 | #SK Decom<lppgb03689vm>VM | Implementation In Progress | 02.12.2022 08:00:00 | 22.12.2022 18:00:00 | TAS000006774582 | Check SAN-Storage return | Staged | Staging in Progress | 21.12.2022 08:00:00 | 21.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144927 | $1 "Colo Group Project" Moving server <lpdbs130> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775262 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 21.12.2022 08:00:00 | 21.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002145308 | $1 "Colo Group Project" Moving server <lpsbdbs014> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006775822 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 21.12.2022 08:00:00 | 21.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002147179 | $1 "Colo Group Project" Moving server <lpdbs144> to new location | Implementation In Progress | 07.12.2022 09:00:00 | 31.01.2023 18:00:00 | TAS000006781574 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Staged | Staging in Progress | 21.12.2022 09:00:00 | 21.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127321 | $1 "Colo Group Project" Moving server <ltdbs006> to new location | Implementation In Progress | 24.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731415 | readyops:global¦Supervise-servermove_unix-single-san-complex | Staged | Staging in Progress | 21.12.2022 09:30:00 | 21.12.2022 15:00:00 | os-unix-std-06:global:2nd
CRQ000002127321 | $1 "Colo Group Project" Moving server <ltdbs006> to new location | Implementation In Progress | 24.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731419 | readyops:global¦SAN-mirror-unix-single | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002146600 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp07dbipsq001/002 | Scheduled For Approval | 22.12.2022 08:00:00 | 22.12.2022 15:00:00 | TAS000006780788 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 14:00:00 | os-unix-std-06:global:2nd
CRQ000002146600 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp07dbipsq001/002 | Scheduled For Approval | 22.12.2022 08:00:00 | 22.12.2022 15:00:00 | TAS000006780790 | server-unix-std:global¦06¦050c-network-mgmt | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 14:00:00 | os-unix-std-06:global:2nd
CRQ000002147075 | $1 "Colo Group Project" Moving server <lpdbs150> to new location | Implementation In Progress | 08.12.2022 09:00:00 | 31.01.2023 18:00:00 | TAS000006782835 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002151156 | Moving server <LI30YXQ04; LP30TNP08; LP30TNP10> to new location | Implementation In Progress | 12.12.2022 14:15:00 | 31.01.2023 18:00:00 | TAS000006789519 | readyops:global¦Pre-check-OS-team_unix-single-san | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002151643 | Moving server <LP30D07; LP30D09; LP30D11; LT30D02> to new location | Implementation In Progress | 12.12.2022 13:30:00 | 31.01.2023 18:00:00 | TAS000006789316 | readyops:global¦Pre-check-OS-team_unix-single-san | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002151651 | Moving server < LP30TNP09; LP30TNP11; LP30YXP09> to new location | Implementation In Progress | 12.12.2022 13:40:00 | 31.01.2023 18:00:00 | TAS000006791146 | readyops:global¦Pre-check-OS-team_unix-single-no-san | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002151287 | Moving server <LP30D08; LP30D10; LP30D12> to new location | Implementation In Progress | 12.12.2022 14:15:00 | 31.01.2023 18:00:00 | TAS000006791035 | readyops:global¦Pre-check-OS-team_unix-single-san | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002151645 | Moving server <LP30TNP07> to new location | Implementation In Progress | 12.12.2022 13:35:00 | 31.01.2023 18:00:00 | TAS000006791132 | readyops:global¦Pre-check-OS-team_unix-single-san | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002151655 | Moving server <LP30TNP12; LP30YXP10> to new location | Implementation In Progress | 12.12.2022 14:15:00 | 31.01.2023 18:00:00 | TAS000006789612 | readyops:global¦Pre-check-OS-team_unix-single-no-san | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002147182 | $1 "Colo Group Project" Moving server <lpdbs146> to new location | Implementation In Progress | 07.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006781598 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Staged | Staging in Progress | 22.12.2022 09:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002147712 | $1 "Colo Group Project" Moving server <lpdbs148> to new location | Implementation In Progress | 08.12.2022 09:00:00 | 31.01.2023 18:00:00 | TAS000006782381 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Staged | Staging in Progress | 22.12.2022 09:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002137234 | *PKG-MOVE* *GSP* MOVE package from lp02d55/56 to lp02db005/006 | Scheduled For Approval | 22.12.2022 11:00:00 | 08.01.2023 23:00:00 | TAS000006756791 | server-unix-std:global¦06¦022c-cluster-prepare-migrate-package | Staged | Staging in Progress | 22.12.2022 11:00:00 | 25.12.2022 23:00:00 | os-unix-std-06:global:2nd
CRQ000002139407 | *PKG-MOVE* *GSP* MOVE packages from lp02d53/54 to lp02db003/004 | Scheduled For Approval | 22.12.2022 18:00:00 | 04.01.2023 19:00:00 | TAS000006761565 | server-unix-std:global¦06¦022c-cluster-prepare-migrate-package | Staged | Staging in Progress | 22.12.2022 18:00:00 | 25.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002152711 | #AR $1 Provision <lpsbm01> Virtual Server - Gold | Implementation In Progress | 13.12.2022 08:00:00 | 19.12.2022 18:00:00 | TAS000006792871 | Quality check | Assigned |  | 15.12.2022 08:00:00 | 15.12.2022 18:00:00 | os-linux-std-06:global:2nd | Shruti Pandey (EXT)
CRQ000002101623 | FX1 SAP System | Implementation In Progress | 05.10.2022 13:00:27 | 08.10.2022 13:00:27 | TAS000006767410 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 15.12.2022 14:00:00 | 15.12.2022 18:00:00 | os-linux-std-06:global:2nd | amit sharma (EXT)
CRQ000002068054 | RWI SAP System | Implementation In Progress | 17.08.2022 09:57:21 | 20.08.2022 09:57:21 | TAS000006596854 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 16.12.2022 00:00:00 | 16.12.2022 04:00:00 | os-linux-std-06:global:2nd | Manvendra Singh (EXT)
CRQ000002056956 | WYT SAP System | Implementation In Progress | 02.08.2022 10:41:24 | 05.08.2022 10:41:24 | TAS000006570731 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 16.12.2022 06:00:00 | 17.12.2022 18:00:00 | os-linux-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002111392 | Connect Direct Installation and Migration | Scheduled | 13.11.2022 23:00:00 | 29.12.2022 23:00:00 | TAS000006697413 | server-unix-std:global¦06¦Initial-Rudder-CD-Installation | Assigned |  | 16.12.2022 07:00:00 | 16.12.2022 16:00:00 | os-linux-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002036566 | GUI SAP System | Implementation In Progress | 05.07.2022 14:02:17 | 08.07.2022 14:02:17 | TAS000006519303 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 16.12.2022 08:30:00 | 16.12.2022 12:30:00 | os-linux-std-06:global:2nd | Ashwini Tendulkar (EXT)
CRQ000002141201 | STARD: SND CS migration - implementation | Implementation In Progress | 12.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006764688 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 16.12.2022 10:00:00 | 16.12.2022 14:00:00 | os-linux-std-06:global:2nd | Prodyut Paul (EXT)
CRQ000002140992 | RS Production C:D Version Upgrade to fix security vulnerabilities 6.x | Implementation In Progress | 10.12.2022 16:00:00 | 18.12.2022 10:00:00 | TAS000006766638 | server-unix-std:global¦06¦070c-modify-system | Assigned |  | 16.12.2022 16:00:00 | 16.12.2022 20:00:00 | os-linux-std-06:global:2nd | Prodyut Paul (EXT)
CRQ000002144834 | #PROD - Informatica NA migration from Xen to VMWare Status | Implementation In Progress | 16.12.2022 18:30:00 | 18.12.2022 22:30:00 | TAS000006774975 | server-unix-std:global¦06¦070c-modify-system | Assigned |  | 16.12.2022 21:00:00 | 18.12.2022 21:30:00 | os-linux-std-06:global:2nd | Makkena Raghava (EXT)
CRQ000002150029 | #Migration Linux VM #Global#Downtime#2h#CCM_HR PROD | Scheduled | 16.12.2022 23:00:00 | 18.12.2022 22:00:00 | TAS000006787655 | server-unix-std:global¦06¦050c-network-mgmt | Assigned |  | 17.12.2022 13:00:00 | 17.12.2022 15:00:00 | os-linux-std-06:global:2nd | Kishore Kumar (EXT)
CRQ000002125016 | STARD: TXD CS migration + DI replacement - implementation | Scheduled | 18.12.2022 05:00:00 | 30.12.2022 18:00:00 | TAS000006727212 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 18.12.2022 09:00:00 | 18.12.2022 13:00:00 | os-linux-std-06:global:2nd | Tushar Lohia (EXT)
CRQ000002151873 | STE: Upgrade C:D | Scheduled | 18.12.2022 10:00:00 | 18.12.2022 14:00:00 | TAS000006792089 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 18.12.2022 10:00:00 | 18.12.2022 12:00:00 | os-linux-std-06:global:2nd | Vinayak Awasthi (EXT)
CRQ000002151879 | STI: Upgrade C:D | Scheduled | 18.12.2022 10:00:00 | 18.12.2022 14:00:00 | TAS000006792172 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 18.12.2022 10:00:00 | 18.12.2022 12:00:00 | os-linux-std-06:global:2nd | Narugopal Pal (EXT)
CRQ000002125016 | STARD: TXD CS migration + DI replacement - implementation | Scheduled | 18.12.2022 05:00:00 | 30.12.2022 18:00:00 | TAS000006728523 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 18.12.2022 11:30:00 | 18.12.2022 15:00:00 | os-linux-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002148932 | STI/STP: Install C:D override on new CS servers | Scheduled | 19.12.2022 12:00:00 | 21.12.2022 12:00:00 | TAS000006784991 | server-unix-std:global¦045s-install-override-(NSTC) | Assigned |  | 19.12.2022 12:00:00 | 21.12.2022 12:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002148932 | STI/STP: Install C:D override on new CS servers | Scheduled | 19.12.2022 12:00:00 | 21.12.2022 12:00:00 | TAS000006784992 | server-unix-std:global¦045s-install-override-(NSTC) | Assigned |  | 19.12.2022 12:00:00 | 21.12.2022 12:00:00 | os-linux-std-06:global:2nd | Prodyut Paul (EXT)
CRQ000002150964 | Update GAMMA GF5 INT C:D nodes | Implementation In Progress | 19.12.2022 14:00:00 | 19.12.2022 18:00:00 | TAS000006789642 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 19.12.2022 14:00:00 | 19.12.2022 18:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002151435 | Update FKD GF5 INT C:D nodes | Implementation In Progress | 19.12.2022 14:00:00 | 19.12.2022 18:00:00 | TAS000006789259 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 19.12.2022 14:00:00 | 19.12.2022 18:00:00 | os-linux-std-06:global:2nd | Kishore Kumar (EXT)
CRQ000002088579 | HRD SAP System | Implementation In Progress | 15.09.2022 14:31:04 | 18.09.2022 14:31:04 | TAS000006643531 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 20.12.2022 00:00:00 | 20.12.2022 04:00:00 | os-linux-std-06:global:2nd | Manvendra Singh (EXT)
CRQ000002101633 | FX2 SAP System | Implementation In Progress | 05.10.2022 13:18:50 | 08.10.2022 13:18:50 | TAS000006768383 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 20.12.2022 14:00:00 | 20.12.2022 18:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002148692 | DAM16 PROD - Upgrade SLES12 SP2 to SLES12 SP5 | Scheduled | 21.12.2022 04:00:00 | 21.12.2022 10:00:00 | TAS000006785408 | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (VM) | Assigned |  | 21.12.2022 04:00:00 | 21.12.2022 10:00:00 | os-linux-std-06:global:2nd | Kamendra Chauhan (EXT)
CRQ000002151025 | Update FKD GF5 PROD C:D nodes | Implementation In Progress | 21.12.2022 14:00:00 | 21.12.2022 18:00:00 | TAS000006789839 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 21.12.2022 14:00:00 | 21.12.2022 18:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002151429 | Update GAMMA GF5 PROD C:D nodes | Implementation In Progress | 21.12.2022 14:00:00 | 21.12.2022 18:00:00 | TAS000006789545 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 21.12.2022 14:00:00 | 21.12.2022 18:00:00 | os-linux-std-06:global:2nd | Kishore Kumar (EXT)
CRQ000002124204 | STARD: TGQ CS migration + DI replacement - implementation | Scheduled | 04.12.2022 05:00:00 | 16.12.2022 18:00:00 | TAS000006725801 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 22.12.2022 09:00:00 | 22.12.2022 13:00:00 | os-linux-std-06:global:2nd | Ashwini Tendulkar (EXT)
CRQ000002124204 | STARD: TGQ CS migration + DI replacement - implementation | Scheduled | 04.12.2022 05:00:00 | 16.12.2022 18:00:00 | TAS000006725812 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 22.12.2022 11:30:00 | 22.12.2022 15:00:00 | os-linux-std-06:global:2nd | Kishore Kumar (EXT)
CRQ000002101659 | FX3 SAP System | Implementation In Progress | 05.10.2022 14:12:32 | 08.10.2022 14:12:32 | TAS000006768835 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 22.12.2022 14:00:00 | 22.12.2022 18:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002088573 | V20 SAP System | Implementation In Progress | 15.09.2022 14:14:04 | 18.09.2022 14:14:04 | TAS000006643296 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 23.12.2022 10:00:00 | 23.12.2022 14:00:00 | os-linux-std-06:global:2nd | Vishnu Athreya (EXT)
CRQ000002066916 | BRD SAP System | Implementation In Progress | 15.08.2022 16:01:52 | 18.08.2022 16:01:52 | TAS000006593458 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 23.12.2022 14:30:00 | 23.12.2022 18:30:00 | os-linux-std-06:global:2nd | Dilip Kumar (EXT)
CRQ000002061326 | MGT SAP System | Implementation In Progress | 08.08.2022 11:10:24 | 11.08.2022 11:10:24 | TAS000006580549 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 23.12.2022 20:00:00 | 24.12.2022 00:00:00 | os-linux-std-06:global:2nd | Makkena Raghava (EXT)
CRQ000002149938 | BRD (Brazil Development) VMWare Installation and Migration | Scheduled For Approval | 14.12.2022 14:00:00 | 07.01.2023 11:00:00 | TAS000006787936 | Confirm Timezones on the NEW Servers for BRD System | Staged | Staging in Progress | 19.12.2022 07:00:00 | 21.12.2022 15:00:00 | os-linux-std-06:global:2nd

## MasterSheet-1
CRQ Number | CRQ Description | CRQ Status | CRQ Start Date | CRQ End Date | Linux Tasks in CRQ | Task Description | Task Status | Task Status 1 | Task Start Date | Task End Date | Xen/VMWare | Assignee
CRQ000002035384 | GTZ SAP System | Implementation In Progress | 05.07.2022 13:56:18 | 08.07.2022 13:56:18 | TAS000006518807 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 16.12.2022 19:00:00 | 16.12.2022 23:00:00 | os-unix-std-06:global:2nd | Alok Pai (EXT)
CRQ000002036566 | GUI SAP System | Implementation In Progress | 05.07.2022 14:02:17 | 08.07.2022 14:02:17 | TAS000006519303 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 16.12.2022 08:30:00 | 16.12.2022 12:30:00 | os-linux-std-06:global:2nd | Ashwini Tendulkar (EXT)
CRQ000002056956 | WYT SAP System | Implementation In Progress | 02.08.2022 10:41:24 | 05.08.2022 10:41:24 | TAS000006570731 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 16.12.2022 06:00:00 | 17.12.2022 18:00:00 | os-linux-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002061326 | MGT SAP System | Implementation In Progress | 08.08.2022 11:10:24 | 11.08.2022 11:10:24 | TAS000006580549 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 23.12.2022 20:00:00 | 24.12.2022 00:00:00 | os-linux-std-06:global:2nd | Makkena Raghava (EXT)
CRQ000002066916 | BRD SAP System | Implementation In Progress | 15.08.2022 16:01:52 | 18.08.2022 16:01:52 | TAS000006593458 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 23.12.2022 14:30:00 | 23.12.2022 18:30:00 | os-linux-std-06:global:2nd | Dilip Kumar (EXT)
CRQ000002068054 | RWI SAP System | Implementation In Progress | 17.08.2022 09:57:21 | 20.08.2022 09:57:21 | TAS000006596854 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 16.12.2022 00:00:00 | 16.12.2022 04:00:00 | os-linux-std-06:global:2nd | Manvendra Singh (EXT)
CRQ000002088573 | V20 SAP System | Implementation In Progress | 15.09.2022 14:14:04 | 18.09.2022 14:14:04 | TAS000006643296 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 23.12.2022 10:00:00 | 23.12.2022 14:00:00 | os-linux-std-06:global:2nd | Vishnu Athreya (EXT)
CRQ000002088579 | HRD SAP System | Implementation In Progress | 15.09.2022 14:31:04 | 18.09.2022 14:31:04 | TAS000006643531 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 20.12.2022 00:00:00 | 20.12.2022 04:00:00 | os-linux-std-06:global:2nd | Manvendra Singh (EXT)
CRQ000002101623 | FX1 SAP System | Implementation In Progress | 05.10.2022 13:00:27 | 08.10.2022 13:00:27 | TAS000006767410 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 15.12.2022 14:00:00 | 15.12.2022 18:00:00 | os-linux-std-06:global:2nd | amit sharma (EXT)
CRQ000002101633 | FX2 SAP System | Implementation In Progress | 05.10.2022 13:18:50 | 08.10.2022 13:18:50 | TAS000006768383 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 20.12.2022 14:00:00 | 20.12.2022 18:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002101659 | FX3 SAP System | Implementation In Progress | 05.10.2022 14:12:32 | 08.10.2022 14:12:32 | TAS000006768835 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 22.12.2022 14:00:00 | 22.12.2022 18:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002111392 | Connect Direct Installation and Migration | Scheduled | 13.11.2022 23:00:00 | 29.12.2022 23:00:00 | TAS000006697413 | server-unix-std:global¦06¦Initial-Rudder-CD-Installation | Assigned |  | 16.12.2022 07:00:00 | 16.12.2022 16:00:00 | os-linux-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002120037 | *MR+Veritas* *ESP* lp34d53/54 install Masterrelease | Scheduled | 17.12.2022 22:00:00 | 18.12.2022 05:00:00 | TAS000006716745 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 17.12.2022 22:00:00 | 18.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002120065 | *SLES12 SP5* *ESP* *lp34d51/52* upgrade to the new Version of SuSE SLES12 SP5 | Scheduled | 18.12.2022 20:00:00 | 19.12.2022 03:00:00 | TAS000006716797 | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Cluster) | Pending | Assignment | 18.12.2022 20:00:00 | 19.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002124204 | STARD: TGQ CS migration + DI replacement - implementation | Scheduled | 04.12.2022 05:00:00 | 16.12.2022 18:00:00 | TAS000006725801 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 22.12.2022 09:00:00 | 22.12.2022 13:00:00 | os-linux-std-06:global:2nd | Ashwini Tendulkar (EXT)
CRQ000002124204 | STARD: TGQ CS migration + DI replacement - implementation | Scheduled | 04.12.2022 05:00:00 | 16.12.2022 18:00:00 | TAS000006725812 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 22.12.2022 11:30:00 | 22.12.2022 15:00:00 | os-linux-std-06:global:2nd | Kishore Kumar (EXT)
CRQ000002124612 | MR Update on SolMan servers-lpssm09, lpssm10 | Implementation In Progress | 25.11.2022 05:30:00 | 31.01.2023 18:30:00 | TAS000006758222 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 17.12.2022 10:00:00 | 17.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002125016 | STARD: TXD CS migration + DI replacement - implementation | Scheduled | 18.12.2022 05:00:00 | 30.12.2022 18:00:00 | TAS000006727212 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 18.12.2022 09:00:00 | 18.12.2022 13:00:00 | os-linux-std-06:global:2nd | Tushar Lohia (EXT)
CRQ000002125016 | STARD: TXD CS migration + DI replacement - implementation | Scheduled | 18.12.2022 05:00:00 | 30.12.2022 18:00:00 | TAS000006728523 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 18.12.2022 11:30:00 | 18.12.2022 15:00:00 | os-linux-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002126431 | $1 "Colo Group Project" Moving server <lpsbdbs012> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006730898 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Pending | Assignment | 19.12.2022 08:00:00 | 19.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002126431 | $1 "Colo Group Project" Moving server <lpsbdbs012> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006730901 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 20.12.2022 09:30:00 | 20.12.2022 15:00:00 | os-unix-std-06:global:2nd
CRQ000002126431 | $1 "Colo Group Project" Moving server <lpsbdbs012> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006730905 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 21.12.2022 08:00:00 | 21.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002126580 | $1 "Colo Group Project" Moving server <lpdbs133> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731394 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Staged | Staging in Progress | 20.12.2022 08:00:00 | 20.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127032 | $1 "Colo Group Project" Moving server <lpdbs132> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 23.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731384 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 15.12.2022 08:00:00 | 15.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127117 | $1 "Colo Group Project" Moving server <lpdbs136> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 23.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006732018 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 15.12.2022 08:00:00 | 15.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127120 | $1 "Colo Group Project" Moving server <lpdbs138> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 23.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006732260 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 15.12.2022 08:00:00 | 15.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127216 | Planned Power shutdown 16.47 Miramas - UPS Replacement | Scheduled | 19.12.2022 06:00:00 | 21.12.2022 19:30:00 | TAS000006746565 | server-win:emea¦Shutdown_Server_Unix | Pending | Assignment | 19.12.2022 08:30:00 | 21.12.2022 17:30:00 | os-unix-std-06:global:2nd
CRQ000002127315 | $1 "Colo Group Project" Moving server <lpdbs131> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731817 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Staged | Staging in Progress | 20.12.2022 08:00:00 | 20.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127317 | $1 "Colo Group Project" Moving server <lpdbs135> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006732238 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 15.12.2022 09:30:00 | 15.12.2022 15:00:00 | os-unix-std-06:global:2nd
CRQ000002127317 | $1 "Colo Group Project" Moving server <lpdbs135> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006732242 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 16.12.2022 08:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127319 | $1 "Colo Group Project" Moving server <lpdbs137> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006732336 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 15.12.2022 09:30:00 | 15.12.2022 15:00:00 | os-unix-std-06:global:2nd
CRQ000002127319 | $1 "Colo Group Project" Moving server <lpdbs137> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006732340 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 16.12.2022 08:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127321 | $1 "Colo Group Project" Moving server <ltdbs006> to new location | Implementation In Progress | 24.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731412 | readyops:global¦Pre-check-OS-team_unix-single-san-complex | Staged | Staging in Progress | 16.12.2022 08:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127321 | $1 "Colo Group Project" Moving server <ltdbs006> to new location | Implementation In Progress | 24.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731415 | readyops:global¦Supervise-servermove_unix-single-san-complex | Staged | Staging in Progress | 21.12.2022 09:30:00 | 21.12.2022 15:00:00 | os-unix-std-06:global:2nd
CRQ000002127321 | $1 "Colo Group Project" Moving server <ltdbs006> to new location | Implementation In Progress | 24.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731419 | readyops:global¦SAN-mirror-unix-single | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127753 | *MR+VERITAS* *ESP* lpkrd07/08 install Masterrelease | Scheduled For Approval | 17.12.2022 16:00:00 | 17.12.2022 23:00:00 | TAS000006735046 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Staged | Staging in Progress | 17.12.2022 16:30:00 | 17.12.2022 22:30:00 | os-unix-std-06:global:2nd
CRQ000002128060 | *MR+VERITAS* *ESP* lpkrd04/05 install Masterrelease | Scheduled For Approval | 17.12.2022 16:30:00 | 17.12.2022 23:00:00 | TAS000006735035 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Staged | Staging in Progress | 17.12.2022 16:30:00 | 17.12.2022 22:30:00 | os-unix-std-06:global:2nd
CRQ000002128803 | *SLES12 SP5* *GMA* upgrade to the new Version of SuSE SLES12 SP5 | Implementation In Progress | 27.11.2022 07:00:00 | 17.12.2022 17:00:00 | TAS000006747256 | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (VM) | Pending | Assignment | 17.12.2022 02:00:00 | 17.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002128803 | *SLES12 SP5* *GMA* upgrade to the new Version of SuSE SLES12 SP5 | Implementation In Progress | 27.11.2022 07:00:00 | 17.12.2022 17:00:00 | TAS000006736858 | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (VM) | Pending | Assignment | 17.12.2022 15:00:00 | 17.12.2022 17:00:00 | os-unix-std-06:global:2nd
CRQ000002132514 | *MR+Veritas* *GMA* lpdbs115/116 install Masterrelease | Scheduled | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | TAS000006744297 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002133911 | *MR* *GMA* VMs install Masterrelease | Implementation In Progress | 10.12.2022 10:00:00 | 18.12.2022 18:00:00 | TAS000006748476 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 18.12.2022 15:00:00 | 18.12.2022 17:00:00 | os-unix-std-06:global:2nd
CRQ000002134463 | IPS-I-P34-PROD - Update Masterrelease | Scheduled | 17.12.2022 19:00:00 | 18.12.2022 06:00:00 | TAS000006750323 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 17.12.2022 19:30:00 | 17.12.2022 21:30:00 | os-unix-std-06:global:2nd
CRQ000002134463 | IPS-I-P34-PROD - Update Masterrelease | Scheduled | 17.12.2022 19:00:00 | 18.12.2022 06:00:00 | TAS000006750324 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 17.12.2022 19:30:00 | 17.12.2022 21:30:00 | os-unix-std-06:global:2nd
CRQ000002134463 | IPS-I-P34-PROD - Update Masterrelease | Scheduled | 17.12.2022 19:00:00 | 18.12.2022 06:00:00 | TAS000006750325 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 17.12.2022 19:30:00 | 17.12.2022 21:30:00 | os-unix-std-06:global:2nd
CRQ000002134463 | IPS-I-P34-PROD - Update Masterrelease | Scheduled | 17.12.2022 19:00:00 | 18.12.2022 06:00:00 | TAS000006750326 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 17.12.2022 19:30:00 | 17.12.2022 21:30:00 | os-unix-std-06:global:2nd
CRQ000002134463 | IPS-I-P34-PROD - Update Masterrelease | Scheduled | 17.12.2022 19:00:00 | 18.12.2022 06:00:00 | TAS000006750327 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 17.12.2022 19:30:00 | 17.12.2022 21:30:00 | os-unix-std-06:global:2nd
CRQ000002134463 | IPS-I-P34-PROD - Update Masterrelease | Scheduled | 17.12.2022 19:00:00 | 18.12.2022 06:00:00 | TAS000006750328 | server-unix-std:global¦06¦070-OS-config-check_IPS_I | Pending | Assignment | 17.12.2022 21:30:00 | 18.12.2022 01:30:00 | os-unix-std-06:global:2nd
CRQ000002134715 | Farm replacement <lp02xenmq03/04> VM's Offline Migration | Scheduled | 19.12.2022 11:00:00 | 31.12.2022 11:00:00 | TAS000006749615 | server-unix-std:global¦06¦084c-move-farm-prep-(NSTC) | Pending | Assignment | 19.12.2022 11:00:00 | 22.12.2022 11:00:00 | os-unix-std-06:global:2nd
CRQ000002135229 | SAN GS 3: SAN_MICROCODE_UPDATE GMA3S1 (BGs) | Scheduled | 19.12.2022 08:00:00 | 19.12.2022 16:00:00 | TAS000006750593 | NTT Unix: SAN GS 3: SAN_MICROCODE_UPDATE GMA3S1 (BGs) | Pending | Assignment | 19.12.2022 08:00:00 | 19.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002135781 | SAN GS 3: SAN_MICROCODE_UPDATE GMA311 (BGs) | Scheduled | 20.12.2022 08:00:00 | 20.12.2022 16:00:00 | TAS000006754377 | NTT Unix: SAN GS 3: SAN_MICROCODE_UPDATE GMA311 (BGs) | Pending | Assignment | 20.12.2022 08:00:00 | 20.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002136172 | SAN GS 3: SAN_MICROCODE_UPDATE GMA312 (BGs) | Scheduled | 21.12.2022 08:00:00 | 21.12.2022 16:00:00 | TAS000006754406 | NTT Unix: SAN GS 3: SAN_MICROCODE_UPDATE GMA312 (BGs) | Pending | Assignment | 21.12.2022 08:00:00 | 21.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002136178 | SAN GS 3: SAN_MICROCODE_UPDATE GMA313 (BGs) | Scheduled | 22.12.2022 08:00:00 | 22.12.2022 16:00:00 | TAS000006754663 | NTT Unix: SAN GS 3: SAN_MICROCODE_UPDATE GMA313 (BGs) | Pending | Assignment | 22.12.2022 08:00:00 | 22.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002136190 | SAN #Data: SAN_MICROCODE_UPDATE AAR401 / BRE401 | Scheduled | 18.12.2022 08:00:00 | 18.12.2022 16:00:00 | TAS000006755447 | NTT Unix: SAN #Data: SAN_MICROCODE_UPDATE AAR401 / BRE401 | Pending | Assignment | 18.12.2022 08:00:00 | 18.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002137234 | *PKG-MOVE* *GSP* MOVE package from lp02d55/56 to lp02db005/006 | Scheduled For Approval | 22.12.2022 11:00:00 | 08.01.2023 23:00:00 | TAS000006756791 | server-unix-std:global¦06¦022c-cluster-prepare-migrate-package | Staged | Staging in Progress | 22.12.2022 11:00:00 | 25.12.2022 23:00:00 | os-unix-std-06:global:2nd
CRQ000002137598 | *MR+Veritas* *GMA* lpdbs117/118 install Masterrelease | Scheduled | 18.12.2022 01:00:00 | 18.12.2022 08:00:00 | TAS000006757790 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 18.12.2022 01:00:00 | 18.12.2022 07:00:00 | os-unix-std-06:global:2nd
CRQ000002137992 | *MR+Veritas* *GMA* install Masterrelease-lpdbvdm07_lpdbvdm08 | Scheduled | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | TAS000006758400 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002137992 | *MR+Veritas* *GMA* install Masterrelease | Scheduled | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | TAS000006766509 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 18.12.2022 21:00:00 | 18.12.2022 23:00:00 | os-unix-std-06:global:2nd
CRQ000002139200 | SAN_MIG ¦ AAR401 ¦ li16db002 | Implementation In Progress | 02.12.2022 09:00:00 | 04.01.2023 17:00:00 | TAS000006761961 | MIG_SERVER: Verification during SAN migration | Assigned |  | 15.12.2022 08:00:00 | 15.12.2022 11:00:00 | os-unix-std-06:global:2nd | Tushar Lohia (EXT)
CRQ000002139407 | *PKG-MOVE* *GSP* MOVE packages from lp02d53/54 to lp02db003/004 | Scheduled For Approval | 22.12.2022 18:00:00 | 04.01.2023 19:00:00 | TAS000006761565 | server-unix-std:global¦06¦022c-cluster-prepare-migrate-package | Staged | Staging in Progress | 22.12.2022 18:00:00 | 25.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002139706 | SAN_MIG ¦ BRE401 ¦ li16db001 | Implementation In Progress | 02.12.2022 09:00:00 | 05.01.2023 17:00:00 | TAS000006761979 | MIG_SERVER: Verification during SAN migration | Assigned |  | 15.12.2022 13:00:00 | 15.12.2022 16:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002139722 | SAN_MIG ¦ BEJ401 ¦ lt19xen23/24_lt19xen31/32_lt19xens11/12 | Implementation In Progress | 08.12.2022 09:00:00 | 12.01.2023 17:00:00 | TAS000006762529 | MIG_SERVER: Verification during SAN migration | Pending | Assignment | 21.12.2022 08:00:00 | 21.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002139916 | VMs Offline Migration from xenfarm node- ltxen1033 | Scheduled | 19.12.2022 20:00:00 | 21.12.2022 20:00:00 | TAS000006781657 | [VMs Offline Migration] | Pending | Assignment | 19.12.2022 20:00:00 | 20.12.2022 00:00:00 | os-unix-std-06:global:2nd
CRQ000002139916 | VMs Offline Migration from xenfarm node- ltxen1033 | Scheduled | 19.12.2022 20:00:00 | 21.12.2022 20:00:00 | TAS000006781836 | [VMs Offline Migration] | Pending | Assignment | 20.12.2022 00:00:00 | 20.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002139916 | VMs Offline Migration from xenfarm node- ltxen1033 | Scheduled | 19.12.2022 20:00:00 | 21.12.2022 20:00:00 | TAS000006781650 | [OS Re-installation ¦¦ SLES-12 SP5] | Pending | Assignment | 20.12.2022 10:00:00 | 20.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002140000 | Postgres VMs Online Migration / MR + Firmware Update for Q4 2022 | Implementation In Progress | 29.11.2022 12:00:00 | 31.12.2022 00:00:00 | TAS000006768164 | [MR + Firmware Update + Reboot] | Pending | Assignment | 18.12.2022 20:00:00 | 19.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002140992 | RS Production C:D Version Upgrade to fix security vulnerabilities 6.x | Implementation In Progress | 10.12.2022 16:00:00 | 18.12.2022 10:00:00 | TAS000006766638 | server-unix-std:global¦06¦070c-modify-system | Assigned |  | 16.12.2022 16:00:00 | 16.12.2022 20:00:00 | os-linux-std-06:global:2nd | Prodyut Paul (EXT)
CRQ000002141201 | STARD: SND CS migration - implementation | Implementation In Progress | 12.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006764688 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 16.12.2022 10:00:00 | 16.12.2022 14:00:00 | os-linux-std-06:global:2nd | Prodyut Paul (EXT)
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778216 | server-unix-std:global¦06¦085c-move-farm-exec | Assigned |  | 17.12.2022 00:00:00 | 17.12.2022 04:00:00 | os-unix-std-06:global:2nd | KumaraSwamy Nasika (EXT)
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778217 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 17.12.2022 04:00:00 | 17.12.2022 08:00:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778218 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 17.12.2022 08:00:00 | 17.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778219 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 17.12.2022 12:00:00 | 17.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778656 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 17.12.2022 16:00:00 | 17.12.2022 20:00:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778943 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 17.12.2022 20:00:00 | 18.12.2022 00:00:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778944 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 18.12.2022 00:00:00 | 18.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778945 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 18.12.2022 04:00:00 | 18.12.2022 08:00:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778220 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 21.12.2022 09:00:00 | 26.12.2022 09:00:00 | os-unix-std-06:global:2nd
CRQ000002144399 | $1 "Colo Group Project" Moving server <lpdbs140> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006774915 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Pending | Assignment | 19.12.2022 08:00:00 | 19.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144399 | $1 "Colo Group Project" Moving server <lpdbs140> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006774918 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 20.12.2022 09:30:00 | 20.12.2022 15:00:00 | os-unix-std-06:global:2nd
CRQ000002144399 | $1 "Colo Group Project" Moving server <lpdbs140> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775722 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 21.12.2022 08:00:00 | 21.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144834 | #PROD - Informatica NA migration from Xen to VMWare Status | Implementation In Progress | 16.12.2022 18:30:00 | 18.12.2022 22:30:00 | TAS000006774976 | server-unix-std:global¦06¦070c-modify-system | Staged | Staging in Progress | 16.12.2022 23:30:00 | 18.12.2022 23:30:00 | os-unix-std-06:global:2nd
CRQ000002144834 | #PROD - Informatica NA migration from Xen to VMWare Status | Implementation In Progress | 16.12.2022 18:30:00 | 18.12.2022 22:30:00 | TAS000006774975 | server-unix-std:global¦06¦070c-modify-system | Assigned |  | 16.12.2022 21:00:00 | 18.12.2022 21:30:00 | os-linux-std-06:global:2nd | Makkena Raghava (EXT)
CRQ000002144907 | ##T##D## Preparation for decommissioning EDBIC PROD&INT-Server | Implementation In Progress | 02.12.2022 20:00:00 | 05.12.2022 20:00:00 | TAS000006774206 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Pending | Assignment | 19.12.2022 21:00:00 | 21.12.2022 21:00:00 | os-unix-std-06:global:2nd
CRQ000002144907 | ##T##D## Preparation for decommissioning EDBIC PROD&INT-Server | Implementation In Progress | 02.12.2022 20:00:00 | 05.12.2022 20:00:00 | TAS000006774207 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Pending | Assignment | 19.12.2022 21:00:00 | 21.12.2022 21:00:00 | os-unix-std-06:global:2nd
CRQ000002144907 | ##T##D## Preparation for decommissioning EDBIC PROD&INT-Server | Implementation In Progress | 02.12.2022 20:00:00 | 05.12.2022 20:00:00 | TAS000006774208 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Pending | Assignment | 19.12.2022 21:00:00 | 21.12.2022 21:00:00 | os-unix-std-06:global:2nd
CRQ000002144907 | ##T##D## Preparation for decommissioning EDBIC PROD&INT-Server | Implementation In Progress | 02.12.2022 20:00:00 | 05.12.2022 20:00:00 | TAS000006774209 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Pending | Assignment | 19.12.2022 21:00:00 | 21.12.2022 21:00:00 | os-unix-std-06:global:2nd
CRQ000002144927 | $1 "Colo Group Project" Moving server <lpdbs130> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775255 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Assigned |  | 16.12.2022 08:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002144927 | $1 "Colo Group Project" Moving server <lpdbs130> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775258 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 20.12.2022 09:30:00 | 20.12.2022 15:00:00 | os-unix-std-06:global:2nd
CRQ000002144927 | $1 "Colo Group Project" Moving server <lpdbs130> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775262 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 21.12.2022 08:00:00 | 21.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002145308 | $1 "Colo Group Project" Moving server <lpsbdbs014> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006775315 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Pending | Assignment | 19.12.2022 08:00:00 | 19.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002145308 | $1 "Colo Group Project" Moving server <lpsbdbs014> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006775318 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 20.12.2022 09:30:00 | 20.12.2022 15:00:00 | os-unix-std-06:global:2nd
CRQ000002145308 | $1 "Colo Group Project" Moving server <lpsbdbs014> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006775822 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 21.12.2022 08:00:00 | 21.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002145522 | $1 "Colo Group Project" Moving server <lpsbdbs016> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006776778 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Pending | Assignment | 19.12.2022 08:00:00 | 19.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002145643 | *ORA-OFFMIG* lpdboctanevm from lpxendb410 to lpxendb409 | Scheduled | 17.12.2022 08:00:00 | 17.12.2022 11:00:00 | TAS000006777107 | [OS VM offline Migration] lpdboctanevm from lpxendb410 to lpxendb409 | Pending | Assignment | 17.12.2022 08:00:00 | 17.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002145851 | [OS Online/Offline Migration] | Scheduled | 17.12.2022 20:00:00 | 31.12.2022 00:00:00 | TAS000006777812 | [OS Online/Offline Migration] lpxensor17 | Pending | Assignment | 17.12.2022 20:00:00 | 17.12.2022 21:00:00 | os-unix-std-06:global:2nd
CRQ000002146592 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor17/18> | Implementation In Progress | 12.12.2022 10:00:00 | 27.12.2022 00:00:00 | TAS000006779991 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 19.12.2022 22:00:00 | 20.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002146592 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor17/18> | Implementation In Progress | 12.12.2022 10:00:00 | 27.12.2022 00:00:00 | TAS000006781222 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 20.12.2022 02:00:00 | 20.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002146592 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor17/18> | Implementation In Progress | 12.12.2022 10:00:00 | 27.12.2022 00:00:00 | TAS000006781224 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 20.12.2022 10:00:00 | 25.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002146600 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp07dbipsq001/002 | Scheduled For Approval | 22.12.2022 08:00:00 | 22.12.2022 15:00:00 | TAS000006780788 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 14:00:00 | os-unix-std-06:global:2nd
CRQ000002146600 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp07dbipsq001/002 | Scheduled For Approval | 22.12.2022 08:00:00 | 22.12.2022 15:00:00 | TAS000006780790 | server-unix-std:global¦06¦050c-network-mgmt | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 14:00:00 | os-unix-std-06:global:2nd
CRQ000002146628 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor19/20> | Implementation In Progress | 12.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006780342 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 19.12.2022 22:00:00 | 20.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002146963 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor15/16> | Implementation In Progress | 12.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006780821 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 20.12.2022 00:00:00 | 20.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002146963 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor15/16> | Implementation In Progress | 12.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006781822 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 21.12.2022 10:00:00 | 28.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002147075 | $1 "Colo Group Project" Moving server <lpdbs150> to new location | Implementation In Progress | 08.12.2022 09:00:00 | 31.01.2023 18:00:00 | TAS000006782835 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002147179 | $1 "Colo Group Project" Moving server <lpdbs144> to new location | Implementation In Progress | 07.12.2022 09:00:00 | 31.01.2023 18:00:00 | TAS000006781574 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Staged | Staging in Progress | 21.12.2022 09:00:00 | 21.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002147182 | $1 "Colo Group Project" Moving server <lpdbs146> to new location | Implementation In Progress | 07.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006781598 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Staged | Staging in Progress | 22.12.2022 09:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002147303 | $1 "Colo Group Project" Moving server <lpdbs142> to new location | Implementation In Progress | 07.12.2022 09:00:00 | 31.01.2023 18:00:00 | TAS000006780687 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Pending | Assignment | 21.12.2022 08:00:00 | 21.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002147341 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor15/16> | Implementation In Progress | 13.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006782493 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 20.12.2022 02:00:00 | 20.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002147341 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensor15/16> | Implementation In Progress | 13.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006781704 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 20.12.2022 10:00:00 | 26.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002147712 | $1 "Colo Group Project" Moving server <lpdbs148> to new location | Implementation In Progress | 08.12.2022 09:00:00 | 31.01.2023 18:00:00 | TAS000006782381 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Staged | Staging in Progress | 22.12.2022 09:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002147935 | *DB_MOVE* *GMA* MOVE to lpdbs103/104 | Scheduled | 15.12.2022 06:00:00 | 09.01.2023 23:00:00 | TAS000006783152 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Assigned |  | 15.12.2022 12:00:00 | 17.12.2022 12:00:00 | os-unix-std-06:global:2nd | Vinayak Awasthi (EXT)
CRQ000002147984 | ORA-OFFMIG* ltbkdbtde038vm VM from ltbkxendb31_32 to ltbkxendb53_54 | Implementation In Progress | 11.12.2022 14:00:00 | 20.12.2022 15:00:00 | TAS000006782916 | server-unix-std:global¦06¦082c-move-vm-exec | Assigned |  | 16.12.2022 20:00:00 | 16.12.2022 22:00:00 | os-unix-std-06:global:2nd | Manvendra Singh (EXT)
CRQ000002147984 | ORA-OFFMIG* ltbkdbtde038vm VM from ltbkxendb31_32 to ltbkxendb53_54 | Implementation In Progress | 11.12.2022 14:00:00 | 20.12.2022 15:00:00 | TAS000006782917 | server-unix-std:global¦06¦083c-move-vm-cleanup-(NSTC) | Pending | Assignment | 17.12.2022 14:00:00 | 20.12.2022 14:00:00 | os-unix-std-06:global:2nd
CRQ000002148411 | Host: lplogstash1vm.bmwgroup.net Service: os_linux_fs_check_btrfs State: CRITICAL | Planning In Progress |  |  | TAS000006783769 | BTRFS Balance | Staged | Staging in Progress | 17.12.2022 22:30:00 | 18.12.2022 02:30:00 | os-unix-std-06:global:2nd
CRQ000002148692 | DAM16 PROD - Upgrade SLES12 SP2 to SLES12 SP5 | Scheduled | 21.12.2022 04:00:00 | 21.12.2022 10:00:00 | TAS000006785408 | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (VM) | Assigned |  | 21.12.2022 04:00:00 | 21.12.2022 10:00:00 | os-linux-std-06:global:2nd | Kamendra Chauhan (EXT)
CRQ000002148748 | DAM16 PROD - Upgrade SLES12 SP2 to SLES12 SP5 | Scheduled | 20.12.2022 04:00:00 | 20.12.2022 08:00:00 | TAS000006785730 | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (VM) | Pending | Assignment | 20.12.2022 04:00:00 | 20.12.2022 08:00:00 | os-unix-std-06:global:2nd
CRQ000002148920 | DAM16 PROD - Upgrade SLES12 SP2 to SLES12 SP5 | Scheduled | 19.12.2022 03:30:00 | 19.12.2022 10:00:00 | TAS000006785243 | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (VM) | Pending | Assignment | 19.12.2022 04:00:00 | 19.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002148932 | STI/STP: Install C:D override on new CS servers | Scheduled | 19.12.2022 12:00:00 | 21.12.2022 12:00:00 | TAS000006784991 | server-unix-std:global¦045s-install-override-(NSTC) | Assigned |  | 19.12.2022 12:00:00 | 21.12.2022 12:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002148932 | STI/STP: Install C:D override on new CS servers | Scheduled | 19.12.2022 12:00:00 | 21.12.2022 12:00:00 | TAS000006784992 | server-unix-std:global¦045s-install-override-(NSTC) | Assigned |  | 19.12.2022 12:00:00 | 21.12.2022 12:00:00 | os-linux-std-06:global:2nd | Prodyut Paul (EXT)
CRQ000002149277 | Update TIM GF4 INT C:D node | Scheduled | 16.12.2022 14:00:00 | 16.12.2022 18:00:00 | TAS000006787225 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 16.12.2022 14:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002149528 | IPS-I-P09-PROD - Update Masterrelease | Scheduled | 16.12.2022 10:00:00 | 16.12.2022 22:00:00 | TAS000006789242 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 16.12.2022 11:00:00 | 16.12.2022 13:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002149528 | IPS-I-P09-PROD - Update Masterrelease | Scheduled | 16.12.2022 10:00:00 | 16.12.2022 22:00:00 | TAS000006789243 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 16.12.2022 11:00:00 | 16.12.2022 13:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002149528 | IPS-I-P09-PROD - Update Masterrelease | Scheduled | 16.12.2022 10:00:00 | 16.12.2022 22:00:00 | TAS000006789526 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 16.12.2022 11:00:00 | 16.12.2022 13:00:00 | os-unix-std-06:global:2nd | Nanda Padala (EXT)
CRQ000002149528 | IPS-I-P09-PROD - Update Masterrelease | Scheduled | 16.12.2022 10:00:00 | 16.12.2022 22:00:00 | TAS000006789828 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 16.12.2022 11:00:00 | 16.12.2022 13:00:00 | os-unix-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002149528 | IPS-I-P09-PROD - Update Masterrelease | Scheduled | 16.12.2022 10:00:00 | 16.12.2022 22:00:00 | TAS000006789829 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 16.12.2022 11:00:00 | 16.12.2022 13:00:00 | os-unix-std-06:global:2nd | Nanda Padala (EXT)
CRQ000002149528 | IPS-I-P09-PROD - Update Masterrelease | Scheduled | 16.12.2022 10:00:00 | 16.12.2022 22:00:00 | TAS000006789630 | server-unix-std:global¦06¦070-OS-config-check_IPS_I | Assigned |  | 16.12.2022 13:00:00 | 16.12.2022 17:00:00 | os-unix-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002149655 | Update GAMMA GF4 PROD C:D node | Implementation In Progress | 16.12.2022 14:00:00 | 16.12.2022 18:00:00 | TAS000006786783 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 16.12.2022 14:00:00 | 16.12.2022 18:00:00 | os-unix-std-06:global:2nd | Nanda Padala (EXT)
CRQ000002149938 | BRD (Brazil Development) VMWare Installation and Migration | Scheduled For Approval | 14.12.2022 14:00:00 | 07.01.2023 11:00:00 | TAS000006787936 | Confirm Timezones on the NEW Servers for BRD System | Staged | Staging in Progress | 19.12.2022 07:00:00 | 21.12.2022 15:00:00 | os-linux-std-06:global:2nd
CRQ000002150029 | #Migration Linux VM #Global#Downtime#2h#CCM_HR PROD | Scheduled | 16.12.2022 23:00:00 | 18.12.2022 22:00:00 | TAS000006787655 | server-unix-std:global¦06¦050c-network-mgmt | Assigned |  | 17.12.2022 13:00:00 | 17.12.2022 15:00:00 | os-linux-std-06:global:2nd | Kishore Kumar (EXT)
CRQ000002150106 | *PKG-MOVE* *GSP* MOVE package dbprof50 from lp07db003/004 to lp07db001/002 | Scheduled For Approval | 15.12.2022 12:00:00 | 27.12.2022 23:00:00 | TAS000006786884 | server-unix-std:global¦06¦022c-cluster-prepare-migrate-package | Staged | Staging in Progress | 15.12.2022 12:00:00 | 18.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002150106 | *PKG-MOVE* *GSP* MOVE package dbprof50 from lp07db003/004 to lp07db001/002 | Scheduled For Approval | 15.12.2022 12:00:00 | 27.12.2022 23:00:00 | TAS000006786885 | server-unix-std:global¦06¦023c-cluster-migrate-package | Staged | Staging in Progress | 19.12.2022 01:00:00 | 19.12.2022 03:00:00 | os-unix-std-06:global:2nd
CRQ000002150106 | *PKG-MOVE* *GSP* MOVE package dbprof50 from lp07db003/004 to lp07db001/002 | Scheduled For Approval | 15.12.2022 12:00:00 | 27.12.2022 23:00:00 | TAS000006786886 | server-unix-std:global¦06¦024c-cluster-migrate-cleanup-(NSTC) | Staged | Staging in Progress | 20.12.2022 23:00:00 | 27.12.2022 23:00:00 | os-unix-std-06:global:2nd
CRQ000002150964 | Update GAMMA GF5 INT C:D nodes | Implementation In Progress | 19.12.2022 14:00:00 | 19.12.2022 18:00:00 | TAS000006789642 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 19.12.2022 14:00:00 | 19.12.2022 18:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002151025 | Update FKD GF5 PROD C:D nodes | Implementation In Progress | 21.12.2022 14:00:00 | 21.12.2022 18:00:00 | TAS000006789839 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 21.12.2022 14:00:00 | 21.12.2022 18:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002151039 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensdi21/22> | Implementation In Progress | 14.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006790740 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 22.12.2022 20:00:00 | 23.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002151156 | Moving server <LI30YXQ04; LP30TNP08; LP30TNP10> to new location | Implementation In Progress | 12.12.2022 14:15:00 | 31.01.2023 18:00:00 | TAS000006789519 | readyops:global¦Pre-check-OS-team_unix-single-san | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002151287 | Moving server <LP30D08; LP30D10; LP30D12> to new location | Implementation In Progress | 12.12.2022 14:15:00 | 31.01.2023 18:00:00 | TAS000006791035 | readyops:global¦Pre-check-OS-team_unix-single-san | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002151429 | Update GAMMA GF5 PROD C:D nodes | Implementation In Progress | 21.12.2022 14:00:00 | 21.12.2022 18:00:00 | TAS000006789545 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 21.12.2022 14:00:00 | 21.12.2022 18:00:00 | os-linux-std-06:global:2nd | Kishore Kumar (EXT)
CRQ000002151435 | Update FKD GF5 INT C:D nodes | Implementation In Progress | 19.12.2022 14:00:00 | 19.12.2022 18:00:00 | TAS000006789259 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 19.12.2022 14:00:00 | 19.12.2022 18:00:00 | os-linux-std-06:global:2nd | Kishore Kumar (EXT)
CRQ000002151554 | Shutdown empty ORACLE GMA Server until 03/2023 - ORACLE POOL Server | Implementation In Progress | 13.12.2022 12:00:00 | 31.03.2023 12:00:00 | TAS000006793517 | Shutdown empty ORACLE GMA Server until 03/2023 - ORACLE POOL Server Disable Monitoring | Assigned |  | 15.12.2022 13:00:00 | 16.12.2022 06:00:00 | os-unix-std-06:global:2nd | Nanda Padala (EXT)
CRQ000002151581 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensdi21/22> | Implementation In Progress | 14.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006791352 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 22.12.2022 02:00:00 | 22.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002151581 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensdi21/22> | Implementation In Progress | 14.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006791622 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 22.12.2022 10:00:00 | 29.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002151602 | Critical BTRFS Balancing (lpszmq01vm) | Scheduled | 18.12.2022 01:00:00 | 18.12.2022 03:00:00 | TAS000006789858 | Critical BTRFS Balancing (lpszmq01vm) | Pending | Assignment | 18.12.2022 01:00:00 | 18.12.2022 03:00:00 | os-unix-std-06:global:2nd
CRQ000002151643 | Moving server <LP30D07; LP30D09; LP30D11; LT30D02> to new location | Implementation In Progress | 12.12.2022 13:30:00 | 31.01.2023 18:00:00 | TAS000006789316 | readyops:global¦Pre-check-OS-team_unix-single-san | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002151645 | Moving server <LP30TNP07> to new location | Implementation In Progress | 12.12.2022 13:35:00 | 31.01.2023 18:00:00 | TAS000006791132 | readyops:global¦Pre-check-OS-team_unix-single-san | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002151651 | Moving server < LP30TNP09; LP30TNP11; LP30YXP09> to new location | Implementation In Progress | 12.12.2022 13:40:00 | 31.01.2023 18:00:00 | TAS000006791146 | readyops:global¦Pre-check-OS-team_unix-single-no-san | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002151655 | Moving server <LP30TNP12; LP30YXP10> to new location | Implementation In Progress | 12.12.2022 14:15:00 | 31.01.2023 18:00:00 | TAS000006789612 | readyops:global¦Pre-check-OS-team_unix-single-no-san | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002151825 | Reboot the xenfarm node- lpxenppg072 | Scheduled | 15.12.2022 00:00:00 | 20.12.2022 00:00:00 | TAS000006792074 | Reboot the xenfarm node ¦ lpxenppg072 | Assigned |  | 15.12.2022 22:00:00 | 16.12.2022 00:00:00 | os-unix-std-06:global:2nd | Rohit Varmani (EXT)
CRQ000002151868 | IBM Integration Bus - Operational activities for the month December 2022 | Implementation In Progress | 13.12.2022 11:30:00 | 15.01.2023 06:30:00 | TAS000006793186 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 16.12.2022 12:15:00 | 16.12.2022 18:15:00 | os-unix-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002151873 | STE: Upgrade C:D | Scheduled | 18.12.2022 10:00:00 | 18.12.2022 14:00:00 | TAS000006792089 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 18.12.2022 10:00:00 | 18.12.2022 12:00:00 | os-linux-std-06:global:2nd | Vinayak Awasthi (EXT)
CRQ000002151877 | *PKG-MOVE* *GMA* MOVE package plfasi01 from lpdbfips01/02 to lpdbfips001/002. | Implementation In Progress | 13.12.2022 19:00:00 | 26.12.2022 23:00:00 | TAS000006792367 | server-unix-std:global¦06¦023c-cluster-migrate-package | Pending | Assignment | 17.12.2022 08:00:00 | 17.12.2022 11:00:00 | os-unix-std-06:global:2nd
CRQ000002151877 | *PKG-MOVE* *GMA* MOVE package plfasi01 from lpdbfips01/02 to lpdbfips001/002. | Implementation In Progress | 13.12.2022 19:00:00 | 26.12.2022 23:00:00 | TAS000006792368 | server-unix-std:global¦06¦024c-cluster-migrate-cleanup-(NSTC) | Pending | Assignment | 18.12.2022 08:00:00 | 26.12.2022 08:00:00 | os-unix-std-06:global:2nd
CRQ000002151879 | STI: Upgrade C:D | Scheduled | 18.12.2022 10:00:00 | 18.12.2022 14:00:00 | TAS000006792172 | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | Assigned |  | 18.12.2022 10:00:00 | 18.12.2022 12:00:00 | os-linux-std-06:global:2nd | Narugopal Pal (EXT)
CRQ000002152309 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensdi21/22> | Implementation In Progress | 14.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006792533 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 21.12.2022 20:00:00 | 22.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002152309 | Farm replacement - Please offline migrate vm's from Xenfarm <ltxensdi21/22> | Implementation In Progress | 14.12.2022 10:00:00 | 31.12.2022 00:00:00 | TAS000006792346 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 22.12.2022 10:00:00 | 29.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002152388 | #P#DE#Downtime#NONE#AL Claims - Change AVL scan version | Scheduled | 15.12.2022 11:00:00 | 15.12.2022 17:00:00 | TAS000006793207 | server-unix-std:global¦06¦100a-VirusProtection-Installation-(NSTC) | Assigned |  | 15.12.2022 11:00:00 | 15.12.2022 17:00:00 | os-unix-std-06:global:2nd | Christian Basler
CRQ000002152772 | M2P/M6P/M7P: Master Release Patch M22Q04 | Scheduled For Approval | 18.12.2022 02:00:00 | 18.12.2022 07:00:00 | TAS000006793751 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Staged | Staging in Progress | 18.12.2022 02:00:00 | 18.12.2022 06:00:00 | os-unix-std-06:global:2nd
CRQ000002152772 | M2P/M6P/M7P: Master Release Patch M22Q04 | Scheduled For Approval | 18.12.2022 02:00:00 | 18.12.2022 07:00:00 | TAS000006793753 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Staged | Staging in Progress | 18.12.2022 02:00:00 | 18.12.2022 06:00:00 | os-unix-std-06:global:2nd
CRQ000002152772 | M2P/M6P/M7P: Master Release Patch M22Q04 | Scheduled For Approval | 18.12.2022 02:00:00 | 18.12.2022 07:00:00 | TAS000006793754 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Staged | Staging in Progress | 18.12.2022 02:00:00 | 18.12.2022 06:00:00 | os-unix-std-06:global:2nd
CRQ000002152772 | M2P/M6P/M7P: Master Release Patch M22Q04 | Scheduled For Approval | 18.12.2022 02:00:00 | 18.12.2022 07:00:00 | TAS000006793755 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Staged | Staging in Progress | 18.12.2022 02:00:00 | 18.12.2022 06:00:00 | os-unix-std-06:global:2nd
CRQ000002152772 | M2P/M6P/M7P: Master Release Patch M22Q04 | Scheduled For Approval | 18.12.2022 02:00:00 | 18.12.2022 07:00:00 | TAS000006793756 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Staged | Staging in Progress | 18.12.2022 02:00:00 | 18.12.2022 06:00:00 | os-unix-std-06:global:2nd
CRQ000002152772 | M2P/M6P/M7P: Master Release Patch M22Q04 | Scheduled For Approval | 18.12.2022 02:00:00 | 18.12.2022 07:00:00 | TAS000006793757 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Staged | Staging in Progress | 18.12.2022 02:00:00 | 18.12.2022 06:00:00 | os-unix-std-06:global:2nd

## MasterSheet-2
CRQ Number | CRQ Description | CRQ Status | CRQ Start Date | CRQ End Date | Linux Tasks in CRQ | Task Description | Task Status | Task Status 1 | Task Start Date | Task End Date | Xen/VMWare | Assignee
CRQ000002035384,CRQ000002036566,CRQ000002056956,CRQ000002061326,CRQ000002066916,CRQ000002068054,CRQ000002088573,CRQ000002088579,CRQ000002101623,CRQ000002101633,CRQ000002101659 | GTZ GUI WYT MGT BRD RWI V20 HRD FX1 FX2 FX3 - SAP System - OS AB DB_IMPORT Migration exec | Implementation In Progress | 05.07.2022 13:56:18 | 08.07.2022 13:56:18 | TAS000006518807,TAS000006519303,TAS000006570731,TAS000006580549,TAS000006593458,TAS000006596854,TAS000006643296,TAS000006643531,TAS000006767410,TAS000006768383,TAS000006768835 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 16.12.2022 19:00:00 | 16.12.2022 23:00:00 | os-unix-std-06:global:2nd | Alok Pai (EXT)
CRQ000002141201 | STARD: SND CS migration - implementation-SAP OS AB DB_IMPORT Migration exec | Implementation In Progress | 12.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006764688 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 16.12.2022 10:00:00 | 16.12.2022 14:00:00 | os-linux-std-06:global:2nd | Prodyut Paul (EXT)
CRQ000002120037 | *MR+Veritas* *ESP* lp34d53/54 install Masterrelease | Scheduled | 17.12.2022 22:00:00 | 18.12.2022 05:00:00 | TAS000006716745 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 17.12.2022 22:00:00 | 18.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002120065 | *SLES12 SP5* *ESP* *lp34d51/52* upgrade to the new Version of SuSE SLES12 SP5 | Scheduled | 18.12.2022 20:00:00 | 19.12.2022 03:00:00 | TAS000006716797 | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Cluster) | Pending | Assignment | 18.12.2022 20:00:00 | 19.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002124204 | STARD: TGQ CS migration + DI replacement - implementation | Scheduled | 04.12.2022 05:00:00 | 16.12.2022 18:00:00 | TAS000006725801,TAS000006725812 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 22.12.2022 09:00:00 | 22.12.2022 13:00:00 | os-linux-std-06:global:2nd | Ashwini Tendulkar (EXT)
CRQ000002124612 | MR Update on SolMan servers-lpssm09, lpssm10 | Implementation In Progress | 25.11.2022 05:30:00 | 31.01.2023 18:30:00 | TAS000006758222 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 17.12.2022 10:00:00 | 17.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002125016 | STARD: TXD CS migration + DI replacement - implementation | Scheduled | 18.12.2022 05:00:00 | 30.12.2022 18:00:00 | TAS000006727212,TAS000006728523 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 18.12.2022 09:00:00 | 18.12.2022 13:00:00 | os-linux-std-06:global:2nd | Tushar Lohia (EXT)
CRQ000002127216 | Planned Power shutdown 16.47 Miramas - UPS Replacement | Scheduled | 19.12.2022 06:00:00 | 21.12.2022 19:30:00 | TAS000006746565 | server-win:emea¦Shutdown_Server_Unix | Pending | Assignment | 19.12.2022 08:30:00 | 21.12.2022 17:30:00 | os-unix-std-06:global:2nd
CRQ000002127753 | *MR+VERITAS* *ESP* lpkrd07/08 install Masterrelease | Scheduled For Approval | 17.12.2022 16:00:00 | 17.12.2022 23:00:00 | TAS000006735046 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Staged | Staging in Progress | 17.12.2022 16:30:00 | 17.12.2022 22:30:00 | os-unix-std-06:global:2nd
CRQ000002128060 | *MR+VERITAS* *ESP* lpkrd04/05 install Masterrelease | Scheduled For Approval | 17.12.2022 16:30:00 | 17.12.2022 23:00:00 | TAS000006735035 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Staged | Staging in Progress | 17.12.2022 16:30:00 | 17.12.2022 22:30:00 | os-unix-std-06:global:2nd
CRQ000002132514 | *MR+Veritas* *GMA* lpdbs115/116 install Masterrelease | Scheduled | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | TAS000006744297 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002134463 | IPS-I-P34-PROD - Update Masterrelease | Scheduled | 17.12.2022 19:00:00 | 18.12.2022 06:00:00 | TAS000006750323,TAS000006750324,TAS000006750325,TAS000006750326,TAS000006750327,TAS000006750328 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 17.12.2022 19:30:00 | 17.12.2022 21:30:00 | os-unix-std-06:global:2nd
CRQ000002135229 | SAN GS 3: SAN_MICROCODE_UPDATE GMA3S1 (BGs) | Scheduled | 19.12.2022 08:00:00 | 19.12.2022 16:00:00 | TAS000006750593 | NTT Unix: SAN GS 3: SAN_MICROCODE_UPDATE GMA3S1 (BGs) | Pending | Assignment | 19.12.2022 08:00:00 | 19.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002135781 | SAN GS 3: SAN_MICROCODE_UPDATE GMA311 (BGs) | Scheduled | 20.12.2022 08:00:00 | 20.12.2022 16:00:00 | TAS000006754377 | NTT Unix: SAN GS 3: SAN_MICROCODE_UPDATE GMA311 (BGs) | Pending | Assignment | 20.12.2022 08:00:00 | 20.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002136172 | SAN GS 3: SAN_MICROCODE_UPDATE GMA312 (BGs) | Scheduled | 21.12.2022 08:00:00 | 21.12.2022 16:00:00 | TAS000006754406 | NTT Unix: SAN GS 3: SAN_MICROCODE_UPDATE GMA312 (BGs) | Pending | Assignment | 21.12.2022 08:00:00 | 21.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002136178 | SAN GS 3: SAN_MICROCODE_UPDATE GMA313 (BGs) | Scheduled | 22.12.2022 08:00:00 | 22.12.2022 16:00:00 | TAS000006754663 | NTT Unix: SAN GS 3: SAN_MICROCODE_UPDATE GMA313 (BGs) | Pending | Assignment | 22.12.2022 08:00:00 | 22.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002136190 | SAN #Data: SAN_MICROCODE_UPDATE AAR401 / BRE401 | Scheduled | 18.12.2022 08:00:00 | 18.12.2022 16:00:00 | TAS000006755447 | NTT Unix: SAN #Data: SAN_MICROCODE_UPDATE AAR401 / BRE401 | Pending | Assignment | 18.12.2022 08:00:00 | 18.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002137234 | *PKG-MOVE* *GSP* MOVE package from lp02d55/56 to lp02db005/006 | Scheduled For Approval | 22.12.2022 11:00:00 | 08.01.2023 23:00:00 | TAS000006756791 | server-unix-std:global¦06¦022c-cluster-prepare-migrate-package | Staged | Staging in Progress | 22.12.2022 11:00:00 | 25.12.2022 23:00:00 | os-unix-std-06:global:2nd
CRQ000002137598 | *MR+Veritas* *GMA* lpdbs117/118 install Masterrelease | Scheduled | 18.12.2022 01:00:00 | 18.12.2022 08:00:00 | TAS000006757790 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 18.12.2022 01:00:00 | 18.12.2022 07:00:00 | os-unix-std-06:global:2nd
CRQ000002137992 | *MR+Veritas* *GMA* install Masterrelease-lpdbvdm07_lpdbvdm08 | Scheduled | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | TAS000006758400,TAS000006766509 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002139407 | *PKG-MOVE* *GSP* MOVE packages from lp02d53/54 to lp02db003/004 | Scheduled For Approval | 22.12.2022 18:00:00 | 04.01.2023 19:00:00 | TAS000006761565 | server-unix-std:global¦06¦022c-cluster-prepare-migrate-package | Staged | Staging in Progress | 22.12.2022 18:00:00 | 25.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778216,TAS000006778217,TAS000006778218,TAS000006778219,TAS000006778656,TAS000006778943,TAS000006778944,TAS000006778945,TAS000006778220 | server-unix-std:global¦06¦085c-move-farm-exec | Assigned |  | 17.12.2022 00:00:00 | 17.12.2022 04:00:00 | os-unix-std-06:global:2nd | KumaraSwamy Nasika (EXT)
CRQ000002144834 | #PROD - Informatica NA migration from Xen to VMWare Status | Implementation In Progress | 16.12.2022 18:30:00 | 18.12.2022 22:30:00 | TAS000006774976,TAS000006774975 | server-unix-std:global¦06¦070c-modify-system | Staged | Staging in Progress | 16.12.2022 23:30:00 | 18.12.2022 23:30:00 | os-unix-std-06:global:2nd
CRQ000002146600 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp07dbipsq001/002 | Scheduled For Approval | 22.12.2022 08:00:00 | 22.12.2022 15:00:00 | TAS000006780788,TAS000006780790 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 14:00:00 | os-unix-std-06:global:2nd
CRQ000002148411 | Host: lplogstash1vm.bmwgroup.net Service-BTRFS Balance | Planning In Progress |  |  | TAS000006783769 | BTRFS Balance | Staged | Staging in Progress | 17.12.2022 22:30:00 | 18.12.2022 02:30:00 | os-unix-std-06:global:2nd
CRQ000002150029 | #Migration Linux VM #Global#Downtime#2h#CCM_HR PROD | Scheduled | 16.12.2022 23:00:00 | 18.12.2022 22:00:00 | TAS000006787655 | server-unix-std:global¦06¦050c-network-mgmt | Assigned |  | 17.12.2022 13:00:00 | 17.12.2022 15:00:00 | os-linux-std-06:global:2nd | Kishore Kumar (EXT)
CRQ000002150106 | *PKG-MOVE* *GSP* MOVE package dbprof50 from lp07db003/004 to lp07db001/002 | Scheduled For Approval | 15.12.2022 12:00:00 | 27.12.2022 23:00:00 | TAS000006786884,TAS000006786885,TAS000006786886 | server-unix-std:global¦06¦022c-cluster-prepare-migrate-package | Staged | Staging in Progress | 15.12.2022 12:00:00 | 18.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002151602 | Critical BTRFS Balancing (lpszmq01vm) | Scheduled | 18.12.2022 01:00:00 | 18.12.2022 03:00:00 | TAS000006789858 | Critical BTRFS Balancing (lpszmq01vm) | Pending | Assignment | 18.12.2022 01:00:00 | 18.12.2022 03:00:00 | os-unix-std-06:global:2nd
CRQ000002151877 | *PKG-MOVE* *GMA* MOVE package plfasi01 from lpdbfips01/02 to lpdbfips001/002. | Implementation In Progress | 13.12.2022 19:00:00 | 26.12.2022 23:00:00 | TAS000006792367,TAS000006792368 | server-unix-std:global¦06¦023c-cluster-migrate-package | Pending | Assignment | 17.12.2022 08:00:00 | 17.12.2022 11:00:00 | os-unix-std-06:global:2nd

## MasterSheet-3
CRQ Number | CRQ Description | CRQ Status | CRQ Start Date | CRQ End Date | Linux Tasks in CRQ | Task Description | Task Status | Task Status 1 | Task Start Date | Task End Date | Xen/VMWare | Assignee
CRQ000002035384,CRQ000002036566,CRQ000002056956,CRQ000002061326,CRQ000002066916,CRQ000002068054,CRQ000002088573,CRQ000002088579,CRQ000002101623,CRQ000002101633,CRQ000002101659 | GTZ GUI WYT MGT BRD RWI V20 HRD FX1 FX2 FX3 - SAP System - OS AB DB_IMPORT Migration exec | Implementation In Progress | 05.07.2022 13:56:18 | 08.07.2022 13:56:18 | TAS000006518807,TAS000006519303,TAS000006570731,TAS000006580549,TAS000006593458,TAS000006596854,TAS000006643296,TAS000006643531,TAS000006767410,TAS000006768383,TAS000006768835 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 16.12.2022 19:00:00 | 16.12.2022 23:00:00 | os-unix-std-06:global:2nd | Alok Pai (EXT)
CRQ000002141201 | STARD: SND CS migration - implementation-SAP OS AB DB_IMPORT Migration exec | Implementation In Progress | 12.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006764688 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 16.12.2022 10:00:00 | 16.12.2022 14:00:00 | os-linux-std-06:global:2nd | Prodyut Paul (EXT)
CRQ000002124204 | STARD: TGQ CS migration + DI replacement - implementation--SAP OS AB DB_IMPORT Migration exec | Scheduled | 04.12.2022 05:00:00 | 16.12.2022 18:00:00 | TAS000006725801,TAS000006725812 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 22.12.2022 09:00:00 | 22.12.2022 13:00:00 | os-linux-std-06:global:2nd | Ashwini Tendulkar (EXT)
CRQ000002125016 | STARD: TXD CS migration + DI replacement - implementation | Scheduled | 18.12.2022 05:00:00 | 30.12.2022 18:00:00 | TAS000006727212,TAS000006728523 | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | Assigned |  | 18.12.2022 09:00:00 | 18.12.2022 13:00:00 | os-linux-std-06:global:2nd | Tushar Lohia (EXT)
CRQ000002120037 | *MR+Veritas* *ESP* lp34d53/54 install Masterrelease | Scheduled | 17.12.2022 22:00:00 | 18.12.2022 05:00:00 | TAS000006716745 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 17.12.2022 22:00:00 | 18.12.2022 04:00:00 | os-unix-std-06:global:2nd
CRQ000002120065 | *SLES12 SP5* *ESP* *lp34d51/52* upgrade to the new Version of SuSE SLES12 SP5 | Scheduled | 18.12.2022 20:00:00 | 19.12.2022 03:00:00 | TAS000006716797 | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Cluster) | Pending | Assignment | 18.12.2022 20:00:00 | 19.12.2022 02:00:00 | os-unix-std-06:global:2nd
CRQ000002124612 | MR Update on SolMan servers-lpssm09, lpssm10 | Implementation In Progress | 25.11.2022 05:30:00 | 31.01.2023 18:30:00 | TAS000006758222 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 17.12.2022 10:00:00 | 17.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002127753 | *MR+VERITAS* *ESP* lpkrd07/08 install Masterrelease | Scheduled For Approval | 17.12.2022 16:00:00 | 17.12.2022 23:00:00 | TAS000006735046 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Staged | Staging in Progress | 17.12.2022 16:30:00 | 17.12.2022 22:30:00 | os-unix-std-06:global:2nd
CRQ000002128060 | *MR+VERITAS* *ESP* lpkrd04/05 install Masterrelease | Scheduled For Approval | 17.12.2022 16:30:00 | 17.12.2022 23:00:00 | TAS000006735035 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Staged | Staging in Progress | 17.12.2022 16:30:00 | 17.12.2022 22:30:00 | os-unix-std-06:global:2nd
CRQ000002132514 | *MR+Veritas* *GMA* lpdbs115/116 install Masterrelease | Scheduled | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | TAS000006744297 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002137234 | *PKG-MOVE* *GSP* MOVE package from lp02d55/56 to lp02db005/006 | Scheduled For Approval | 22.12.2022 11:00:00 | 08.01.2023 23:00:00 | TAS000006756791 | server-unix-std:global¦06¦022c-cluster-prepare-migrate-package | Staged | Staging in Progress | 22.12.2022 11:00:00 | 25.12.2022 23:00:00 | os-unix-std-06:global:2nd
CRQ000002137598 | *MR+Veritas* *GMA* lpdbs117/118 install Masterrelease | Scheduled | 18.12.2022 01:00:00 | 18.12.2022 08:00:00 | TAS000006757790 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 18.12.2022 01:00:00 | 18.12.2022 07:00:00 | os-unix-std-06:global:2nd
CRQ000002137992 | *MR+Veritas* *GMA* install Masterrelease-lpdbvdm07_lpdbvdm08 | Scheduled | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | TAS000006758400,TAS000006766509 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002139407 | *PKG-MOVE* *GSP* MOVE packages from lp02d53/54 to lp02db003/004 | Scheduled For Approval | 22.12.2022 18:00:00 | 04.01.2023 19:00:00 | TAS000006761565 | server-unix-std:global¦06¦022c-cluster-prepare-migrate-package | Staged | Staging in Progress | 22.12.2022 18:00:00 | 25.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002150106 | *PKG-MOVE* *GSP* MOVE package dbprof50 from lp07db003/004 to lp07db001/002 | Scheduled For Approval | 15.12.2022 12:00:00 | 27.12.2022 23:00:00 | TAS000006786884,TAS000006786885,TAS000006786886 | server-unix-std:global¦06¦022c-cluster-prepare-migrate-package | Staged | Staging in Progress | 15.12.2022 12:00:00 | 18.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002151877 | *PKG-MOVE* *GMA* MOVE package plfasi01 from lpdbfips01/02 to lpdbfips001/002. | Implementation In Progress | 13.12.2022 19:00:00 | 26.12.2022 23:00:00 | TAS000006792367,TAS000006792368 | server-unix-std:global¦06¦023c-cluster-migrate-package | Pending | Assignment | 17.12.2022 08:00:00 | 17.12.2022 11:00:00 | os-unix-std-06:global:2nd
CRQ000002146600 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp07dbipsq001/002 | Scheduled For Approval | 22.12.2022 08:00:00 | 22.12.2022 15:00:00 | TAS000006780788,TAS000006780790 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 14:00:00 | os-unix-std-06:global:2nd
CRQ000002134463 | IPS-I-P34-PROD - Update Masterrelease | Scheduled | 17.12.2022 19:00:00 | 18.12.2022 06:00:00 | TAS000006750323,TAS000006750324,TAS000006750325,TAS000006750326,TAS000006750327,TAS000006750328 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 17.12.2022 19:30:00 | 17.12.2022 21:30:00 | os-unix-std-06:global:2nd
CRQ000002142425 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002 | Implementation In Progress | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | TAS000006778216,TAS000006778217,TAS000006778218,TAS000006778219,TAS000006778656,TAS000006778943,TAS000006778944,TAS000006778945,TAS000006778220 | server-unix-std:global¦06¦085c-move-farm-exec | Assigned |  | 17.12.2022 00:00:00 | 17.12.2022 04:00:00 | os-unix-std-06:global:2nd | KumaraSwamy Nasika (EXT)
CRQ000002144834 | #PROD - Informatica NA migration from Xen to VMWare Status | Implementation In Progress | 16.12.2022 18:30:00 | 18.12.2022 22:30:00 | TAS000006774976,TAS000006774975 | server-unix-std:global¦06¦070c-modify-system | Staged | Staging in Progress | 16.12.2022 23:30:00 | 18.12.2022 23:30:00 | os-unix-std-06:global:2nd
CRQ000002148411 | Host: lplogstash1vm.bmwgroup.net Service-BTRFS Balance | Planning In Progress |  |  | TAS000006783769 | BTRFS Balance | Staged | Staging in Progress | 17.12.2022 22:30:00 | 18.12.2022 02:30:00 | os-unix-std-06:global:2nd
CRQ000002151602 | Critical BTRFS Balancing (lpszmq01vm) | Scheduled | 18.12.2022 01:00:00 | 18.12.2022 03:00:00 | TAS000006789858 | Critical BTRFS Balancing (lpszmq01vm) | Pending | Assignment | 18.12.2022 01:00:00 | 18.12.2022 03:00:00 | os-unix-std-06:global:2nd
CRQ000002150029 | #Migration Linux VM #Global#Downtime#2h#CCM_HR PROD | Scheduled | 16.12.2022 23:00:00 | 18.12.2022 22:00:00 | TAS000006787655 | server-unix-std:global¦06¦050c-network-mgmt | Assigned |  | 17.12.2022 13:00:00 | 17.12.2022 15:00:00 | os-linux-std-06:global:2nd | Kishore Kumar (EXT)
CRQ000002126431,CRQ000002127032,CRQ000002127117,CRQ000002127120,CRQ000002144399,CRQ000002144927,CRQ000002145308,CRQ000002145522 | Colo Group Project Moving server <lpsbdbs012> <lpdbs132> <lpdbs136> <lpdbs138> <lpdbs140> <lpdbs130> <lpsbdbs014> <lpsbdbs016> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006730898,TAS000006730901,TAS000006730905,TAS000006731384,TAS000006732018,TAS000006732260,TAS000006774915,TAS000006774918,TAS000006775722,TAS000006775255,TAS000006775258,TAS000006775262,TAS000006775315,TAS000006775318,TAS000006775822,TAS000006776778 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Pending | Assignment | 19.12.2022 08:00:00 | 19.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002147075,CRQ000002147179,CRQ000002147182,CRQ000002147303,CRQ000002147712,CRQ000002126580,CRQ000002127315,CRQ000002127317,CRQ000002127319 | Colo Group Project Moving server <lpdbs150><lpdbs144><lpdbs146><lpdbs142><lpdbs148><lpdbs133><lpdbs131><lpdbs135><lpdbs137> to new location | Implementation In Progress | 08.12.2022 09:00:00 | 31.01.2023 18:00:00 | TAS000006782835,TAS000006781574,TAS000006781598,TAS000006780687,TAS000006782381,TAS000006731394,TAS000006731817,TAS000006732238,TAS000006732242,TAS000006732336,TAS000006732340 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Staged | Staging in Progress | 22.12.2022 08:00:00 | 22.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002135229,CRQ000002135781,CRQ000002136172,CRQ000002136178,CRQ000002136190 | SAN GS 3: SAN_MICROCODE_UPDATE GMA3S1,GMA311,GMA312,GMA313 (BGs),AAR401 / BRE401 | Scheduled | 19.12.2022 08:00:00 | 19.12.2022 16:00:00 | TAS000006750593,TAS000006754377,TAS000006754406,TAS000006754663,TAS000006755447 | NTT Unix: SAN GS 3: SAN_MICROCODE_UPDATE GMA3S1 (BGs) | Pending | Assignment | 19.12.2022 08:00:00 | 19.12.2022 16:00:00 | os-unix-std-06:global:2nd
CRQ000002127216 | Planned Power shutdown 16.47 Miramas - UPS Replacement | Scheduled | 19.12.2022 06:00:00 | 21.12.2022 19:30:00 | TAS000006746565 | server-win:emea¦Shutdown_Server_Unix | Pending | Assignment | 19.12.2022 08:30:00 | 21.12.2022 17:30:00 | os-unix-std-06:global:2nd

## LastButOne
CRQ Number | Linux Tasks in CRQ | CRQ Start Date | CRQ End Date | CRQ Description, Additional Information
CRQ000002035384,CRQ000002036566,CRQ000002056956,CRQ000002061326,CRQ000002066916,CRQ000002068054,CRQ000002088573,CRQ000002088579,CRQ000002101623,CRQ000002101633,CRQ000002101659 | TAS000006518807,TAS000006519303,TAS000006570731,TAS000006580549,TAS000006593458,TAS000006596854,TAS000006643296,TAS000006643531,TAS000006767410,TAS000006768383,TAS000006768835 | 05.07.2022 13:56:18 | 08.07.2022 13:56:18 | GTZ GUI WYT MGT BRD RWI V20 HRD FX1 FX2 FX3 - SAP System - OS AB DB_IMPORT Migration exec
CRQ000002141201 | TAS000006764688 | 12.12.2022 08:00:00 | 30.12.2022 18:00:00 | STARD: SND CS migration - implementation-SAP OS AB DB_IMPORT Migration exec
CRQ000002124204 | TAS000006725801,TAS000006725812 | 04.12.2022 05:00:00 | 16.12.2022 18:00:00 | STARD: TGQ CS migration + DI replacement - implementation--SAP OS AB DB_IMPORT Migration exec
CRQ000002125016 | TAS000006727212,TAS000006728523 | 18.12.2022 05:00:00 | 30.12.2022 18:00:00 | STARD: TXD CS migration + DI replacement - implementation
CRQ000002120037 | TAS000006716745 | 17.12.2022 22:00:00 | 18.12.2022 05:00:00 | *MR+Veritas* *ESP* lp34d53/54 install Masterrelease
CRQ000002120065 | TAS000006716797 | 18.12.2022 20:00:00 | 19.12.2022 03:00:00 | *SLES12 SP5* *ESP* *lp34d51/52* upgrade to the new Version of SuSE SLES12 SP5
CRQ000002124612 | TAS000006758222 | 25.11.2022 05:30:00 | 31.01.2023 18:30:00 | MR Update on SolMan servers-lpssm09, lpssm10
CRQ000002127753 | TAS000006735046 | 17.12.2022 16:00:00 | 17.12.2022 23:00:00 | *MR+VERITAS* *ESP* lpkrd07/08 install Masterrelease
CRQ000002128060 | TAS000006735035 | 17.12.2022 16:30:00 | 17.12.2022 23:00:00 | *MR+VERITAS* *ESP* lpkrd04/05 install Masterrelease
CRQ000002132514 | TAS000006744297 | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | *MR+Veritas* *GMA* lpdbs115/116 install Masterrelease
CRQ000002137234 | TAS000006756791 | 22.12.2022 11:00:00 | 08.01.2023 23:00:00 | *PKG-MOVE* *GSP* MOVE package from lp02d55/56 to lp02db005/006
CRQ000002137598 | TAS000006757790 | 18.12.2022 01:00:00 | 18.12.2022 08:00:00 | *MR+Veritas* *GMA* lpdbs117/118 install Masterrelease
CRQ000002137992 | TAS000006758400,TAS000006766509 | 18.12.2022 06:00:00 | 18.12.2022 12:00:00 | *MR+Veritas* *GMA* install Masterrelease-lpdbvdm07_lpdbvdm08
CRQ000002139407 | TAS000006761565 | 22.12.2022 18:00:00 | 04.01.2023 19:00:00 | *PKG-MOVE* *GSP* MOVE packages from lp02d53/54 to lp02db003/004
CRQ000002150106 | TAS000006786884,TAS000006786885,TAS000006786886 | 15.12.2022 12:00:00 | 27.12.2022 23:00:00 | *PKG-MOVE* *GSP* MOVE package dbprof50 from lp07db003/004 to lp07db001/002
CRQ000002151877 | TAS000006792367,TAS000006792368 | 13.12.2022 19:00:00 | 26.12.2022 23:00:00 | *PKG-MOVE* *GMA* MOVE package plfasi01 from lpdbfips01/02 to lpdbfips001/002.
CRQ000002146600 | TAS000006780788,TAS000006780790 | 22.12.2022 08:00:00 | 22.12.2022 15:00:00 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp07dbipsq001/002
CRQ000002134463 | TAS000006750323,TAS000006750324,TAS000006750325,TAS000006750326,TAS000006750327,TAS000006750328 | 17.12.2022 19:00:00 | 18.12.2022 06:00:00 | IPS-I-P34-PROD - Update Masterrelease
CRQ000002142425 | TAS000006778216,TAS000006778217,TAS000006778218,TAS000006778219,TAS000006778656,TAS000006778943,TAS000006778944,TAS000006778945,TAS000006778220 | 12.12.2022 09:00:00 | 26.12.2022 09:00:00 | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002
CRQ000002144834 | TAS000006774976,TAS000006774975 | 16.12.2022 18:30:00 | 18.12.2022 22:30:00 | #PROD - Informatica NA migration from Xen to VMWare Status
CRQ000002151602 | TAS000006789858 | 18.12.2022 01:00:00 | 18.12.2022 03:00:00 | Critical BTRFS Balancing (lpszmq01vm)
CRQ000002150029 | TAS000006787655 | 16.12.2022 23:00:00 | 18.12.2022 22:00:00 | #Migration Linux VM #Global#Downtime#2h#CCM_HR PROD
CRQ000002126431,CRQ000002127032,CRQ000002127117,CRQ000002127120,CRQ000002144399,CRQ000002144927,CRQ000002145308,CRQ000002145522 | TAS000006730898,TAS000006730901,TAS000006730905,TAS000006731384,TAS000006732018,TAS000006732260,TAS000006774915,TAS000006774918,TAS000006775722,TAS000006775255,TAS000006775258,TAS000006775262,TAS000006775315,TAS000006775318,TAS000006775822,TAS000006776778 | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | Colo Group Project Moving server <lpsbdbs012> <lpdbs132> <lpdbs136> <lpdbs138> <lpdbs140> <lpdbs130> <lpsbdbs014> <lpsbdbs016> ONLY SAN Migration (No physical Move of server)
CRQ000002147075,CRQ000002147179,CRQ000002147182,CRQ000002147303,CRQ000002147712,CRQ000002126580,CRQ000002127315,CRQ000002127317,CRQ000002127319 | TAS000006782835,TAS000006781574,TAS000006781598,TAS000006780687,TAS000006782381,TAS000006731394,TAS000006731817,TAS000006732238,TAS000006732242,TAS000006732336,TAS000006732340 | 08.12.2022 09:00:00 | 31.01.2023 18:00:00 | Colo Group Project Moving server <lpdbs150><lpdbs144><lpdbs146><lpdbs142><lpdbs148><lpdbs133><lpdbs131><lpdbs135><lpdbs137> to new location
CRQ000002135229,CRQ000002135781,CRQ000002136172,CRQ000002136178,CRQ000002136190 | TAS000006750593,TAS000006754377,TAS000006754406,TAS000006754663,TAS000006755447 | 19.12.2022 08:00:00 | 19.12.2022 16:00:00 | SAN GS 3: SAN_MICROCODE_UPDATE GMA3S1,GMA311,GMA312,GMA313 (BGs),AAR401 / BRE401
CRQ000002127216 | TAS000006746565 | 19.12.2022 06:00:00 | 21.12.2022 19:30:00 | Planned Power shutdown 16.47 Miramas - UPS Replacement

## Final
CRQ Number | Linux Tasks in CRQ | CRQ Start Date | CRQ End Date | CRQ Description, Additional Information
CRQ000002035384,CRQ000002036566,CRQ000002056956,CRQ000002061326,CRQ000002066916,CRQ000002068054,CRQ000002088573,CRQ000002088579,CRQ000002101623,CRQ000002101633,CRQ000002101659 | TAS000006518807,TAS000006519303,TAS000006570731,TAS000006580549,TAS000006593458,TAS000006596854,TAS000006643296,TAS000006643531,TAS000006767410,TAS000006768383,TAS000006768835 | 05-Jul-22,Tuesday, 1:56:18 PM | 08-Jul-22,Friday, 1:56:18 PM | GTZ GUI WYT MGT BRD RWI V20 HRD FX1 FX2 FX3 - SAP System - OS AB DB_IMPORT Migration exec
CRQ000002141201 | TAS000006764688 | 12-Dec-22,Monday, 8:00:00 AM | 30-Dec-22,Friday, 6:00:00 PM | STARD: SND CS migration - implementation-SAP OS AB DB_IMPORT Migration exec
CRQ000002124204 | TAS000006725801,TAS000006725812 | 04-Dec-22,Sunday, 5:00:00 AM | 16-Dec-22,Friday, 6:00:00 PM | STARD: TGQ CS migration + DI replacement - implementation--SAP OS AB DB_IMPORT Migration exec
CRQ000002125016 | TAS000006727212,TAS000006728523 | 18-Dec-22,Sunday, 5:00:00 AM | 30-Dec-22,Friday, 6:00:00 PM | STARD: TXD CS migration + DI replacement - implementation
CRQ000002120037 | TAS000006716745 | 17-Dec-22,Saturday, 10:00:00 PM | 18-Dec-22,Sunday, 5:00:00 AM | *MR+Veritas* *ESP* lp34d53/54 install Masterrelease
CRQ000002120065 | TAS000006716797 | 18-Dec-22,Sunday, 8:00:00 PM | 19-Dec-22,Monday, 3:00:00 AM | *SLES12 SP5* *ESP* *lp34d51/52* upgrade to the new Version of SuSE SLES12 SP5
CRQ000002124612 | TAS000006758222 | 25-Nov-22,Friday, 5:30:00 AM | 31-Jan-23,Tuesday, 6:30:00 PM | MR Update on SolMan servers-lpssm09, lpssm10
CRQ000002127753 | TAS000006735046 | 17-Dec-22,Saturday, 4:00:00 PM | 17-Dec-22,Saturday, 11:00:00 PM | *MR+VERITAS* *ESP* lpkrd07/08 install Masterrelease
CRQ000002128060 | TAS000006735035 | 17-Dec-22,Saturday, 4:30:00 PM | 17-Dec-22,Saturday, 11:00:00 PM | *MR+VERITAS* *ESP* lpkrd04/05 install Masterrelease
CRQ000002132514 | TAS000006744297 | 18-Dec-22,Sunday, 6:00:00 AM | 18-Dec-22,Sunday, 12:00:00 PM | *MR+Veritas* *GMA* lpdbs115/116 install Masterrelease
CRQ000002137234 | TAS000006756791 | 22-Dec-22,Thursday, 11:00:00 AM | 08-Jan-23,Sunday, 11:00:00 PM | *PKG-MOVE* *GSP* MOVE package from lp02d55/56 to lp02db005/006
CRQ000002137598 | TAS000006757790 | 18-Dec-22,Sunday, 1:00:00 AM | 18-Dec-22,Sunday, 8:00:00 AM | *MR+Veritas* *GMA* lpdbs117/118 install Masterrelease
CRQ000002137992 | TAS000006758400,TAS000006766509 | 18-Dec-22,Sunday, 6:00:00 AM | 18-Dec-22,Sunday, 12:00:00 PM | *MR+Veritas* *GMA* install Masterrelease-lpdbvdm07_lpdbvdm08
CRQ000002139407 | TAS000006761565 | 22-Dec-22,Thursday, 6:00:00 PM | 04-Jan-23,Wednesday, 7:00:00 PM | *PKG-MOVE* *GSP* MOVE packages from lp02d53/54 to lp02db003/004
CRQ000002150106 | TAS000006786884,TAS000006786885,TAS000006786886 | 15-Dec-22,Thursday, 12:00:00 PM | 27-Dec-22,Tuesday, 11:00:00 PM | *PKG-MOVE* *GSP* MOVE package dbprof50 from lp07db003/004 to lp07db001/002
CRQ000002151877 | TAS000006792367,TAS000006792368 | 13-Dec-22,Tuesday, 7:00:00 PM | 26-Dec-22,Monday, 11:00:00 PM | *PKG-MOVE* *GMA* MOVE package plfasi01 from lpdbfips01/02 to lpdbfips001/002.
CRQ000002146600 | TAS000006780788,TAS000006780790 | 22-Dec-22,Thursday, 8:00:00 AM | 22-Dec-22,Thursday, 3:00:00 PM | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp07dbipsq001/002
CRQ000002134463 | TAS000006750323,TAS000006750324,TAS000006750325,TAS000006750326,TAS000006750327,TAS000006750328 | 17-Dec-22,Saturday, 7:00:00 PM | 18-Dec-22,Sunday, 6:00:00 AM | IPS-I-P34-PROD - Update Masterrelease
CRQ000002142425 | TAS000006778216,TAS000006778217,TAS000006778218,TAS000006778219,TAS000006778656,TAS000006778943,TAS000006778944,TAS000006778945,TAS000006778220 | 12-Dec-22,Monday, 9:00:00 AM | 26-Dec-22,Monday, 9:00:00 AM | Farm replacement - Source Farm lpxenmq11/12 to Target Host lpsbxenfind001/002
CRQ000002144834 | TAS000006774976,TAS000006774975 | 16-Dec-22,Friday, 6:30:00 PM | 18-Dec-22,Sunday, 10:30:00 PM | #PROD - Informatica NA migration from Xen to VMWare Status
CRQ000002151602 | TAS000006789858 | 18-Dec-22,Sunday, 1:00:00 AM | 18-Dec-22,Sunday, 3:00:00 AM | Critical BTRFS Balancing (lpszmq01vm)
CRQ000002150029 | TAS000006787655 | 16-Dec-22,Friday, 11:00:00 PM | 18-Dec-22,Sunday, 10:00:00 PM | #Migration Linux VM #Global#Downtime#2h#CCM_HR PROD
CRQ000002126431,CRQ000002127032,CRQ000002127117,CRQ000002127120,CRQ000002144399,CRQ000002144927,CRQ000002145308,CRQ000002145522 | TAS000006730898,TAS000006730901,TAS000006730905,TAS000006731384,TAS000006732018,TAS000006732260,TAS000006774915,TAS000006774918,TAS000006775722,TAS000006775255,TAS000006775258,TAS000006775262,TAS000006775315,TAS000006775318,TAS000006775822,TAS000006776778 | 05-Dec-22,Monday, 8:00:00 AM | 31-Jan-23,Tuesday, 6:00:00 PM | Colo Group Project Moving server <lpsbdbs012> <lpdbs132> <lpdbs136> <lpdbs138> <lpdbs140> <lpdbs130> <lpsbdbs014> <lpsbdbs016> ONLY SAN Migration (No physical Move of server)
CRQ000002147075,CRQ000002147179,CRQ000002147182,CRQ000002147303,CRQ000002147712,CRQ000002126580,CRQ000002127315,CRQ000002127317,CRQ000002127319 | TAS000006782835,TAS000006781574,TAS000006781598,TAS000006780687,TAS000006782381,TAS000006731394,TAS000006731817,TAS000006732238,TAS000006732242,TAS000006732336,TAS000006732340 | 08-Dec-22,Thursday, 9:00:00 AM | 31-Jan-23,Tuesday, 6:00:00 PM | Colo Group Project Moving server <lpdbs150><lpdbs144><lpdbs146><lpdbs142><lpdbs148><lpdbs133><lpdbs131><lpdbs135><lpdbs137> to new location
CRQ000002135229,CRQ000002135781,CRQ000002136172,CRQ000002136178,CRQ000002136190 | TAS000006750593,TAS000006754377,TAS000006754406,TAS000006754663,TAS000006755447 | 19-Dec-22,Monday, 8:00:00 AM | 19-Dec-22,Monday, 4:00:00 PM | SAN GS 3: SAN_MICROCODE_UPDATE GMA3S1,GMA311,GMA312,GMA313 (BGs),AAR401 / BRE401
CRQ000002127216 | TAS000006746565 | 19-Dec-22,Monday, 6:00:00 AM | 21-Dec-22,Wednesday, 7:30:00 PM | Planned Power shutdown 16.47 Miramas - UPS Replacement