## MasterSheet
CRQ Number | CRQ Description | CRQ Status | CRQ Start Date | CRQ End Date | Linux Tasks in CRQ | Task Description | Task Status | Task Status 1 | Task Start Date | Task End Date | Xen/VMWare | Assignee
CRQ000002145059 | $1 "Colo Group Project" Moving server <lpdbs141> to new location | Implementation In Progress | 06.12.2022 03:30:00 | 31.01.2023 13:30:00 | TAS000006776763 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Assigned |  | 29.12.2022 08:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002146003 | $1 "Colo Group Project" Moving server <lpdbs147> to new location | Implementation In Progress | 06.12.2022 08:00:00 | 28.02.2023 18:00:00 | TAS000006777840 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Assigned |  | 29.12.2022 08:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Rajendra Bhandari (EXT)
CRQ000002144896 | #SK Decom <lp10dkpga0052vm>VM | Implementation In Progress | 05.12.2022 08:00:00 | 04.01.2023 18:00:00 | TAS000006776119 | Return/Change SAN-Storage | Assigned |  | 29.12.2022 08:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Chimaladinne Ramesh (EXT)
CRQ000002145911 | $1 "Colo Group Project" Moving server <lpdbs145> to new location | Implementation In Progress | 06.12.2022 08:00:00 | 28.02.2023 18:00:00 | TAS000006776407 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Assigned |  | 29.12.2022 08:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002145078 | #SK Decom <lp10dkpga0044vm>VM | Implementation In Progress | 05.12.2022 08:00:00 | 04.01.2023 18:00:00 | TAS000006776983 | Return/Change SAN-Storage | Assigned |  | 29.12.2022 08:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Saeed Mansoorie (EXT)
CRQ000002153820 | #SK Decom<lp19dkpgb0061vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 04.01.2023 18:00:00 | TAS000006797196 | Return/Change SAN-Storage | Assigned |  | 29.12.2022 08:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Paras Chhabra (EXT)
CRQ000002153943 | #SK Decom<lpdkalas05vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 04.01.2023 18:00:00 | TAS000006798275 | Return/Change SAN-Storage | Assigned |  | 29.12.2022 08:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | VinodKumar Uppara (EXT)
CRQ000002153784 | #SK Decom<lppcmdbvirscan01>VM | Implementation In Progress | 15.12.2022 08:00:00 | 04.01.2023 18:00:00 | TAS000006797920 | Return/Change SAN-Storage | Assigned |  | 29.12.2022 08:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Sushmitha R (EXT)
CRQ000002153799 | #SK Decom<lpdkalas06vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 04.01.2023 18:00:00 | TAS000006798065 | Return/Change SAN-Storage | Assigned |  | 29.12.2022 08:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Chimaladinne Ramesh (EXT)
CRQ000002127315 | $1 "Colo Group Project" Moving server <lpdbs131> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731820 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Assigned |  | 29.12.2022 09:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002143662 | SAN_MIG ¦ BEJ401 ¦ lp19xentw007/008_lp19xentwa2020/2021_lp19crmtomat03/04 | Implementation In Progress | 29.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775528 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 29.12.2022 09:00:00 | 02.01.2023 17:00:00 | os-unix-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002144727 | SAN_MIG ¦ BEJ401 ¦ lp19xentwa2022/2023_lp19xentwb2020/2021_lp19xentwb2022/2023 | Implementation In Progress | 29.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775534 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 29.12.2022 09:00:00 | 02.01.2023 17:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002127316 | $1 "Colo Group Project" Moving server <lpdbs134>ONLY SAN Change (No physical Move of server) | Implementation In Progress | 23.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731997 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Assigned |  | 29.12.2022 09:30:00 | 29.12.2022 15:00:00 | os-unix-std-06:global:2nd | Vinayak Awasthi (EXT)
CRQ000002157576 | Postgres [VLAN tagging] lpxenppg083/084 | Scheduled | 29.12.2022 10:00:00 | 30.12.2022 10:00:00 | TAS000006808164 | [OS VLAN Tagging] | Assigned |  | 29.12.2022 10:30:00 | 29.12.2022 16:30:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002141968 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp03db001/002 | Scheduled | 30.12.2022 06:00:00 | 30.12.2022 14:00:00 | TAS000006768672 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Assigned |  | 30.12.2022 06:00:00 | 30.12.2022 12:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002141968 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp03db001/002 | Scheduled | 30.12.2022 06:00:00 | 30.12.2022 14:00:00 | TAS000006769021 | server-unix-std:global¦06¦050c-network-mgmt | Assigned |  | 30.12.2022 06:00:00 | 30.12.2022 12:00:00 | os-unix-std-06:global:2nd | Rajendra Bhandari (EXT)
CRQ000002140014 | *MR* *GSP* lp03d11/12 install Masterrelease | Scheduled | 30.12.2022 07:00:00 | 30.12.2022 17:00:00 | TAS000006763162 | *GSP* *W3* *OID* *4EYE* DNS (before MR) update for oraoid1.w3 | Assigned |  | 30.12.2022 07:00:00 | 30.12.2022 09:00:00 | os-unix-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002154009 | #AK Decom<lt19fieapdf00>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006797639 | Return/Change SAN-Storage | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd | Chimaladinne Ramesh (EXT)
CRQ000002154009 | #AK Decom<lt19fieapdf00>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006797640 | Clear virtual instance | Assigned |  | 30.12.2022 08:00:00 | 02.01.2023 18:00:00 | os-unix-std-06:global:2nd | Chimaladinne Ramesh (EXT)
CRQ000002153818 | #SA Decom<li19dc03>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006797180 | Return/Change SAN-Storage | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd | Sushmitha R (EXT)
CRQ000002153472 | #SA Decom<li19dc01>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006797651 | Return/Change SAN-Storage | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd | Paras Chhabra (EXT)
CRQ000002153920 | #DK Decom<lt19dc01>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006797675 | Return/Change SAN-Storage | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd | VinodKumar Uppara (EXT)
CRQ000002153920 | #DK Decom<lt19dc01>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006797676 | Clear virtual instance | Assigned |  | 30.12.2022 08:00:00 | 02.01.2023 18:00:00 | os-unix-std-06:global:2nd | VinodKumar Uppara (EXT)
CRQ000002154035 | #DK Decom <ltaax02>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006797687 | Return/Change SAN-Storage | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd | Paras Chhabra (EXT)
CRQ000002154035 | #DK Decom <ltaax02>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006797688 | Clear virtual instance | Assigned |  | 30.12.2022 08:00:00 | 02.01.2023 18:00:00 | os-unix-std-06:global:2nd | Paras Chhabra (EXT)
CRQ000002154310 | #DK Decom<lpdkalas70vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006798099 | Return/Change SAN-Storage | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd | Sushmitha R (EXT)
CRQ000002154310 | #DK Decom<lpdkalas70vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006798100 | Clear virtual instance | Assigned |  | 30.12.2022 08:00:00 | 02.01.2023 18:00:00 | os-unix-std-06:global:2nd | Sushmitha R (EXT)
CRQ000002154502 | #DK Decom<lpdkalas94vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006798553 | Return/Change SAN-Storage | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd | Ravneet Bagga (EXT)
CRQ000002154502 | #DK Decom<lpdkalas94vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006798554 | Clear virtual instance | Assigned |  | 30.12.2022 08:00:00 | 02.01.2023 18:00:00 | os-unix-std-06:global:2nd | Ravneet Bagga (EXT)
CRQ000002154032 | #DK Decom<lt19dc02>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006797828 | Return/Change SAN-Storage | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd | Nagarjuna Medarametla (EXT)
CRQ000002153793 | #AK Decom<lpdkalas97vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006798323 | Return/Change SAN-Storage | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd | Saeed Mansoorie (EXT)
CRQ000002153793 | #AK Decom<lpdkalas97vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006798324 | Clear virtual instance | Assigned |  | 30.12.2022 08:00:00 | 02.01.2023 18:00:00 | os-unix-std-06:global:2nd | Saeed Mansoorie (EXT)
CRQ000002153939 | #SA Decom<lpdkalas01vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006798053 | Return/Change SAN-Storage | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd | Paras Chhabra (EXT)
CRQ000002153498 | #AK Decom<lpdkalas96vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006798341 | Return/Change SAN-Storage | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd | Paras Chhabra (EXT)
CRQ000002153498 | #AK Decom<lpdkalas96vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006798343 | Clear virtual instance | Assigned |  | 30.12.2022 08:00:00 | 02.01.2023 18:00:00 | os-unix-std-06:global:2nd | Paras Chhabra (EXT)
CRQ000002154074 | #SA Decom<lpdkalas02vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006798077 | Return/Change SAN-Storage | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd | Chimaladinne Ramesh (EXT)
CRQ000002154074 | #SA Decom<lpdkalas02vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006798078 | Clear virtual instance | Assigned |  | 30.12.2022 08:00:00 | 02.01.2023 18:00:00 | os-unix-std-06:global:2nd | VinodKumar Uppara (EXT)
CRQ000002153955 | #SA Decom<lpdkalasmon01vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006798410 | Return/Change SAN-Storage | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd | VinodKumar Uppara (EXT)
CRQ000002153955 | #SA Decom<lpdkalasmon01vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006798412 | Clear virtual instance | Assigned |  | 30.12.2022 08:00:00 | 02.01.2023 18:00:00 | os-unix-std-06:global:2nd | VinodKumar Uppara (EXT)
CRQ000002154881 | #NN Decom<ltbkappnf01vm>VM | Implementation In Progress | 16.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006800630 | Return/Change SAN-Storage | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd | Saeed Mansoorie (EXT)
CRQ000002155306 | #NN Decom <ltaad03>VM | Implementation In Progress | 16.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006800459 | Return/Change SAN-Storage | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd | Chimaladinne Ramesh (EXT)
CRQ000002140014 | *MR* *GSP* lp03d11/12 install Masterrelease | Scheduled | 30.12.2022 07:00:00 | 30.12.2022 17:00:00 | TAS000006763160 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Assigned |  | 30.12.2022 09:00:00 | 30.12.2022 15:00:00 | os-unix-std-06:global:2nd | Rajendra Bhandari (EXT)
CRQ000002143663 | SAN_MIG ¦ BEJ401 ¦ lp19xenppgdk001/002_lp19xenppgdk005/006_lp19xenpw009/010 | Implementation In Progress | 30.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775649 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 30.12.2022 09:00:00 | 03.01.2023 17:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002144728 | SAN_MIG ¦ BEJ401 ¦ lp19xenpw011/012_lp19xenpwa2020/2021_lp19xenpwa2022/2023 | Implementation In Progress | 30.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775656 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 30.12.2022 09:00:00 | 03.01.2023 17:00:00 | os-unix-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789865 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789865 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789866 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789868 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789869 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789870 | server-unix-std:global¦06¦070-OS-config-check_IPS_I | Assigned |  | 30.12.2022 13:00:00 | 30.12.2022 17:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002140014 | *MR* *GSP* lp03d11/12 install Masterrelease | Scheduled | 30.12.2022 07:00:00 | 30.12.2022 17:00:00 | TAS000006763163 | *GSP* *W3* *OID* *4EYE* DNS (After MR) update for oraoid1.w3 | Assigned |  | 30.12.2022 15:00:00 | 30.12.2022 17:00:00 | os-unix-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752320 | server-unix-std:global¦06¦085c-move-farm-exec | Assigned |  | 30.12.2022 18:00:00 | 30.12.2022 22:00:00 | os-unix-std-06:global:2nd | Makkena Raghava (EXT)
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752321 | server-unix-std:global¦06¦085c-move-farm-exec | Assigned |  | 30.12.2022 22:00:00 | 31.12.2022 02:00:00 | os-unix-std-06:global:2nd | KumaraSwamy Nasika (EXT)
CRQ000002145069 | #SA Decom<lp10dkpga0034vm>VM | Implementation In Progress | 05.12.2022 08:00:00 | 10.01.2023 18:00:00 | TAS000006776050 | Return/Change SAN-Storage | Assigned |  | 03.01.2023 08:00:00 | 03.01.2023 18:00:00 | os-unix-std-06:global:2nd | Chimaladinne Ramesh (EXT)
CRQ000002145543 | #SA Decom<lp10dkpga0010vm>VM | Implementation In Progress | 05.12.2022 08:00:00 | 10.01.2023 18:00:00 | TAS000006776520 | Clear virtual instance | Assigned |  | 03.01.2023 08:00:00 | 04.01.2023 18:00:00 | os-unix-std-06:global:2nd | Saeed Mansoorie (EXT)
CRQ000002145543 | #SA Decom<lp10dkpga0010vm>VM | Implementation In Progress | 05.12.2022 08:00:00 | 10.01.2023 18:00:00 | TAS000006776875 | Return/Change SAN-Storage | Assigned |  | 03.01.2023 08:00:00 | 03.01.2023 18:00:00 | os-unix-std-06:global:2nd | Saeed Mansoorie (EXT)
CRQ000002159326 | MCI - Refresh SAP MCI from MCQ - Sub Tasks | Scheduled | 29.12.2022 09:00:00 | 31.03.2023 10:00:00 | TAS000006810806 | server-unix-std:global¦06¦002-sudo-mgmt-(NSTC) | Pending | Assignment | 29.12.2022 09:00:00 | 31.12.2022 09:00:00 | os-unix-std-06:global:2nd
CRQ000002154226 | #DK Decom<lpdkalas93vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006798175 | Return/Change SAN-Storage | Pending | Assignment | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002154226 | #DK Decom<lpdkalas93vm>VM | Implementation In Progress | 15.12.2022 08:00:00 | 05.01.2023 18:00:00 | TAS000006798176 | Clear virtual instance | Pending | Assignment | 30.12.2022 08:00:00 | 02.01.2023 18:00:00 | os-unix-std-06:global:2nd
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752953 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 31.12.2022 02:00:00 | 31.12.2022 06:00:00 | os-unix-std-06:global:2nd
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752954 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 31.12.2022 06:00:00 | 31.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002157628 | *ORA-OFFMIG* VM ltbkdbtde020vm , ltbkdbtde013vm from ltbkxendb33_34 to ltbkxendb53_54 | Implementation In Progress | 26.12.2022 20:00:00 | 06.01.2023 00:00:00 | TAS000006806253 | server-unix-std:global¦06¦088c-decom-weekly-move-vm-exec | Pending | Assignment | 31.12.2022 08:00:00 | 31.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006753624 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 31.12.2022 10:00:00 | 31.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002157628 | *ORA-OFFMIG* VM ltbkdbtde020vm , ltbkdbtde013vm from ltbkxendb33_34 to ltbkxendb53_54 | Implementation In Progress | 26.12.2022 20:00:00 | 06.01.2023 00:00:00 | TAS000006806258 | server-unix-std:global¦06¦088c-decom-weekly-move-vm-exec | Pending | Assignment | 31.12.2022 12:00:00 | 31.12.2022 14:00:00 | os-unix-std-06:global:2nd
CRQ000002126276 | Farm replacement - Source Farm lp07xenmq03/04 to Target Host lp07xen21/22 | Implementation In Progress | 20.12.2022 09:00:00 | 31.12.2022 09:00:00 | TAS000006731848 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 31.12.2022 18:00:00 | 31.12.2022 22:00:00 | os-unix-std-06:global:2nd
CRQ000002155246 | Critical BTRFS Balancing (lp19intra12001vm.bmwgroup.net) | Scheduled | 31.12.2022 22:00:00 | 01.01.2023 06:00:00 | TAS000006800388 | Critical BTRFS Balancing (lp19intra12001vm.bmwgroup.net) | Pending | Assignment | 31.12.2022 22:00:00 | 01.01.2023 02:00:00 | os-unix-std-06:global:2nd
CRQ000002129151 | Farm replacement <lp06xenmq03/04> VM's Offline Migration | Implementation In Progress | 06.12.2022 10:00:00 | 17.12.2022 10:00:00 | TAS000006737333 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 01.01.2023 00:00:00 | 01.01.2023 04:00:00 | os-unix-std-06:global:2nd
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805684 | server-unix-std:global¦06¦092c-universal | Pending | Assignment | 01.01.2023 03:30:00 | 04.01.2023 03:30:00 | os-unix-std-06:global:2nd
CRQ000002129151 | Farm replacement <lp06xenmq03/04> VM's Offline Migration | Implementation In Progress | 06.12.2022 10:00:00 | 17.12.2022 10:00:00 | TAS000006737334 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 01.01.2023 04:00:00 | 01.01.2023 06:00:00 | os-unix-std-06:global:2nd
CRQ000002129151 | Farm replacement <lp06xenmq03/04> VM's Offline Migration | Implementation In Progress | 06.12.2022 10:00:00 | 17.12.2022 10:00:00 | TAS000006737335 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 01.01.2023 08:00:00 | 01.01.2023 12:00:00 | os-unix-std-06:global:2nd
CRQ000002129151 | Farm replacement <lp06xenmq03/04> VM's Offline Migration | Implementation In Progress | 06.12.2022 10:00:00 | 17.12.2022 10:00:00 | TAS000006769055 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 01.01.2023 08:00:00 | 01.01.2023 10:00:00 | os-unix-std-06:global:2nd
CRQ000002159131 | Critical BTRFS Balancing (lp05ipm12w5vm) | Scheduled | 01.01.2023 08:00:00 | 01.01.2023 10:00:00 | TAS000006810397 | Critical BTRFS Balancing (lp05ipm12w5vm) | Pending | Assignment | 01.01.2023 08:00:00 | 01.01.2023 10:00:00 | os-unix-std-06:global:2nd
CRQ000002128057 | *MR+VERITAS* *ESP* lp19d23/24 install Masterrelease | Scheduled | 01.01.2023 17:00:00 | 02.01.2023 00:00:00 | TAS000006735031 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 01.01.2023 17:00:00 | 01.01.2023 23:00:00 | os-unix-std-06:global:2nd
CRQ000002126276 | Farm replacement - Source Farm lp07xenmq03/04 to Target Host lp07xen21/22 | Implementation In Progress | 20.12.2022 09:00:00 | 31.12.2022 09:00:00 | TAS000006731939 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 01.01.2023 18:00:00 | 01.01.2023 22:00:00 | os-unix-std-06:global:2nd
CRQ000002157628 | *ORA-OFFMIG* VM ltbkdbtde020vm , ltbkdbtde013vm from ltbkxendb33_34 to ltbkxendb53_54 | Implementation In Progress | 26.12.2022 20:00:00 | 06.01.2023 00:00:00 | TAS000006806254 | server-unix-std:global¦06¦089c-decom-weekly-move-vm-cleanup | Pending | Assignment | 02.01.2023 00:00:00 | 05.01.2023 23:00:00 | os-unix-std-06:global:2nd
CRQ000002152537 | *PKG-MOVE+Package domain change * *GSP* MOVE packages dbqarow1 from lp01d69/70 to lp01db005/006 | Scheduled | 29.12.2022 01:00:00 | 10.01.2023 05:00:00 | TAS000006793062 | server-unix-std:global¦06¦023c-cluster-migrate-package | Pending | Assignment | 02.01.2023 01:00:00 | 02.01.2023 05:00:00 | os-unix-std-06:global:2nd
CRQ000002152537 | *PKG-MOVE+Package domain change * *GSP* MOVE packages dbqarow1 from lp01d69/70 to lp01db005/006 | Scheduled | 29.12.2022 01:00:00 | 10.01.2023 05:00:00 | TAS000006793201 | server-unix-std:global¦06¦050c-network-mgmt | Pending | Assignment | 02.01.2023 01:00:00 | 02.01.2023 05:00:00 | os-unix-std-06:global:2nd
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006804612 | server-unix-std:global¦06¦092c-universal | Pending | Assignment | 02.01.2023 05:30:00 | 04.01.2023 23:30:00 | os-unix-std-06:global:2nd
CRQ000002126276 | Farm replacement - Source Farm lp07xenmq03/04 to Target Host lp07xen21/22 | Implementation In Progress | 20.12.2022 09:00:00 | 31.12.2022 09:00:00 | TAS000006731849 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 02.01.2023 09:00:00 | 07.01.2023 09:00:00 | os-unix-std-06:global:2nd
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752955 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 02.01.2023 09:00:00 | 07.01.2023 09:00:00 | os-unix-std-06:global:2nd
CRQ000002146306 | SAN_MIG ¦ BEJ401 ¦ lpcabcs3/4_lp19cip01/02_lp19cip03 | Implementation In Progress | 02.01.2023 09:00:00 | 02.02.2023 17:00:00 | TAS000006778429 | MIG_SERVER: Precheck for SAN-Migration | Pending | Assignment | 02.01.2023 09:00:00 | 04.01.2023 17:00:00 | os-unix-std-06:global:2nd
CRQ000002146895 | SAN_MIG ¦ BEJ401 ¦ lp19asr01_lp19xbackup02_li19d04 | Implementation In Progress | 02.01.2023 09:00:00 | 02.02.2023 17:00:00 | TAS000006781368 | MIG_SERVER: Precheck for SAN-Migration | Pending | Assignment | 02.01.2023 09:00:00 | 04.01.2023 17:00:00 | os-unix-std-06:global:2nd
CRQ000002129151 | Farm replacement <lp06xenmq03/04> VM's Offline Migration | Implementation In Progress | 06.12.2022 10:00:00 | 17.12.2022 10:00:00 | TAS000006736693 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 02.01.2023 10:00:00 | 07.01.2023 10:00:00 | os-unix-std-06:global:2nd
CRQ000002148781 | *DB_MOVE* *GMA* *dbcms01* *quis* *squarep* *rccbuffp* *flstdep* *wdmspe* MOVE to lpdbs103/lpdbs104 | Scheduled | 02.01.2023 11:00:00 | 22.01.2023 17:00:00 | TAS000006785783 | server-unix-std:global¦06¦035s-nfs-mount-filesystem | Pending | Assignment | 02.01.2023 13:00:00 | 04.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002152537 | *PKG-MOVE+Package domain change * *GSP* MOVE packages dbqarow1 from lp01d69/70 to lp01db005/006 | Scheduled | 29.12.2022 01:00:00 | 10.01.2023 05:00:00 | TAS000006793063 | server-unix-std:global¦06¦024c-cluster-migrate-cleanup-(NSTC) | Pending | Assignment | 03.01.2023 01:00:00 | 10.01.2023 01:00:00 | os-unix-std-06:global:2nd
CRQ000002145542 | #DK Decom<lp10dkpga0014vm>VM | Implementation In Progress | 05.12.2022 08:00:00 | 10.01.2023 18:00:00 | TAS000006776874 | Return/Change SAN-Storage | Pending | Assignment | 03.01.2023 08:00:00 | 03.01.2023 18:00:00 | os-unix-std-06:global:2nd
CRQ000002145542 | #DK Decom<lp10dkpga0014vm>VM | Implementation In Progress | 05.12.2022 08:00:00 | 10.01.2023 18:00:00 | TAS000006776876 | Clear virtual instance | Pending | Assignment | 03.01.2023 08:00:00 | 04.01.2023 18:00:00 | os-unix-std-06:global:2nd
CRQ000002145545 | #DK Decom<lp10dkpgb0009vm>VM | Implementation In Progress | 05.12.2022 08:00:00 | 10.01.2023 18:00:00 | TAS000006776953 | Return/Change SAN-Storage | Pending | Assignment | 03.01.2023 08:00:00 | 03.01.2023 18:00:00 | os-unix-std-06:global:2nd
CRQ000002145545 | #DK Decom<lp10dkpgb0009vm>VM | Implementation In Progress | 05.12.2022 08:00:00 | 10.01.2023 18:00:00 | TAS000006776955 | Clear virtual instance | Pending | Assignment | 03.01.2023 08:00:00 | 04.01.2023 18:00:00 | os-unix-std-06:global:2nd
CRQ000002153708 | Un-Mount and Mount to new NFS-Share for Telegramm storge in plant Berlin W03 | Scheduled | 03.01.2023 08:00:00 | 10.01.2023 12:00:00 | TAS000006797041 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Pending | Assignment | 03.01.2023 08:00:00 | 10.01.2023 10:00:00 | os-unix-std-06:global:2nd
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806223 | server-unix-std:global¦06¦092c-universal | Pending | Assignment | 03.01.2023 09:30:00 | 06.01.2023 09:30:00 | os-unix-std-06:global:2nd
CRQ000002147082 | Farm replacement <lpxenpwa013 / 014 > VM Offline Migration | Scheduled | 03.01.2023 08:00:00 | 08.01.2023 00:00:00 | TAS000006782211 | server-unix-std:global¦06¦084c-move-farm-prep-(NSTC) | Pending | Assignment | 04.01.2023 00:00:00 | 07.01.2023 00:00:00 | os-unix-std-06:global:2nd
CRQ000002145740 | SAN_MIG ¦ BEJ401 ¦ lp19xendk01/02_lp19xeneai03/4_lp19xenpgag001/002 | Implementation In Progress | 04.01.2023 09:00:00 | 03.02.2023 17:00:00 | TAS000006778443 | MIG_SERVER: Precheck for SAN-Migration | Pending | Assignment | 04.01.2023 09:00:00 | 09.01.2023 17:00:00 | os-unix-std-06:global:2nd
CRQ000002146307 | SAN_MIG ¦ BEJ401 ¦lp19xen15/16_lp19xen21/22 | Implementation In Progress | 04.01.2023 09:00:00 | 03.02.2023 17:00:00 | TAS000006778435 | MIG_SERVER: Precheck for SAN-Migration | Pending | Assignment | 04.01.2023 09:00:00 | 09.01.2023 17:00:00 | os-unix-std-06:global:2nd
CRQ000002126431 | $1 "Colo Group Project" Moving server <lpsbdbs012> ONLY SAN Change (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006730901 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Pending | Assignment | 04.01.2023 09:30:00 | 04.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002144399 | $1 "Colo Group Project" Moving server <lpdbs140> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006774918 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Pending | Assignment | 04.01.2023 09:30:00 | 04.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002145308 | $1 "Colo Group Project" Moving server <lpsbdbs014> ONLY SAN Change (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006775318 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Pending | Assignment | 04.01.2023 09:30:00 | 04.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002148715 | [VLAN tagging] lp1 lpsbxenfind003/004 | Scheduled | 09.12.2022 09:00:00 | 16.12.2022 17:00:00 | TAS000006784931 | server-unix-std:global¦06¦070c-modify-system | Pending | Assignment | 04.01.2023 11:00:00 | 04.01.2023 16:00:00 | os-unix-std-06:global:2nd
CRQ000002143251 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* for lp02dbipsq001/002 | Scheduled | 05.01.2023 08:30:00 | 05.01.2023 15:30:00 | TAS000006771849 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 05.01.2023 08:30:00 | 05.01.2023 14:30:00 | os-unix-std-06:global:2nd
CRQ000002143251 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* for lp02dbipsq001/002 | Scheduled | 05.01.2023 08:30:00 | 05.01.2023 15:30:00 | TAS000006771851 | server-unix-std:global¦06¦050c-network-mgmt | Pending | Assignment | 05.01.2023 08:30:00 | 05.01.2023 14:30:00 | os-unix-std-06:global:2nd
CRQ000002144918 | $1 "Colo Group Project" Moving server <lpdbs139> to new location | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775235 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Pending | Assignment | 05.01.2023 10:00:00 | 05.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002146522 | [VLAN tagging] lp1 lpsbxenfind001/002 | Scheduled | 07.12.2022 09:00:00 | 16.12.2022 18:00:00 | TAS000006778770 | server-unix-std:global¦06¦070c-modify-system | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 16:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785810 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785812 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785813 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785814 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785815 | server-unix-std:global¦06¦070-OS-config-check_IPS_I | Pending | Assignment | 05.01.2023 13:00:00 | 05.01.2023 17:00:00 | os-unix-std-06:global:2nd
CRQ000002121895 | $1 "Colo Group Project" Moving server <lpsbdbs011> to new location | Implementation In Progress | 09.11.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006722161 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144350 | $1 "Colo Group Project" Moving server <lpdbs129> to new location | Implementation In Progress | 05.12.2022 09:00:00 | 30.12.2022 18:00:00 | TAS000006773880 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144918 | $1 "Colo Group Project" Moving server <lpdbs139> to new location | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775239 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002145580 | *MR+Veritas* *ESP* lp30d09_lp30d10 install Masterrelease | Rejected | 01.01.2023 06:00:00 | 01.01.2023 16:00:00 | TAS000006776393 | *ESP* *W30* *OID* *4EYE* DNS (before MR+Veritas) update for oraoid2.w30.bmwgroup.net | Staged | Staging in Progress | 01.01.2023 06:00:00 | 01.01.2023 08:00:00 | os-unix-std-06:global:2nd
CRQ000002145580 | *MR+Veritas* *ESP* lp30d09_lp30d10 install Masterrelease | Rejected | 01.01.2023 06:00:00 | 01.01.2023 16:00:00 | TAS000006776395 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Staged | Staging in Progress | 01.01.2023 08:00:00 | 01.01.2023 14:00:00 | os-unix-std-06:global:2nd
CRQ000002145580 | *MR+Veritas* *ESP* lp30d09_lp30d10 install Masterrelease | Rejected | 01.01.2023 06:00:00 | 01.01.2023 16:00:00 | TAS000006776394 | *ESP* *W30* *OID* *4EYE* DNS (After MR+Veritas) update for oraoid2.w30.bmwgroup.net | Staged | Staging in Progress | 01.01.2023 14:00:00 | 01.01.2023 16:00:00 | os-unix-std-06:global:2nd
CRQ000002142661 | #DK Decom <lpdkpga00173vm>VM | Implementation In Progress | 30.11.2022 08:00:00 | 04.01.2023 18:00:00 | TAS000006770585 | Check SAN-Storage return | Staged | Staging in Progress | 03.01.2023 08:00:00 | 03.01.2023 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144628 | VLAN tagging lp10xen29/30 | Implementation In Progress | 09.12.2022 12:00:00 | 30.12.2022 20:00:00 | TAS000006774637 | check Task SAP | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002145207 | VLAN Tagging lpxensdi38 | Implementation In Progress | 09.12.2022 16:00:00 | 30.12.2022 20:00:00 | TAS000006775827 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002143988 | VLAN tagging lpsbxensor003/4 | Implementation In Progress | 09.12.2022 11:00:00 | 30.12.2022 20:00:00 | TAS000006774240 | check Task SAP VLAN tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002144629 | VLAN Tagging lp10xen23/24 | Implementation In Progress | 09.12.2022 15:00:00 | 30.12.2022 20:00:00 | TAS000006774638 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002145309 | VLAN Tagging ltxensor28 | Implementation In Progress | 09.12.2022 17:00:00 | 30.12.2022 20:00:00 | TAS000006775757 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002144959 | VLAN Tagging lpxensdi36 | Implementation In Progress | 09.12.2022 15:00:00 | 30.12.2022 20:00:00 | TAS000006775759 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002145208 | VLAN Tagging lpxensdi41 | Implementation In Progress | 09.12.2022 17:00:00 | 30.12.2022 20:00:00 | TAS000006775758 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002147667 | VLAN tagging lp05xen18 | Implementation In Progress | 26.12.2022 11:00:00 | 06.01.2023 20:00:00 | TAS000006782516 | check Task SAP/W05 VLAN tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002126431 | $1 "Colo Group Project" Moving server <lpsbdbs012> ONLY SAN Change (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006730905 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 05.01.2023 08:00:00 | 05.01.2023 18:00:00 | os-unix-std-06:global:2nd
CRQ000002145308 | $1 "Colo Group Project" Moving server <lpsbdbs014> ONLY SAN Change (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006775822 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 05.01.2023 08:00:00 | 05.01.2023 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144399 | $1 "Colo Group Project" Moving server <lpdbs140> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775722 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 05.01.2023 09:00:00 | 05.01.2023 18:00:00 | os-unix-std-06:global:2nd
CRQ000002121895 | $1 "Colo Group Project" Moving server <lpsbdbs011> to new location | Implementation In Progress | 09.11.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006722157 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 05.01.2023 09:30:00 | 05.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002144383 | $1 "Colo Group Project" Moving server <lpsbdbs013> to new location | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006775333 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 05.01.2023 10:00:00 | 05.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002145283 | $1 "Colo Group Project" Moving server <lpsbdbs015> to new location | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006776680 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 05.01.2023 10:00:00 | 05.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002129291 | Mount the share in lpvpp02 | Scheduled | 15.11.2022 17:00:00 | 19.11.2022 17:00:00 | TAS000006738382 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Assigned |  | 30.12.2022 05:00:00 | 03.01.2023 05:00:00 | os-linux-std-06:global:2nd | Rajendra Bhandari (EXT)
CRQ000002129291 | Mount the share in lpvpp02 | Scheduled | 15.11.2022 17:00:00 | 19.11.2022 17:00:00 | TAS000006738528 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Assigned |  | 30.12.2022 05:00:00 | 03.01.2023 05:00:00 | os-linux-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002129291 | Mount the share in lpvpp02 | Scheduled | 15.11.2022 17:00:00 | 19.11.2022 17:00:00 | TAS000006738529 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Assigned |  | 30.12.2022 05:00:00 | 03.01.2023 05:00:00 | os-linux-std-06:global:2nd | Rajendra Bhandari (EXT)
CRQ000002129291 | Mount the share in lpvpp02 | Scheduled | 15.11.2022 17:00:00 | 19.11.2022 17:00:00 | TAS000006738530 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Assigned |  | 30.12.2022 05:00:00 | 03.01.2023 05:00:00 | os-linux-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002159445 | #NK $2 Provision <lp19bp05-lp19bp06> VM Virtual Server - Gold | Implementation In Progress | 28.12.2022 08:00:00 | 03.01.2023 18:00:00 | TAS000006812065 | Quality check | Assigned |  | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-linux-std-06:global:2nd | Shruti Pandey (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789867 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002158171 | MGx: Add QQBMWMUX + sudo | Implementation In Progress | 28.12.2022 09:00:00 | 04.01.2023 18:00:00 | TAS000006808143 | server-unix-std:global¦06¦002-sudo-mgmt-(NSTC) | Assigned |  | 30.12.2022 13:00:00 | 04.01.2023 13:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002148197 | W6.11 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 31.12.2022 00:00:00 | 31.12.2022 12:00:00 | TAS000006784410 | server-unix-std:global¦06¦092c-universal | Assigned |  | 31.12.2022 00:00:00 | 31.12.2022 12:00:00 | os-linux-std-06:global:2nd | Alok Pai (EXT)
CRQ000002143290 | Move VMware VM to other VMware farm (2nd try) | Scheduled | 01.01.2023 00:00:00 | 25.01.2023 00:00:00 | TAS000006771818 | server-unix-std:global¦06¦081c-move-vm-prep-(NSTC) | Assigned |  | 01.01.2023 00:00:00 | 09.01.2023 00:00:00 | os-linux-std-06:global:2nd | KumaraSwamy Nasika (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006777852 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 01:30:00 | 04.01.2023 01:30:00 | os-linux-std-06:global:2nd | KumaraSwamy Nasika (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805685 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 05:30:00 | 04.01.2023 05:30:00 | os-linux-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805762 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 09:30:00 | 04.01.2023 09:30:00 | os-linux-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006804607 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 11:30:00 | 04.01.2023 11:30:00 | os-linux-std-06:global:2nd | Nanda Padala (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805688 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 13:30:00 | 04.01.2023 13:30:00 | os-linux-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805691 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 18:30:00 | 04.01.2023 18:30:00 | os-linux-std-06:global:2nd | Manvendra Singh (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006804611 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 20:30:00 | 04.01.2023 20:30:00 | os-linux-std-06:global:2nd | Alok Pai (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805695 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 22:30:00 | 04.01.2023 22:30:00 | os-linux-std-06:global:2nd | Gaurav Johri (EXT)
CRQ000002153326 | Sudo rights for Application User | Scheduled | 02.01.2023 08:00:00 | 06.01.2023 00:00:00 | TAS000006793516 | server-unix-std:global¦06¦002-sudo-mgmt-(NSTC) | Assigned |  | 02.01.2023 00:00:00 | 04.01.2023 00:00:00 | os-linux-std-06:global:2nd | Alok Pai (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805764 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 01:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Rohit Varmani (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805714 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 03:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002135557 | RRI Migration: Migrate C:D and MQ | Implementation In Progress | 05.12.2022 13:00:00 | 31.01.2023 18:00:00 | TAS000006805398 | server-unix-std:global¦045s-install-override-(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 04.01.2023 18:00:00 | os-linux-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002140850 | TAEE.Next##PRE-PROD##DE##NO## PRE-PROD maintenance work | Implementation In Progress | 28.11.2022 15:00:00 | 28.12.2022 15:00:00 | TAS000006808239 | server-unix-std:global¦06¦002c-sudo-temp-root-permissions(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 04.01.2023 09:00:00 | os-linux-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002152845 | RRP Migration: Migrate AD Roles and Middleware | Scheduled | 02.01.2023 09:00:00 | 24.02.2023 18:00:00 | TAS000006795964 | server-unix-std:global¦06¦002-sudo-mgmt-(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 05.01.2023 09:00:00 | os-linux-std-06:global:2nd | Kamendra Chauhan (EXT)
CRQ000002152845 | RRP Migration: Migrate AD Roles and Middleware | Scheduled | 02.01.2023 09:00:00 | 24.02.2023 18:00:00 | TAS000006795966 | server-unix-std:global¦06¦001s-user-mgmt-(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 05.01.2023 09:00:00 | os-linux-std-06:global:2nd | Tushar Lohia (EXT)
CRQ000002152845 | RRP Migration: Migrate AD Roles and Middleware | Scheduled | 02.01.2023 09:00:00 | 24.02.2023 18:00:00 | TAS000006796155 | server-unix-std:global¦06¦001s-user-mgmt-(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 05.01.2023 09:00:00 | os-linux-std-06:global:2nd | Ashwini Tendulkar (EXT)
CRQ000002152845 | RRP Migration: Migrate AD Roles and Middleware | Scheduled | 02.01.2023 09:00:00 | 24.02.2023 18:00:00 | TAS000006805400 | server-unix-std:global¦045s-install-override-(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 05.01.2023 09:00:00 | os-linux-std-06:global:2nd | Ashwini Tendulkar (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805765 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 09:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Prodyut Paul (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805717 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 11:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805718 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 13:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Kishore Kumar (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805719 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 18:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Manvendra Singh (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006777082 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 01:30:00 | 06.01.2023 01:30:00 | os-linux-std-06:global:2nd | Alok Pai (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006805721 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 01:30:00 | 06.01.2023 03:30:00 | os-linux-std-06:global:2nd | Gaurav Johri (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805720 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 02:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806222 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 05:30:00 | 06.01.2023 05:30:00 | os-linux-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806224 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 11:30:00 | 06.01.2023 11:30:00 | os-linux-std-06:global:2nd | Ashwini Tendulkar (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806225 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 13:30:00 | 06.01.2023 13:30:00 | os-linux-std-06:global:2nd | Prodyut Paul (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806227 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 18:30:00 | 06.01.2023 18:30:00 | os-linux-std-06:global:2nd | Makkena Raghava (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006805783 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 20:30:00 | 06.01.2023 20:30:00 | os-linux-std-06:global:2nd | Rohit Varmani (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006805784 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 22:30:00 | 06.01.2023 22:30:00 | os-linux-std-06:global:2nd | Gaurav Johri (EXT)

## MasterSheet-1
CRQ Number | CRQ Description | CRQ Status | CRQ Start Date | CRQ End Date | Linux Tasks in CRQ | Task Description | Task Status | Task Status 1 | Task Start Date | Task End Date | Xen/VMWare | Assignee
CRQ000002121895 | $1 "Colo Group Project" Moving server <lpsbdbs011> to new location | Implementation In Progress | 09.11.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006722161 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002121895 | $1 "Colo Group Project" Moving server <lpsbdbs011> to new location | Implementation In Progress | 09.11.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006722157 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 05.01.2023 09:30:00 | 05.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002126276 | Farm replacement - Source Farm lp07xenmq03/04 to Target Host lp07xen21/22 | Implementation In Progress | 20.12.2022 09:00:00 | 31.12.2022 09:00:00 | TAS000006731848 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 31.12.2022 18:00:00 | 31.12.2022 22:00:00 | os-unix-std-06:global:2nd
CRQ000002126276 | Farm replacement - Source Farm lp07xenmq03/04 to Target Host lp07xen21/22 | Implementation In Progress | 20.12.2022 09:00:00 | 31.12.2022 09:00:00 | TAS000006731939 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 01.01.2023 18:00:00 | 01.01.2023 22:00:00 | os-unix-std-06:global:2nd
CRQ000002126276 | Farm replacement - Source Farm lp07xenmq03/04 to Target Host lp07xen21/22 | Implementation In Progress | 20.12.2022 09:00:00 | 31.12.2022 09:00:00 | TAS000006731849 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 02.01.2023 09:00:00 | 07.01.2023 09:00:00 | os-unix-std-06:global:2nd
CRQ000002126431 | $1 "Colo Group Project" Moving server <lpsbdbs012> ONLY SAN Change (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006730901 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Pending | Assignment | 04.01.2023 09:30:00 | 04.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002126431 | $1 "Colo Group Project" Moving server <lpsbdbs012> ONLY SAN Change (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006730905 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 05.01.2023 08:00:00 | 05.01.2023 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127315 | $1 "Colo Group Project" Moving server <lpdbs131> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731820 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Assigned |  | 29.12.2022 09:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002127316 | $1 "Colo Group Project" Moving server <lpdbs134>ONLY SAN Change (No physical Move of server) | Implementation In Progress | 23.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731997 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Assigned |  | 29.12.2022 09:30:00 | 29.12.2022 15:00:00 | os-unix-std-06:global:2nd | Vinayak Awasthi (EXT)
CRQ000002128057 | *MR+VERITAS* *ESP* lp19d23/24 install Masterrelease | Scheduled | 01.01.2023 17:00:00 | 02.01.2023 00:00:00 | TAS000006735031 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 01.01.2023 17:00:00 | 01.01.2023 23:00:00 | os-unix-std-06:global:2nd
CRQ000002129151 | Farm replacement <lp06xenmq03/04> VM's Offline Migration | Implementation In Progress | 06.12.2022 10:00:00 | 17.12.2022 10:00:00 | TAS000006737333 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 01.01.2023 00:00:00 | 01.01.2023 04:00:00 | os-unix-std-06:global:2nd
CRQ000002129151 | Farm replacement <lp06xenmq03/04> VM's Offline Migration | Implementation In Progress | 06.12.2022 10:00:00 | 17.12.2022 10:00:00 | TAS000006737334 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 01.01.2023 04:00:00 | 01.01.2023 06:00:00 | os-unix-std-06:global:2nd
CRQ000002129151 | Farm replacement <lp06xenmq03/04> VM's Offline Migration | Implementation In Progress | 06.12.2022 10:00:00 | 17.12.2022 10:00:00 | TAS000006737335 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 01.01.2023 08:00:00 | 01.01.2023 12:00:00 | os-unix-std-06:global:2nd
CRQ000002129151 | Farm replacement <lp06xenmq03/04> VM's Offline Migration | Implementation In Progress | 06.12.2022 10:00:00 | 17.12.2022 10:00:00 | TAS000006769055 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 01.01.2023 08:00:00 | 01.01.2023 10:00:00 | os-unix-std-06:global:2nd
CRQ000002129151 | Farm replacement <lp06xenmq03/04> VM's Offline Migration | Implementation In Progress | 06.12.2022 10:00:00 | 17.12.2022 10:00:00 | TAS000006736693 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 02.01.2023 10:00:00 | 07.01.2023 10:00:00 | os-unix-std-06:global:2nd
CRQ000002129291 | Mount the share in lpvpp02 | Scheduled | 15.11.2022 17:00:00 | 19.11.2022 17:00:00 | TAS000006738382 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Assigned |  | 30.12.2022 05:00:00 | 03.01.2023 05:00:00 | os-linux-std-06:global:2nd | Rajendra Bhandari (EXT)
CRQ000002129291 | Mount the share in lpvpp02 | Scheduled | 15.11.2022 17:00:00 | 19.11.2022 17:00:00 | TAS000006738528 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Assigned |  | 30.12.2022 05:00:00 | 03.01.2023 05:00:00 | os-linux-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002129291 | Mount the share in lpvpp02 | Scheduled | 15.11.2022 17:00:00 | 19.11.2022 17:00:00 | TAS000006738529 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Assigned |  | 30.12.2022 05:00:00 | 03.01.2023 05:00:00 | os-linux-std-06:global:2nd | Rajendra Bhandari (EXT)
CRQ000002129291 | Mount the share in lpvpp02 | Scheduled | 15.11.2022 17:00:00 | 19.11.2022 17:00:00 | TAS000006738530 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Assigned |  | 30.12.2022 05:00:00 | 03.01.2023 05:00:00 | os-linux-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002135557 | RRI Migration: Migrate C:D and MQ | Implementation In Progress | 05.12.2022 13:00:00 | 31.01.2023 18:00:00 | TAS000006805398 | server-unix-std:global¦045s-install-override-(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 04.01.2023 18:00:00 | os-linux-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752320 | server-unix-std:global¦06¦085c-move-farm-exec | Assigned |  | 30.12.2022 18:00:00 | 30.12.2022 22:00:00 | os-unix-std-06:global:2nd | Makkena Raghava (EXT)
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752321 | server-unix-std:global¦06¦085c-move-farm-exec | Assigned |  | 30.12.2022 22:00:00 | 31.12.2022 02:00:00 | os-unix-std-06:global:2nd | KumaraSwamy Nasika (EXT)
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752953 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 31.12.2022 02:00:00 | 31.12.2022 06:00:00 | os-unix-std-06:global:2nd
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752954 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 31.12.2022 06:00:00 | 31.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006753624 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 31.12.2022 10:00:00 | 31.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752955 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 02.01.2023 09:00:00 | 07.01.2023 09:00:00 | os-unix-std-06:global:2nd
CRQ000002140014 | *MR* *GSP* lp03d11/12 install Masterrelease | Scheduled | 30.12.2022 07:00:00 | 30.12.2022 17:00:00 | TAS000006763162 | *GSP* *W3* *OID* *4EYE* DNS (before MR) update for oraoid1.w3 | Assigned |  | 30.12.2022 07:00:00 | 30.12.2022 09:00:00 | os-unix-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002140014 | *MR* *GSP* lp03d11/12 install Masterrelease | Scheduled | 30.12.2022 07:00:00 | 30.12.2022 17:00:00 | TAS000006763160 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Assigned |  | 30.12.2022 09:00:00 | 30.12.2022 15:00:00 | os-unix-std-06:global:2nd | Rajendra Bhandari (EXT)
CRQ000002140014 | *MR* *GSP* lp03d11/12 install Masterrelease | Scheduled | 30.12.2022 07:00:00 | 30.12.2022 17:00:00 | TAS000006763163 | *GSP* *W3* *OID* *4EYE* DNS (After MR) update for oraoid1.w3 | Assigned |  | 30.12.2022 15:00:00 | 30.12.2022 17:00:00 | os-unix-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002140850 | TAEE.Next##PRE-PROD##DE##NO## PRE-PROD maintenance work | Implementation In Progress | 28.11.2022 15:00:00 | 28.12.2022 15:00:00 | TAS000006808239 | server-unix-std:global¦06¦002c-sudo-temp-root-permissions(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 04.01.2023 09:00:00 | os-linux-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002141968 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp03db001/002 | Scheduled | 30.12.2022 06:00:00 | 30.12.2022 14:00:00 | TAS000006768672 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Assigned |  | 30.12.2022 06:00:00 | 30.12.2022 12:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002141968 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp03db001/002 | Scheduled | 30.12.2022 06:00:00 | 30.12.2022 14:00:00 | TAS000006769021 | server-unix-std:global¦06¦050c-network-mgmt | Assigned |  | 30.12.2022 06:00:00 | 30.12.2022 12:00:00 | os-unix-std-06:global:2nd | Rajendra Bhandari (EXT)
CRQ000002143251 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* for lp02dbipsq001/002 | Scheduled | 05.01.2023 08:30:00 | 05.01.2023 15:30:00 | TAS000006771849 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 05.01.2023 08:30:00 | 05.01.2023 14:30:00 | os-unix-std-06:global:2nd
CRQ000002143251 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* for lp02dbipsq001/002 | Scheduled | 05.01.2023 08:30:00 | 05.01.2023 15:30:00 | TAS000006771851 | server-unix-std:global¦06¦050c-network-mgmt | Pending | Assignment | 05.01.2023 08:30:00 | 05.01.2023 14:30:00 | os-unix-std-06:global:2nd
CRQ000002143290 | Move VMware VM to other VMware farm (2nd try) | Scheduled | 01.01.2023 00:00:00 | 25.01.2023 00:00:00 | TAS000006771818 | server-unix-std:global¦06¦081c-move-vm-prep-(NSTC) | Assigned |  | 01.01.2023 00:00:00 | 09.01.2023 00:00:00 | os-linux-std-06:global:2nd | KumaraSwamy Nasika (EXT)
CRQ000002143662 | SAN_MIG ¦ BEJ401 ¦ lp19xentw007/008_lp19xentwa2020/2021_lp19crmtomat03/04 | Implementation In Progress | 29.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775528 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 29.12.2022 09:00:00 | 02.01.2023 17:00:00 | os-unix-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002143663 | SAN_MIG ¦ BEJ401 ¦ lp19xenppgdk001/002_lp19xenppgdk005/006_lp19xenpw009/010 | Implementation In Progress | 30.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775649 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 30.12.2022 09:00:00 | 03.01.2023 17:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002143988 | VLAN tagging lpsbxensor003/4 | Implementation In Progress | 09.12.2022 11:00:00 | 30.12.2022 20:00:00 | TAS000006774240 | check Task SAP VLAN tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002144350 | $1 "Colo Group Project" Moving server <lpdbs129> to new location | Implementation In Progress | 05.12.2022 09:00:00 | 30.12.2022 18:00:00 | TAS000006773880 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144383 | $1 "Colo Group Project" Moving server <lpsbdbs013> to new location | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006775333 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 05.01.2023 10:00:00 | 05.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002144399 | $1 "Colo Group Project" Moving server <lpdbs140> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006774918 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Pending | Assignment | 04.01.2023 09:30:00 | 04.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002144399 | $1 "Colo Group Project" Moving server <lpdbs140> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775722 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 05.01.2023 09:00:00 | 05.01.2023 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144628 | VLAN tagging lp10xen29/30 | Implementation In Progress | 09.12.2022 12:00:00 | 30.12.2022 20:00:00 | TAS000006774637 | check Task SAP | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002144629 | VLAN Tagging lp10xen23/24 | Implementation In Progress | 09.12.2022 15:00:00 | 30.12.2022 20:00:00 | TAS000006774638 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002144727 | SAN_MIG ¦ BEJ401 ¦ lp19xentwa2022/2023_lp19xentwb2020/2021_lp19xentwb2022/2023 | Implementation In Progress | 29.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775534 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 29.12.2022 09:00:00 | 02.01.2023 17:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002144728 | SAN_MIG ¦ BEJ401 ¦ lp19xenpw011/012_lp19xenpwa2020/2021_lp19xenpwa2022/2023 | Implementation In Progress | 30.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775656 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 30.12.2022 09:00:00 | 03.01.2023 17:00:00 | os-unix-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002144918 | $1 "Colo Group Project" Moving server <lpdbs139> to new location | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775235 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Pending | Assignment | 05.01.2023 10:00:00 | 05.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002144918 | $1 "Colo Group Project" Moving server <lpdbs139> to new location | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775239 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144959 | VLAN Tagging lpxensdi36 | Implementation In Progress | 09.12.2022 15:00:00 | 30.12.2022 20:00:00 | TAS000006775759 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002145059 | $1 "Colo Group Project" Moving server <lpdbs141> to new location | Implementation In Progress | 06.12.2022 03:30:00 | 31.01.2023 13:30:00 | TAS000006776763 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Assigned |  | 29.12.2022 08:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002145207 | VLAN Tagging lpxensdi38 | Implementation In Progress | 09.12.2022 16:00:00 | 30.12.2022 20:00:00 | TAS000006775827 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002145208 | VLAN Tagging lpxensdi41 | Implementation In Progress | 09.12.2022 17:00:00 | 30.12.2022 20:00:00 | TAS000006775758 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002145283 | $1 "Colo Group Project" Moving server <lpsbdbs015> to new location | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006776680 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 05.01.2023 10:00:00 | 05.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002145308 | $1 "Colo Group Project" Moving server <lpsbdbs014> ONLY SAN Change (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006775318 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Pending | Assignment | 04.01.2023 09:30:00 | 04.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002145308 | $1 "Colo Group Project" Moving server <lpsbdbs014> ONLY SAN Change (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006775822 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 05.01.2023 08:00:00 | 05.01.2023 18:00:00 | os-unix-std-06:global:2nd
CRQ000002145309 | VLAN Tagging ltxensor28 | Implementation In Progress | 09.12.2022 17:00:00 | 30.12.2022 20:00:00 | TAS000006775757 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806223 | server-unix-std:global¦06¦092c-universal | Pending | Assignment | 03.01.2023 09:30:00 | 06.01.2023 09:30:00 | os-unix-std-06:global:2nd
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006777082 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 01:30:00 | 06.01.2023 01:30:00 | os-linux-std-06:global:2nd | Alok Pai (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006805721 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 01:30:00 | 06.01.2023 03:30:00 | os-linux-std-06:global:2nd | Gaurav Johri (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806222 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 05:30:00 | 06.01.2023 05:30:00 | os-linux-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806224 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 11:30:00 | 06.01.2023 11:30:00 | os-linux-std-06:global:2nd | Ashwini Tendulkar (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806225 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 13:30:00 | 06.01.2023 13:30:00 | os-linux-std-06:global:2nd | Prodyut Paul (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806227 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 18:30:00 | 06.01.2023 18:30:00 | os-linux-std-06:global:2nd | Makkena Raghava (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006805783 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 20:30:00 | 06.01.2023 20:30:00 | os-linux-std-06:global:2nd | Rohit Varmani (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006805784 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 22:30:00 | 06.01.2023 22:30:00 | os-linux-std-06:global:2nd | Gaurav Johri (EXT)
CRQ000002145740 | SAN_MIG ¦ BEJ401 ¦ lp19xendk01/02_lp19xeneai03/4_lp19xenpgag001/002 | Implementation In Progress | 04.01.2023 09:00:00 | 03.02.2023 17:00:00 | TAS000006778443 | MIG_SERVER: Precheck for SAN-Migration | Pending | Assignment | 04.01.2023 09:00:00 | 09.01.2023 17:00:00 | os-unix-std-06:global:2nd
CRQ000002145911 | $1 "Colo Group Project" Moving server <lpdbs145> to new location | Implementation In Progress | 06.12.2022 08:00:00 | 28.02.2023 18:00:00 | TAS000006776407 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Assigned |  | 29.12.2022 08:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002146003 | $1 "Colo Group Project" Moving server <lpdbs147> to new location | Implementation In Progress | 06.12.2022 08:00:00 | 28.02.2023 18:00:00 | TAS000006777840 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Assigned |  | 29.12.2022 08:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Rajendra Bhandari (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805684 | server-unix-std:global¦06¦092c-universal | Pending | Assignment | 01.01.2023 03:30:00 | 04.01.2023 03:30:00 | os-unix-std-06:global:2nd
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006804612 | server-unix-std:global¦06¦092c-universal | Pending | Assignment | 02.01.2023 05:30:00 | 04.01.2023 23:30:00 | os-unix-std-06:global:2nd
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006777852 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 01:30:00 | 04.01.2023 01:30:00 | os-linux-std-06:global:2nd | KumaraSwamy Nasika (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805685 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 05:30:00 | 04.01.2023 05:30:00 | os-linux-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805762 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 09:30:00 | 04.01.2023 09:30:00 | os-linux-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006804607 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 11:30:00 | 04.01.2023 11:30:00 | os-linux-std-06:global:2nd | Nanda Padala (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805688 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 13:30:00 | 04.01.2023 13:30:00 | os-linux-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805691 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 18:30:00 | 04.01.2023 18:30:00 | os-linux-std-06:global:2nd | Manvendra Singh (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006804611 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 20:30:00 | 04.01.2023 20:30:00 | os-linux-std-06:global:2nd | Alok Pai (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805695 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 22:30:00 | 04.01.2023 22:30:00 | os-linux-std-06:global:2nd | Gaurav Johri (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805764 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 01:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Rohit Varmani (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805714 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 03:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805765 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 09:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Prodyut Paul (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805717 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 11:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805718 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 13:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Kishore Kumar (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805719 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 18:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Manvendra Singh (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805720 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 02:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002146306 | SAN_MIG ¦ BEJ401 ¦ lpcabcs3/4_lp19cip01/02_lp19cip03 | Implementation In Progress | 02.01.2023 09:00:00 | 02.02.2023 17:00:00 | TAS000006778429 | MIG_SERVER: Precheck for SAN-Migration | Pending | Assignment | 02.01.2023 09:00:00 | 04.01.2023 17:00:00 | os-unix-std-06:global:2nd
CRQ000002146307 | SAN_MIG ¦ BEJ401 ¦lp19xen15/16_lp19xen21/22 | Implementation In Progress | 04.01.2023 09:00:00 | 03.02.2023 17:00:00 | TAS000006778435 | MIG_SERVER: Precheck for SAN-Migration | Pending | Assignment | 04.01.2023 09:00:00 | 09.01.2023 17:00:00 | os-unix-std-06:global:2nd
CRQ000002146522 | [VLAN tagging] lp1 lpsbxenfind001/002 | Scheduled | 07.12.2022 09:00:00 | 16.12.2022 18:00:00 | TAS000006778770 | server-unix-std:global¦06¦070c-modify-system | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 16:00:00 | os-unix-std-06:global:2nd
CRQ000002146895 | SAN_MIG ¦ BEJ401 ¦ lp19asr01_lp19xbackup02_li19d04 | Implementation In Progress | 02.01.2023 09:00:00 | 02.02.2023 17:00:00 | TAS000006781368 | MIG_SERVER: Precheck for SAN-Migration | Pending | Assignment | 02.01.2023 09:00:00 | 04.01.2023 17:00:00 | os-unix-std-06:global:2nd
CRQ000002147082 | Farm replacement <lpxenpwa013 / 014 > VM Offline Migration | Scheduled | 03.01.2023 08:00:00 | 08.01.2023 00:00:00 | TAS000006782211 | server-unix-std:global¦06¦084c-move-farm-prep-(NSTC) | Pending | Assignment | 04.01.2023 00:00:00 | 07.01.2023 00:00:00 | os-unix-std-06:global:2nd
CRQ000002147667 | VLAN tagging lp05xen18 | Implementation In Progress | 26.12.2022 11:00:00 | 06.01.2023 20:00:00 | TAS000006782516 | check Task SAP/W05 VLAN tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002148197 | W6.11 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 31.12.2022 00:00:00 | 31.12.2022 12:00:00 | TAS000006784410 | server-unix-std:global¦06¦092c-universal | Assigned |  | 31.12.2022 00:00:00 | 31.12.2022 12:00:00 | os-linux-std-06:global:2nd | Alok Pai (EXT)
CRQ000002148715 | [VLAN tagging] lp1 lpsbxenfind003/004 | Scheduled | 09.12.2022 09:00:00 | 16.12.2022 17:00:00 | TAS000006784931 | server-unix-std:global¦06¦070c-modify-system | Pending | Assignment | 04.01.2023 11:00:00 | 04.01.2023 16:00:00 | os-unix-std-06:global:2nd
CRQ000002148781 | *DB_MOVE* *GMA* *dbcms01* *quis* *squarep* *rccbuffp* *flstdep* *wdmspe* MOVE to lpdbs103/lpdbs104 | Scheduled | 02.01.2023 11:00:00 | 22.01.2023 17:00:00 | TAS000006785783 | server-unix-std:global¦06¦035s-nfs-mount-filesystem | Pending | Assignment | 02.01.2023 13:00:00 | 04.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785810 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785812 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785813 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785814 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785815 | server-unix-std:global¦06¦070-OS-config-check_IPS_I | Pending | Assignment | 05.01.2023 13:00:00 | 05.01.2023 17:00:00 | os-unix-std-06:global:2nd
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789865 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789865 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789866 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789868 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789869 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789870 | server-unix-std:global¦06¦070-OS-config-check_IPS_I | Assigned |  | 30.12.2022 13:00:00 | 30.12.2022 17:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789867 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002152537 | *PKG-MOVE+Package domain change * *GSP* MOVE packages dbqarow1 from lp01d69/70 to lp01db005/006 | Scheduled | 29.12.2022 01:00:00 | 10.01.2023 05:00:00 | TAS000006793062 | server-unix-std:global¦06¦023c-cluster-migrate-package | Pending | Assignment | 02.01.2023 01:00:00 | 02.01.2023 05:00:00 | os-unix-std-06:global:2nd
CRQ000002152537 | *PKG-MOVE+Package domain change * *GSP* MOVE packages dbqarow1 from lp01d69/70 to lp01db005/006 | Scheduled | 29.12.2022 01:00:00 | 10.01.2023 05:00:00 | TAS000006793201 | server-unix-std:global¦06¦050c-network-mgmt | Pending | Assignment | 02.01.2023 01:00:00 | 02.01.2023 05:00:00 | os-unix-std-06:global:2nd
CRQ000002152537 | *PKG-MOVE+Package domain change * *GSP* MOVE packages dbqarow1 from lp01d69/70 to lp01db005/006 | Scheduled | 29.12.2022 01:00:00 | 10.01.2023 05:00:00 | TAS000006793063 | server-unix-std:global¦06¦024c-cluster-migrate-cleanup-(NSTC) | Pending | Assignment | 03.01.2023 01:00:00 | 10.01.2023 01:00:00 | os-unix-std-06:global:2nd
CRQ000002152845 | RRP Migration: Migrate AD Roles and Middleware | Scheduled | 02.01.2023 09:00:00 | 24.02.2023 18:00:00 | TAS000006795964 | server-unix-std:global¦06¦002-sudo-mgmt-(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 05.01.2023 09:00:00 | os-linux-std-06:global:2nd | Kamendra Chauhan (EXT)
CRQ000002152845 | RRP Migration: Migrate AD Roles and Middleware | Scheduled | 02.01.2023 09:00:00 | 24.02.2023 18:00:00 | TAS000006795966 | server-unix-std:global¦06¦001s-user-mgmt-(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 05.01.2023 09:00:00 | os-linux-std-06:global:2nd | Tushar Lohia (EXT)
CRQ000002152845 | RRP Migration: Migrate AD Roles and Middleware | Scheduled | 02.01.2023 09:00:00 | 24.02.2023 18:00:00 | TAS000006796155 | server-unix-std:global¦06¦001s-user-mgmt-(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 05.01.2023 09:00:00 | os-linux-std-06:global:2nd | Ashwini Tendulkar (EXT)
CRQ000002152845 | RRP Migration: Migrate AD Roles and Middleware | Scheduled | 02.01.2023 09:00:00 | 24.02.2023 18:00:00 | TAS000006805400 | server-unix-std:global¦045s-install-override-(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 05.01.2023 09:00:00 | os-linux-std-06:global:2nd | Ashwini Tendulkar (EXT)
CRQ000002153326 | Sudo rights for Application User | Scheduled | 02.01.2023 08:00:00 | 06.01.2023 00:00:00 | TAS000006793516 | server-unix-std:global¦06¦002-sudo-mgmt-(NSTC) | Assigned |  | 02.01.2023 00:00:00 | 04.01.2023 00:00:00 | os-linux-std-06:global:2nd | Alok Pai (EXT)
CRQ000002153708 | Un-Mount and Mount to new NFS-Share for Telegramm storge in plant Berlin W03 | Scheduled | 03.01.2023 08:00:00 | 10.01.2023 12:00:00 | TAS000006797041 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Pending | Assignment | 03.01.2023 08:00:00 | 10.01.2023 10:00:00 | os-unix-std-06:global:2nd
CRQ000002155246 | Critical BTRFS Balancing (lp19intra12001vm.bmwgroup.net) | Scheduled | 31.12.2022 22:00:00 | 01.01.2023 06:00:00 | TAS000006800388 | Critical BTRFS Balancing (lp19intra12001vm.bmwgroup.net) | Pending | Assignment | 31.12.2022 22:00:00 | 01.01.2023 02:00:00 | os-unix-std-06:global:2nd
CRQ000002157576 | Postgres [VLAN tagging] lpxenppg083/084 | Scheduled | 29.12.2022 10:00:00 | 30.12.2022 10:00:00 | TAS000006808164 | [OS VLAN Tagging] | Assigned |  | 29.12.2022 10:30:00 | 29.12.2022 16:30:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002157628 | *ORA-OFFMIG* VM ltbkdbtde020vm , ltbkdbtde013vm from ltbkxendb33_34 to ltbkxendb53_54 | Implementation In Progress | 26.12.2022 20:00:00 | 06.01.2023 00:00:00 | TAS000006806253 | server-unix-std:global¦06¦088c-decom-weekly-move-vm-exec | Pending | Assignment | 31.12.2022 08:00:00 | 31.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002157628 | *ORA-OFFMIG* VM ltbkdbtde020vm , ltbkdbtde013vm from ltbkxendb33_34 to ltbkxendb53_54 | Implementation In Progress | 26.12.2022 20:00:00 | 06.01.2023 00:00:00 | TAS000006806258 | server-unix-std:global¦06¦088c-decom-weekly-move-vm-exec | Pending | Assignment | 31.12.2022 12:00:00 | 31.12.2022 14:00:00 | os-unix-std-06:global:2nd
CRQ000002157628 | *ORA-OFFMIG* VM ltbkdbtde020vm , ltbkdbtde013vm from ltbkxendb33_34 to ltbkxendb53_54 | Implementation In Progress | 26.12.2022 20:00:00 | 06.01.2023 00:00:00 | TAS000006806254 | server-unix-std:global¦06¦089c-decom-weekly-move-vm-cleanup | Pending | Assignment | 02.01.2023 00:00:00 | 05.01.2023 23:00:00 | os-unix-std-06:global:2nd
CRQ000002158171 | MGx: Add QQBMWMUX + sudo | Implementation In Progress | 28.12.2022 09:00:00 | 04.01.2023 18:00:00 | TAS000006808143 | server-unix-std:global¦06¦002-sudo-mgmt-(NSTC) | Assigned |  | 30.12.2022 13:00:00 | 04.01.2023 13:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002159131 | Critical BTRFS Balancing (lp05ipm12w5vm) | Scheduled | 01.01.2023 08:00:00 | 01.01.2023 10:00:00 | TAS000006810397 | Critical BTRFS Balancing (lp05ipm12w5vm) | Pending | Assignment | 01.01.2023 08:00:00 | 01.01.2023 10:00:00 | os-unix-std-06:global:2nd
CRQ000002159326 | MCI - Refresh SAP MCI from MCQ - Sub Tasks | Scheduled | 29.12.2022 09:00:00 | 31.03.2023 10:00:00 | TAS000006810806 | server-unix-std:global¦06¦002-sudo-mgmt-(NSTC) | Pending | Assignment | 29.12.2022 09:00:00 | 31.12.2022 09:00:00 | os-unix-std-06:global:2nd

## MasterSheet-2
CRQ Number | CRQ Description | CRQ Status | CRQ Start Date | CRQ End Date | Linux Tasks in CRQ | Task Description | Task Status | Task Status 1 | Task Start Date | Task End Date | Xen/VMWare | Assignee
CRQ000002121895 | $1 "Colo Group Project" Moving server <lpsbdbs011> to new location | Implementation In Progress | 09.11.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006722161 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002121895 | $1 "Colo Group Project" Moving server <lpsbdbs011> to new location | Implementation In Progress | 09.11.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006722157 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 05.01.2023 09:30:00 | 05.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002126276 | Farm replacement - Source Farm lp07xenmq03/04 to Target Host lp07xen21/22 | Implementation In Progress | 20.12.2022 09:00:00 | 31.12.2022 09:00:00 | TAS000006731848 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 31.12.2022 18:00:00 | 31.12.2022 22:00:00 | os-unix-std-06:global:2nd
CRQ000002126276 | Farm replacement - Source Farm lp07xenmq03/04 to Target Host lp07xen21/22 | Implementation In Progress | 20.12.2022 09:00:00 | 31.12.2022 09:00:00 | TAS000006731939 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 01.01.2023 18:00:00 | 01.01.2023 22:00:00 | os-unix-std-06:global:2nd
CRQ000002126276 | Farm replacement - Source Farm lp07xenmq03/04 to Target Host lp07xen21/22 | Implementation In Progress | 20.12.2022 09:00:00 | 31.12.2022 09:00:00 | TAS000006731849 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 02.01.2023 09:00:00 | 07.01.2023 09:00:00 | os-unix-std-06:global:2nd
CRQ000002126431 | $1 "Colo Group Project" Moving server <lpsbdbs012> ONLY SAN Change (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006730901 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Pending | Assignment | 04.01.2023 09:30:00 | 04.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002126431 | $1 "Colo Group Project" Moving server <lpsbdbs012> ONLY SAN Change (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006730905 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 05.01.2023 08:00:00 | 05.01.2023 18:00:00 | os-unix-std-06:global:2nd
CRQ000002127315 | $1 "Colo Group Project" Moving server <lpdbs131> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731820 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Assigned |  | 29.12.2022 09:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002127316 | $1 "Colo Group Project" Moving server <lpdbs134>ONLY SAN Change (No physical Move of server) | Implementation In Progress | 23.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731997 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Assigned |  | 29.12.2022 09:30:00 | 29.12.2022 15:00:00 | os-unix-std-06:global:2nd | Vinayak Awasthi (EXT)
CRQ000002128057 | *MR+VERITAS* *ESP* lp19d23/24 install Masterrelease | Scheduled | 01.01.2023 17:00:00 | 02.01.2023 00:00:00 | TAS000006735031 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 01.01.2023 17:00:00 | 01.01.2023 23:00:00 | os-unix-std-06:global:2nd
CRQ000002129151 | Farm replacement <lp06xenmq03/04> VM's Offline Migration | Implementation In Progress | 06.12.2022 10:00:00 | 17.12.2022 10:00:00 | TAS000006737333 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 01.01.2023 00:00:00 | 01.01.2023 04:00:00 | os-unix-std-06:global:2nd
CRQ000002129151 | Farm replacement <lp06xenmq03/04> VM's Offline Migration | Implementation In Progress | 06.12.2022 10:00:00 | 17.12.2022 10:00:00 | TAS000006737334 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 01.01.2023 04:00:00 | 01.01.2023 06:00:00 | os-unix-std-06:global:2nd
CRQ000002129151 | Farm replacement <lp06xenmq03/04> VM's Offline Migration | Implementation In Progress | 06.12.2022 10:00:00 | 17.12.2022 10:00:00 | TAS000006737335 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 01.01.2023 08:00:00 | 01.01.2023 12:00:00 | os-unix-std-06:global:2nd
CRQ000002129151 | Farm replacement <lp06xenmq03/04> VM's Offline Migration | Implementation In Progress | 06.12.2022 10:00:00 | 17.12.2022 10:00:00 | TAS000006769055 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 01.01.2023 08:00:00 | 01.01.2023 10:00:00 | os-unix-std-06:global:2nd
CRQ000002129151 | Farm replacement <lp06xenmq03/04> VM's Offline Migration | Implementation In Progress | 06.12.2022 10:00:00 | 17.12.2022 10:00:00 | TAS000006736693 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 02.01.2023 10:00:00 | 07.01.2023 10:00:00 | os-unix-std-06:global:2nd
CRQ000002129291 | Mount the share in lpvpp02 | Scheduled | 15.11.2022 17:00:00 | 19.11.2022 17:00:00 | TAS000006738382 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Assigned |  | 30.12.2022 05:00:00 | 03.01.2023 05:00:00 | os-linux-std-06:global:2nd | Rajendra Bhandari (EXT)
CRQ000002129291 | Mount the share in lpvpp02 | Scheduled | 15.11.2022 17:00:00 | 19.11.2022 17:00:00 | TAS000006738528 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Assigned |  | 30.12.2022 05:00:00 | 03.01.2023 05:00:00 | os-linux-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002129291 | Mount the share in lpvpp02 | Scheduled | 15.11.2022 17:00:00 | 19.11.2022 17:00:00 | TAS000006738529 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Assigned |  | 30.12.2022 05:00:00 | 03.01.2023 05:00:00 | os-linux-std-06:global:2nd | Rajendra Bhandari (EXT)
CRQ000002129291 | Mount the share in lpvpp02 | Scheduled | 15.11.2022 17:00:00 | 19.11.2022 17:00:00 | TAS000006738530 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Assigned |  | 30.12.2022 05:00:00 | 03.01.2023 05:00:00 | os-linux-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002135557 | RRI Migration: Migrate C:D and MQ | Implementation In Progress | 05.12.2022 13:00:00 | 31.01.2023 18:00:00 | TAS000006805398 | server-unix-std:global¦045s-install-override-(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 04.01.2023 18:00:00 | os-linux-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752320 | server-unix-std:global¦06¦085c-move-farm-exec | Assigned |  | 30.12.2022 18:00:00 | 30.12.2022 22:00:00 | os-unix-std-06:global:2nd | Makkena Raghava (EXT)
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752321 | server-unix-std:global¦06¦085c-move-farm-exec | Assigned |  | 30.12.2022 22:00:00 | 31.12.2022 02:00:00 | os-unix-std-06:global:2nd | KumaraSwamy Nasika (EXT)
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752953 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 31.12.2022 02:00:00 | 31.12.2022 06:00:00 | os-unix-std-06:global:2nd
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752954 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 31.12.2022 06:00:00 | 31.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006753624 | server-unix-std:global¦06¦085c-move-farm-exec | Pending | Assignment | 31.12.2022 10:00:00 | 31.12.2022 12:00:00 | os-unix-std-06:global:2nd
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752955 | server-unix-std:global¦06¦086c-move-farm-cleanup-(NSTC) | Pending | Assignment | 02.01.2023 09:00:00 | 07.01.2023 09:00:00 | os-unix-std-06:global:2nd
CRQ000002140014 | *MR* *GSP* lp03d11/12 install Masterrelease | Scheduled | 30.12.2022 07:00:00 | 30.12.2022 17:00:00 | TAS000006763162 | *GSP* *W3* *OID* *4EYE* DNS (before MR) update for oraoid1.w3 | Assigned |  | 30.12.2022 07:00:00 | 30.12.2022 09:00:00 | os-unix-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002140014 | *MR* *GSP* lp03d11/12 install Masterrelease | Scheduled | 30.12.2022 07:00:00 | 30.12.2022 17:00:00 | TAS000006763160 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Assigned |  | 30.12.2022 09:00:00 | 30.12.2022 15:00:00 | os-unix-std-06:global:2nd | Rajendra Bhandari (EXT)
CRQ000002140014 | *MR* *GSP* lp03d11/12 install Masterrelease | Scheduled | 30.12.2022 07:00:00 | 30.12.2022 17:00:00 | TAS000006763163 | *GSP* *W3* *OID* *4EYE* DNS (After MR) update for oraoid1.w3 | Assigned |  | 30.12.2022 15:00:00 | 30.12.2022 17:00:00 | os-unix-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002140850 | TAEE.Next##PRE-PROD##DE##NO## PRE-PROD maintenance work | Implementation In Progress | 28.11.2022 15:00:00 | 28.12.2022 15:00:00 | TAS000006808239 | server-unix-std:global¦06¦002c-sudo-temp-root-permissions(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 04.01.2023 09:00:00 | os-linux-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002141968 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp03db001/002 | Scheduled | 30.12.2022 06:00:00 | 30.12.2022 14:00:00 | TAS000006768672 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Assigned |  | 30.12.2022 06:00:00 | 30.12.2022 12:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002141968 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp03db001/002 | Scheduled | 30.12.2022 06:00:00 | 30.12.2022 14:00:00 | TAS000006769021 | server-unix-std:global¦06¦050c-network-mgmt | Assigned |  | 30.12.2022 06:00:00 | 30.12.2022 12:00:00 | os-unix-std-06:global:2nd | Rajendra Bhandari (EXT)
CRQ000002143251 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* for lp02dbipsq001/002 | Scheduled | 05.01.2023 08:30:00 | 05.01.2023 15:30:00 | TAS000006771849 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 05.01.2023 08:30:00 | 05.01.2023 14:30:00 | os-unix-std-06:global:2nd
CRQ000002143251 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* for lp02dbipsq001/002 | Scheduled | 05.01.2023 08:30:00 | 05.01.2023 15:30:00 | TAS000006771851 | server-unix-std:global¦06¦050c-network-mgmt | Pending | Assignment | 05.01.2023 08:30:00 | 05.01.2023 14:30:00 | os-unix-std-06:global:2nd
CRQ000002143290 | Move VMware VM to other VMware farm (2nd try) | Scheduled | 01.01.2023 00:00:00 | 25.01.2023 00:00:00 | TAS000006771818 | server-unix-std:global¦06¦081c-move-vm-prep-(NSTC) | Assigned |  | 01.01.2023 00:00:00 | 09.01.2023 00:00:00 | os-linux-std-06:global:2nd | KumaraSwamy Nasika (EXT)
CRQ000002143662 | SAN_MIG ¦ BEJ401 ¦ lp19xentw007/008_lp19xentwa2020/2021_lp19crmtomat03/04 | Implementation In Progress | 29.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775528 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 29.12.2022 09:00:00 | 02.01.2023 17:00:00 | os-unix-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002143663 | SAN_MIG ¦ BEJ401 ¦ lp19xenppgdk001/002_lp19xenppgdk005/006_lp19xenpw009/010 | Implementation In Progress | 30.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775649 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 30.12.2022 09:00:00 | 03.01.2023 17:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002143988 | VLAN tagging lpsbxensor003/4 | Implementation In Progress | 09.12.2022 11:00:00 | 30.12.2022 20:00:00 | TAS000006774240 | check Task SAP VLAN tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002144350 | $1 "Colo Group Project" Moving server <lpdbs129> to new location | Implementation In Progress | 05.12.2022 09:00:00 | 30.12.2022 18:00:00 | TAS000006773880 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144383 | $1 "Colo Group Project" Moving server <lpsbdbs013> to new location | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006775333 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 05.01.2023 10:00:00 | 05.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002144399 | $1 "Colo Group Project" Moving server <lpdbs140> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006774918 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Pending | Assignment | 04.01.2023 09:30:00 | 04.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002144399 | $1 "Colo Group Project" Moving server <lpdbs140> ONLY SAN Migration (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775722 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 05.01.2023 09:00:00 | 05.01.2023 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144628 | VLAN tagging lp10xen29/30 | Implementation In Progress | 09.12.2022 12:00:00 | 30.12.2022 20:00:00 | TAS000006774637 | check Task SAP | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002144629 | VLAN Tagging lp10xen23/24 | Implementation In Progress | 09.12.2022 15:00:00 | 30.12.2022 20:00:00 | TAS000006774638 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002144727 | SAN_MIG ¦ BEJ401 ¦ lp19xentwa2022/2023_lp19xentwb2020/2021_lp19xentwb2022/2023 | Implementation In Progress | 29.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775534 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 29.12.2022 09:00:00 | 02.01.2023 17:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002144728 | SAN_MIG ¦ BEJ401 ¦ lp19xenpw011/012_lp19xenpwa2020/2021_lp19xenpwa2022/2023 | Implementation In Progress | 30.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775656 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 30.12.2022 09:00:00 | 03.01.2023 17:00:00 | os-unix-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002144918 | $1 "Colo Group Project" Moving server <lpdbs139> to new location | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775235 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Pending | Assignment | 05.01.2023 10:00:00 | 05.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002144918 | $1 "Colo Group Project" Moving server <lpdbs139> to new location | Implementation In Progress | 05.12.2022 08:00:00 | 30.12.2022 18:00:00 | TAS000006775239 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002144959 | VLAN Tagging lpxensdi36 | Implementation In Progress | 09.12.2022 15:00:00 | 30.12.2022 20:00:00 | TAS000006775759 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002145059 | $1 "Colo Group Project" Moving server <lpdbs141> to new location | Implementation In Progress | 06.12.2022 03:30:00 | 31.01.2023 13:30:00 | TAS000006776763 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Assigned |  | 29.12.2022 08:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002145207 | VLAN Tagging lpxensdi38 | Implementation In Progress | 09.12.2022 16:00:00 | 30.12.2022 20:00:00 | TAS000006775827 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002145208 | VLAN Tagging lpxensdi41 | Implementation In Progress | 09.12.2022 17:00:00 | 30.12.2022 20:00:00 | TAS000006775758 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002145283 | $1 "Colo Group Project" Moving server <lpsbdbs015> to new location | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006776680 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Staged | Staging in Progress | 05.01.2023 10:00:00 | 05.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002145308 | $1 "Colo Group Project" Moving server <lpsbdbs014> ONLY SAN Change (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006775318 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Pending | Assignment | 04.01.2023 09:30:00 | 04.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002145308 | $1 "Colo Group Project" Moving server <lpsbdbs014> ONLY SAN Change (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006775822 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 05.01.2023 08:00:00 | 05.01.2023 18:00:00 | os-unix-std-06:global:2nd
CRQ000002145309 | VLAN Tagging ltxensor28 | Implementation In Progress | 09.12.2022 17:00:00 | 30.12.2022 20:00:00 | TAS000006775757 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806223 | server-unix-std:global¦06¦092c-universal | Pending | Assignment | 03.01.2023 09:30:00 | 06.01.2023 09:30:00 | os-unix-std-06:global:2nd
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006777082 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 01:30:00 | 06.01.2023 01:30:00 | os-linux-std-06:global:2nd | Alok Pai (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006805721 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 01:30:00 | 06.01.2023 03:30:00 | os-linux-std-06:global:2nd | Gaurav Johri (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806222 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 05:30:00 | 06.01.2023 05:30:00 | os-linux-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806224 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 11:30:00 | 06.01.2023 11:30:00 | os-linux-std-06:global:2nd | Ashwini Tendulkar (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806225 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 13:30:00 | 06.01.2023 13:30:00 | os-linux-std-06:global:2nd | Prodyut Paul (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806227 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 18:30:00 | 06.01.2023 18:30:00 | os-linux-std-06:global:2nd | Makkena Raghava (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006805783 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 20:30:00 | 06.01.2023 20:30:00 | os-linux-std-06:global:2nd | Rohit Varmani (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006805784 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 22:30:00 | 06.01.2023 22:30:00 | os-linux-std-06:global:2nd | Gaurav Johri (EXT)
CRQ000002145740 | SAN_MIG ¦ BEJ401 ¦ lp19xendk01/02_lp19xeneai03/4_lp19xenpgag001/002 | Implementation In Progress | 04.01.2023 09:00:00 | 03.02.2023 17:00:00 | TAS000006778443 | MIG_SERVER: Precheck for SAN-Migration | Pending | Assignment | 04.01.2023 09:00:00 | 09.01.2023 17:00:00 | os-unix-std-06:global:2nd
CRQ000002145911 | $1 "Colo Group Project" Moving server <lpdbs145> to new location | Implementation In Progress | 06.12.2022 08:00:00 | 28.02.2023 18:00:00 | TAS000006776407 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Assigned |  | 29.12.2022 08:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002146003 | $1 "Colo Group Project" Moving server <lpdbs147> to new location | Implementation In Progress | 06.12.2022 08:00:00 | 28.02.2023 18:00:00 | TAS000006777840 | readyops:global¦Pre-check-OS-team_unix-cluster-san-complex | Assigned |  | 29.12.2022 08:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Rajendra Bhandari (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805684 | server-unix-std:global¦06¦092c-universal | Pending | Assignment | 01.01.2023 03:30:00 | 04.01.2023 03:30:00 | os-unix-std-06:global:2nd
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006804612 | server-unix-std:global¦06¦092c-universal | Pending | Assignment | 02.01.2023 05:30:00 | 04.01.2023 23:30:00 | os-unix-std-06:global:2nd
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006777852 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 01:30:00 | 04.01.2023 01:30:00 | os-linux-std-06:global:2nd | KumaraSwamy Nasika (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805685 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 05:30:00 | 04.01.2023 05:30:00 | os-linux-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805762 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 09:30:00 | 04.01.2023 09:30:00 | os-linux-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006804607 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 11:30:00 | 04.01.2023 11:30:00 | os-linux-std-06:global:2nd | Nanda Padala (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805688 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 13:30:00 | 04.01.2023 13:30:00 | os-linux-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805691 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 18:30:00 | 04.01.2023 18:30:00 | os-linux-std-06:global:2nd | Manvendra Singh (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006804611 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 20:30:00 | 04.01.2023 20:30:00 | os-linux-std-06:global:2nd | Alok Pai (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805695 | server-unix-std:global¦06¦092c-universal | Assigned |  | 01.01.2023 22:30:00 | 04.01.2023 22:30:00 | os-linux-std-06:global:2nd | Gaurav Johri (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805764 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 01:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Rohit Varmani (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805714 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 03:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805765 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 09:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Prodyut Paul (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805717 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 11:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805718 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 13:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Kishore Kumar (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805719 | server-unix-std:global¦06¦092c-universal | Assigned |  | 02.01.2023 18:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Manvendra Singh (EXT)
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805720 | server-unix-std:global¦06¦092c-universal | Assigned |  | 03.01.2023 02:30:00 | 04.01.2023 23:30:00 | os-linux-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002146306 | SAN_MIG ¦ BEJ401 ¦ lpcabcs3/4_lp19cip01/02_lp19cip03 | Implementation In Progress | 02.01.2023 09:00:00 | 02.02.2023 17:00:00 | TAS000006778429 | MIG_SERVER: Precheck for SAN-Migration | Pending | Assignment | 02.01.2023 09:00:00 | 04.01.2023 17:00:00 | os-unix-std-06:global:2nd
CRQ000002146307 | SAN_MIG ¦ BEJ401 ¦lp19xen15/16_lp19xen21/22 | Implementation In Progress | 04.01.2023 09:00:00 | 03.02.2023 17:00:00 | TAS000006778435 | MIG_SERVER: Precheck for SAN-Migration | Pending | Assignment | 04.01.2023 09:00:00 | 09.01.2023 17:00:00 | os-unix-std-06:global:2nd
CRQ000002146522 | [VLAN tagging] lp1 lpsbxenfind001/002 | Scheduled | 07.12.2022 09:00:00 | 16.12.2022 18:00:00 | TAS000006778770 | server-unix-std:global¦06¦070c-modify-system | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 16:00:00 | os-unix-std-06:global:2nd
CRQ000002146895 | SAN_MIG ¦ BEJ401 ¦ lp19asr01_lp19xbackup02_li19d04 | Implementation In Progress | 02.01.2023 09:00:00 | 02.02.2023 17:00:00 | TAS000006781368 | MIG_SERVER: Precheck for SAN-Migration | Pending | Assignment | 02.01.2023 09:00:00 | 04.01.2023 17:00:00 | os-unix-std-06:global:2nd
CRQ000002147082 | Farm replacement <lpxenpwa013 / 014 > VM Offline Migration | Scheduled | 03.01.2023 08:00:00 | 08.01.2023 00:00:00 | TAS000006782211 | server-unix-std:global¦06¦084c-move-farm-prep-(NSTC) | Pending | Assignment | 04.01.2023 00:00:00 | 07.01.2023 00:00:00 | os-unix-std-06:global:2nd
CRQ000002147667 | VLAN tagging lp05xen18 | Implementation In Progress | 26.12.2022 11:00:00 | 06.01.2023 20:00:00 | TAS000006782516 | check Task SAP/W05 VLAN tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002148197 | W6.11 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 31.12.2022 00:00:00 | 31.12.2022 12:00:00 | TAS000006784410 | server-unix-std:global¦06¦092c-universal | Assigned |  | 31.12.2022 00:00:00 | 31.12.2022 12:00:00 | os-linux-std-06:global:2nd | Alok Pai (EXT)
CRQ000002148715 | [VLAN tagging] lp1 lpsbxenfind003/004 | Scheduled | 09.12.2022 09:00:00 | 16.12.2022 17:00:00 | TAS000006784931 | server-unix-std:global¦06¦070c-modify-system | Pending | Assignment | 04.01.2023 11:00:00 | 04.01.2023 16:00:00 | os-unix-std-06:global:2nd
CRQ000002148781 | *DB_MOVE* *GMA* *dbcms01* *quis* *squarep* *rccbuffp* *flstdep* *wdmspe* MOVE to lpdbs103/lpdbs104 | Scheduled | 02.01.2023 11:00:00 | 22.01.2023 17:00:00 | TAS000006785783 | server-unix-std:global¦06¦035s-nfs-mount-filesystem | Pending | Assignment | 02.01.2023 13:00:00 | 04.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785810 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785812 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785813 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785814 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785815 | server-unix-std:global¦06¦070-OS-config-check_IPS_I | Pending | Assignment | 05.01.2023 13:00:00 | 05.01.2023 17:00:00 | os-unix-std-06:global:2nd
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789865 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789865 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789866 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789868 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789869 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Shahnawaz Khan (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789870 | server-unix-std:global¦06¦070-OS-config-check_IPS_I | Assigned |  | 30.12.2022 13:00:00 | 30.12.2022 17:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789867 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002152537 | *PKG-MOVE+Package domain change * *GSP* MOVE packages dbqarow1 from lp01d69/70 to lp01db005/006 | Scheduled | 29.12.2022 01:00:00 | 10.01.2023 05:00:00 | TAS000006793062 | server-unix-std:global¦06¦023c-cluster-migrate-package | Pending | Assignment | 02.01.2023 01:00:00 | 02.01.2023 05:00:00 | os-unix-std-06:global:2nd
CRQ000002152537 | *PKG-MOVE+Package domain change * *GSP* MOVE packages dbqarow1 from lp01d69/70 to lp01db005/006 | Scheduled | 29.12.2022 01:00:00 | 10.01.2023 05:00:00 | TAS000006793201 | server-unix-std:global¦06¦050c-network-mgmt | Pending | Assignment | 02.01.2023 01:00:00 | 02.01.2023 05:00:00 | os-unix-std-06:global:2nd
CRQ000002152537 | *PKG-MOVE+Package domain change * *GSP* MOVE packages dbqarow1 from lp01d69/70 to lp01db005/006 | Scheduled | 29.12.2022 01:00:00 | 10.01.2023 05:00:00 | TAS000006793063 | server-unix-std:global¦06¦024c-cluster-migrate-cleanup-(NSTC) | Pending | Assignment | 03.01.2023 01:00:00 | 10.01.2023 01:00:00 | os-unix-std-06:global:2nd
CRQ000002152845 | RRP Migration: Migrate AD Roles and Middleware | Scheduled | 02.01.2023 09:00:00 | 24.02.2023 18:00:00 | TAS000006795964 | server-unix-std:global¦06¦002-sudo-mgmt-(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 05.01.2023 09:00:00 | os-linux-std-06:global:2nd | Kamendra Chauhan (EXT)
CRQ000002152845 | RRP Migration: Migrate AD Roles and Middleware | Scheduled | 02.01.2023 09:00:00 | 24.02.2023 18:00:00 | TAS000006795966 | server-unix-std:global¦06¦001s-user-mgmt-(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 05.01.2023 09:00:00 | os-linux-std-06:global:2nd | Tushar Lohia (EXT)
CRQ000002152845 | RRP Migration: Migrate AD Roles and Middleware | Scheduled | 02.01.2023 09:00:00 | 24.02.2023 18:00:00 | TAS000006796155 | server-unix-std:global¦06¦001s-user-mgmt-(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 05.01.2023 09:00:00 | os-linux-std-06:global:2nd | Ashwini Tendulkar (EXT)
CRQ000002152845 | RRP Migration: Migrate AD Roles and Middleware | Scheduled | 02.01.2023 09:00:00 | 24.02.2023 18:00:00 | TAS000006805400 | server-unix-std:global¦045s-install-override-(NSTC) | Assigned |  | 02.01.2023 09:00:00 | 05.01.2023 09:00:00 | os-linux-std-06:global:2nd | Ashwini Tendulkar (EXT)
CRQ000002153326 | Sudo rights for Application User | Scheduled | 02.01.2023 08:00:00 | 06.01.2023 00:00:00 | TAS000006793516 | server-unix-std:global¦06¦002-sudo-mgmt-(NSTC) | Assigned |  | 02.01.2023 00:00:00 | 04.01.2023 00:00:00 | os-linux-std-06:global:2nd | Alok Pai (EXT)
CRQ000002153708 | Un-Mount and Mount to new NFS-Share for Telegramm storge in plant Berlin W03 | Scheduled | 03.01.2023 08:00:00 | 10.01.2023 12:00:00 | TAS000006797041 | server-unix-std:global¦06¦035s-nfs-mount-filesystem-(TimeCritical) | Pending | Assignment | 03.01.2023 08:00:00 | 10.01.2023 10:00:00 | os-unix-std-06:global:2nd
CRQ000002155246 | Critical BTRFS Balancing (lp19intra12001vm.bmwgroup.net) | Scheduled | 31.12.2022 22:00:00 | 01.01.2023 06:00:00 | TAS000006800388 | Critical BTRFS Balancing (lp19intra12001vm.bmwgroup.net) | Pending | Assignment | 31.12.2022 22:00:00 | 01.01.2023 02:00:00 | os-unix-std-06:global:2nd
CRQ000002157576 | Postgres [VLAN tagging] lpxenppg083/084 | Scheduled | 29.12.2022 10:00:00 | 30.12.2022 10:00:00 | TAS000006808164 | [OS VLAN Tagging] | Assigned |  | 29.12.2022 10:30:00 | 29.12.2022 16:30:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002157628 | *ORA-OFFMIG* VM ltbkdbtde020vm , ltbkdbtde013vm from ltbkxendb33_34 to ltbkxendb53_54 | Implementation In Progress | 26.12.2022 20:00:00 | 06.01.2023 00:00:00 | TAS000006806253 | server-unix-std:global¦06¦088c-decom-weekly-move-vm-exec | Pending | Assignment | 31.12.2022 08:00:00 | 31.12.2022 10:00:00 | os-unix-std-06:global:2nd
CRQ000002157628 | *ORA-OFFMIG* VM ltbkdbtde020vm , ltbkdbtde013vm from ltbkxendb33_34 to ltbkxendb53_54 | Implementation In Progress | 26.12.2022 20:00:00 | 06.01.2023 00:00:00 | TAS000006806258 | server-unix-std:global¦06¦088c-decom-weekly-move-vm-exec | Pending | Assignment | 31.12.2022 12:00:00 | 31.12.2022 14:00:00 | os-unix-std-06:global:2nd
CRQ000002157628 | *ORA-OFFMIG* VM ltbkdbtde020vm , ltbkdbtde013vm from ltbkxendb33_34 to ltbkxendb53_54 | Implementation In Progress | 26.12.2022 20:00:00 | 06.01.2023 00:00:00 | TAS000006806254 | server-unix-std:global¦06¦089c-decom-weekly-move-vm-cleanup | Pending | Assignment | 02.01.2023 00:00:00 | 05.01.2023 23:00:00 | os-unix-std-06:global:2nd
CRQ000002158171 | MGx: Add QQBMWMUX + sudo | Implementation In Progress | 28.12.2022 09:00:00 | 04.01.2023 18:00:00 | TAS000006808143 | server-unix-std:global¦06¦002-sudo-mgmt-(NSTC) | Assigned |  | 30.12.2022 13:00:00 | 04.01.2023 13:00:00 | os-linux-std-06:global:2nd | Jitender Rajpal (EXT)
CRQ000002159131 | Critical BTRFS Balancing (lp05ipm12w5vm) | Scheduled | 01.01.2023 08:00:00 | 01.01.2023 10:00:00 | TAS000006810397 | Critical BTRFS Balancing (lp05ipm12w5vm) | Pending | Assignment | 01.01.2023 08:00:00 | 01.01.2023 10:00:00 | os-unix-std-06:global:2nd
CRQ000002159326 | MCI - Refresh SAP MCI from MCQ - Sub Tasks | Scheduled | 29.12.2022 09:00:00 | 31.03.2023 10:00:00 | TAS000006810806 | server-unix-std:global¦06¦002-sudo-mgmt-(NSTC) | Pending | Assignment | 29.12.2022 09:00:00 | 31.12.2022 09:00:00 | os-unix-std-06:global:2nd

## MasterSheet-3
CRQ Number | CRQ Description | CRQ Status | CRQ Start Date | CRQ End Date | Linux Tasks in CRQ | Task Description | Task Status | Task Status 1 | Task Start Date | Task End Date | Xen/VMWare | Assignee
CRQ000002128057 | *MR+VERITAS* *ESP* lp19d23/24 install Masterrelease | Scheduled | 01.01.2023 17:00:00 | 02.01.2023 00:00:00 | TAS000006735031 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 01.01.2023 17:00:00 | 01.01.2023 23:00:00 | os-unix-std-06:global:2nd
CRQ000002140014 | *MR* *GSP* lp03d11/12 install Masterrelease | Scheduled | 30.12.2022 07:00:00 | 30.12.2022 17:00:00 | TAS000006763162,TAS000006763160,TAS000006763163 | *GSP* *W3* *OID* *4EYE* DNS (before MR) update for oraoid1.w3 | Assigned |  | 30.12.2022 07:00:00 | 30.12.2022 09:00:00 | os-unix-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002141968 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp03db001/002 | Scheduled | 30.12.2022 06:00:00 | 30.12.2022 14:00:00 | TAS000006768672,TAS000006769021 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Assigned |  | 30.12.2022 06:00:00 | 30.12.2022 12:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002143251 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* for lp02dbipsq001/002 | Scheduled | 05.01.2023 08:30:00 | 05.01.2023 15:30:00 | TAS000006771849,TAS000006771851 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 05.01.2023 08:30:00 | 05.01.2023 14:30:00 | os-unix-std-06:global:2nd
CRQ000002143662 | SAN_MIG ¦ BEJ401 ¦ lp19xentw007/008_lp19xentwa2020/2021_lp19crmtomat03/04 | Implementation In Progress | 29.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775528 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 29.12.2022 09:00:00 | 02.01.2023 17:00:00 | os-unix-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002143663 | SAN_MIG ¦ BEJ401 ¦ lp19xenppgdk001/002_lp19xenppgdk005/006_lp19xenpw009/010 | Implementation In Progress | 30.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775649 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 30.12.2022 09:00:00 | 03.01.2023 17:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002152537 | *PKG-MOVE+Package domain change * *GSP* MOVE packages dbqarow1 from lp01d69/70 to lp01db005/006 | Scheduled | 29.12.2022 01:00:00 | 10.01.2023 05:00:00 | TAS000006793062,TAS000006793201,TAS000006793063 | server-unix-std:global¦06¦023c-cluster-migrate-package | Pending | Assignment | 02.01.2023 01:00:00 | 02.01.2023 05:00:00 | os-unix-std-06:global:2nd
CRQ000002143988 | VLAN tagging lpsbxensor003/4 | Implementation In Progress | 09.12.2022 11:00:00 | 30.12.2022 20:00:00 | TAS000006774240 | check Task SAP VLAN tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002144628 | VLAN tagging lp10xen29/30 | Implementation In Progress | 09.12.2022 12:00:00 | 30.12.2022 20:00:00 | TAS000006774637 | check Task SAP | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002144629 | VLAN Tagging lp10xen23/24 | Implementation In Progress | 09.12.2022 15:00:00 | 30.12.2022 20:00:00 | TAS000006774638 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002144959 | VLAN Tagging lpxensdi36 | Implementation In Progress | 09.12.2022 15:00:00 | 30.12.2022 20:00:00 | TAS000006775759 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002145207 | VLAN Tagging lpxensdi38 | Implementation In Progress | 09.12.2022 16:00:00 | 30.12.2022 20:00:00 | TAS000006775827 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002145208 | VLAN Tagging lpxensdi41 | Implementation In Progress | 09.12.2022 17:00:00 | 30.12.2022 20:00:00 | TAS000006775758 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002145309 | VLAN Tagging ltxensor28 | Implementation In Progress | 09.12.2022 17:00:00 | 30.12.2022 20:00:00 | TAS000006775757 | check Task SAP VLAN Tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806223,TAS000006777082,TAS000006805721,TAS000006806222,TAS000006806224,TAS000006806225,TAS000006806227,TAS000006805783,TAS000006805784 | server-unix-std:global¦06¦092c-universal | Pending | Assignment | 03.01.2023 09:30:00 | 06.01.2023 09:30:00 | os-unix-std-06:global:2nd
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805684,TAS000006804612,TAS000006777852,TAS000006805685,TAS000006805762,TAS000006804607,TAS000006805688,TAS000006805691,TAS000006804611,TAS000006805695,TAS000006805764,TAS000006805714,TAS000006805765,TAS000006805717,TAS000006805718,TAS000006805719,TAS000006805720 | server-unix-std:global¦06¦092c-universal | Pending | Assignment | 01.01.2023 03:30:00 | 04.01.2023 03:30:00 | os-unix-std-06:global:2nd
CRQ000002146522 | [VLAN tagging] lp1 lpsbxenfind001/002 | Scheduled | 07.12.2022 09:00:00 | 16.12.2022 18:00:00 | TAS000006778770 | server-unix-std:global¦06¦070c-modify-system | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 16:00:00 | os-unix-std-06:global:2nd
CRQ000002147667 | VLAN tagging lp05xen18 | Implementation In Progress | 26.12.2022 11:00:00 | 06.01.2023 20:00:00 | TAS000006782516 | check Task SAP/W05 VLAN tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002148197 | W6.11 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 31.12.2022 00:00:00 | 31.12.2022 12:00:00 | TAS000006784410 | server-unix-std:global¦06¦092c-universal | Assigned |  | 31.12.2022 00:00:00 | 31.12.2022 12:00:00 | os-linux-std-06:global:2nd | Alok Pai (EXT)
CRQ000002148715 | [VLAN tagging] lp1 lpsbxenfind003/004 | Scheduled | 09.12.2022 09:00:00 | 16.12.2022 17:00:00 | TAS000006784931 | server-unix-std:global¦06¦070c-modify-system | Pending | Assignment | 04.01.2023 11:00:00 | 04.01.2023 16:00:00 | os-unix-std-06:global:2nd
CRQ000002155246 | Critical BTRFS Balancing (lp19intra12001vm.bmwgroup.net) | Scheduled | 31.12.2022 22:00:00 | 01.01.2023 06:00:00 | TAS000006800388 | Critical BTRFS Balancing (lp19intra12001vm.bmwgroup.net) | Pending | Assignment | 31.12.2022 22:00:00 | 01.01.2023 02:00:00 | os-unix-std-06:global:2nd
CRQ000002157576 | Postgres [VLAN tagging] lpxenppg083/084 | Scheduled | 29.12.2022 10:00:00 | 30.12.2022 10:00:00 | TAS000006808164 | [OS VLAN Tagging] | Assigned |  | 29.12.2022 10:30:00 | 29.12.2022 16:30:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002159131 | Critical BTRFS Balancing (lp05ipm12w5vm) | Scheduled | 01.01.2023 08:00:00 | 01.01.2023 10:00:00 | TAS000006810397 | Critical BTRFS Balancing (lp05ipm12w5vm) | Pending | Assignment | 01.01.2023 08:00:00 | 01.01.2023 10:00:00 | os-unix-std-06:global:2nd

## MasterSheet-4
CRQ Number | CRQ Description | CRQ Status | CRQ Start Date | CRQ End Date | Linux Tasks in CRQ | Task Description | Task Status | Task Status 1 | Task Start Date | Task End Date | Xen/VMWare | Assignee
CRQ000002128057 | *MR+VERITAS* *ESP* lp19d23/24 install Masterrelease | Scheduled | 01.01.2023 17:00:00 | 02.01.2023 00:00:00 | TAS000006735031 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 01.01.2023 17:00:00 | 01.01.2023 23:00:00 | os-unix-std-06:global:2nd
CRQ000002140014 | *MR* *GSP* lp03d11/12 install Masterrelease | Scheduled | 30.12.2022 07:00:00 | 30.12.2022 17:00:00 | TAS000006763162,TAS000006763160,TAS000006763163 | *GSP* *W3* *OID* *4EYE* DNS (before MR) update for oraoid1.w3 | Assigned |  | 30.12.2022 07:00:00 | 30.12.2022 09:00:00 | os-unix-std-06:global:2nd | Mahesh Babu (EXT)
CRQ000002141968 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp03db001/002 | Scheduled | 30.12.2022 06:00:00 | 30.12.2022 14:00:00 | TAS000006768672,TAS000006769021 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Assigned |  | 30.12.2022 06:00:00 | 30.12.2022 12:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002143251 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* for lp02dbipsq001/002 | Scheduled | 05.01.2023 08:30:00 | 05.01.2023 15:30:00 | TAS000006771849,TAS000006771851 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | Pending | Assignment | 05.01.2023 08:30:00 | 05.01.2023 14:30:00 | os-unix-std-06:global:2nd
CRQ000002152537 | *PKG-MOVE+Package domain change * *GSP* MOVE packages dbqarow1 from lp01d69/70 to lp01db005/006 | Scheduled | 29.12.2022 01:00:00 | 10.01.2023 05:00:00 | TAS000006793062,TAS000006793201,TAS000006793063 | server-unix-std:global¦06¦023c-cluster-migrate-package | Pending | Assignment | 02.01.2023 01:00:00 | 02.01.2023 05:00:00 | os-unix-std-06:global:2nd
CRQ000002145576 | W6 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | TAS000006806223,TAS000006777082,TAS000006805721,TAS000006806222,TAS000006806224,TAS000006806225,TAS000006806227,TAS000006805783,TAS000006805784 | server-unix-std:global¦06¦092c-universal | Pending | Assignment | 03.01.2023 09:30:00 | 06.01.2023 09:30:00 | os-unix-std-06:global:2nd
CRQ000002146005 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | TAS000006805684,TAS000006804612,TAS000006777852,TAS000006805685,TAS000006805762,TAS000006804607,TAS000006805688,TAS000006805691,TAS000006804611,TAS000006805695,TAS000006805764,TAS000006805714,TAS000006805765,TAS000006805717,TAS000006805718,TAS000006805719,TAS000006805720 | server-unix-std:global¦06¦092c-universal | Pending | Assignment | 01.01.2023 03:30:00 | 04.01.2023 03:30:00 | os-unix-std-06:global:2nd
CRQ000002148197 | W6.11 Run BTRFS Balancer on productive IPS/PCS servers | Scheduled | 31.12.2022 00:00:00 | 31.12.2022 12:00:00 | TAS000006784410 | server-unix-std:global¦06¦092c-universal | Assigned |  | 31.12.2022 00:00:00 | 31.12.2022 12:00:00 | os-linux-std-06:global:2nd | Alok Pai (EXT)
CRQ000002155246 | Critical BTRFS Balancing (lp19intra12001vm.bmwgroup.net) | Scheduled | 31.12.2022 22:00:00 | 01.01.2023 06:00:00 | TAS000006800388 | Critical BTRFS Balancing (lp19intra12001vm.bmwgroup.net) | Pending | Assignment | 31.12.2022 22:00:00 | 01.01.2023 02:00:00 | os-unix-std-06:global:2nd
CRQ000002159131 | Critical BTRFS Balancing (lp05ipm12w5vm) | Scheduled | 01.01.2023 08:00:00 | 01.01.2023 10:00:00 | TAS000006810397 | Critical BTRFS Balancing (lp05ipm12w5vm) | Pending | Assignment | 01.01.2023 08:00:00 | 01.01.2023 10:00:00 | os-unix-std-06:global:2nd
CRQ000002143662 | SAN_MIG ¦ BEJ401 ¦ lp19xentw007/008_lp19xentwa2020/2021_lp19crmtomat03/04 | Implementation In Progress | 29.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775528 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 29.12.2022 09:00:00 | 02.01.2023 17:00:00 | os-unix-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002143663 | SAN_MIG ¦ BEJ401 ¦ lp19xenppgdk001/002_lp19xenppgdk005/006_lp19xenpw009/010 | Implementation In Progress | 30.12.2022 09:00:00 | 23.01.2023 17:00:00 | TAS000006775649 | MIG_SERVER: Precheck for SAN-Migration | Assigned |  | 30.12.2022 09:00:00 | 03.01.2023 17:00:00 | os-unix-std-06:global:2nd | Vaibhav Bist (EXT)
CRQ000002121895,CRQ000002144350,CRQ000002144383,CRQ000002145283 | Colo Group Project Moving server <lpsbdbs011><lpdbs129><lpsbdbs013><lpsbdbs015> to new location - Staging in Progress | Implementation In Progress | 09.11.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006722161,TAS000006722157,TAS000006773880,TAS000006775333,TAS000006776680 | readyops:global¦SAN-mirror-unix-cluster | Staged | Staging in Progress | 30.12.2022 08:00:00 | 30.12.2022 18:00:00 | os-unix-std-06:global:2nd
CRQ000002126431,CRQ000002127316,CRQ000002144399,CRQ000002145308 | Colo Group Project Moving server <lpsbdbs012><lpdbs134><lpdbs140><lpsbdbs014> ONLY SAN Change (No physical Move of server) | Implementation In Progress | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | TAS000006730901,TAS000006730905,TAS000006731997,TAS000006774918,TAS000006775722,TAS000006775318,TAS000006775822 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Pending | Assignment | 04.01.2023 09:30:00 | 04.01.2023 15:00:00 | os-unix-std-06:global:2nd
CRQ000002127315,CRQ000002144918,CRQ000002145059,CRQ000002145911,CRQ000002146003 | Colo Group Project Moving server <lpdbs131><lpdbs139><lpdbs141><lpdbs145><lpdbs147> to new location | Implementation In Progress | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | TAS000006731820,TAS000006775235,TAS000006775239,TAS000006776763,TAS000006776407,TAS000006777840 | readyops:global¦Supervise-servermove_unix-cluster-san-complex | Assigned |  | 29.12.2022 09:00:00 | 29.12.2022 18:00:00 | os-unix-std-06:global:2nd | Raminder Singh (EXT)
CRQ000002143988,CRQ000002144628,CRQ000002144629,CRQ000002144959,CRQ000002145207,CRQ000002145208,CRQ000002145309,CRQ000002147667 | VLAN tagging lpsbxensor003/4,lp10xen29/30,lp10xen23/24,lpxensdi36,lpxensdi38,lpxensdi41,ltxensor28,lp05xen18 -Staging in Progress | Implementation In Progress | 09.12.2022 11:00:00 | 30.12.2022 20:00:00 | TAS000006774240,TAS000006774637,TAS000006774638,TAS000006775759,TAS000006775827,TAS000006775758,TAS000006775757,TAS000006782516 | check Task SAP VLAN tagging | Staged | Staging in Progress | 03.01.2023 12:00:00 | 03.01.2023 20:00:00 | os-unix-std-06:global:2nd | Krisztina Horvath (EXT)
CRQ000002146522,CRQ000002148715,CRQ000002157576 | [VLAN tagging] lp1 lpsbxenfind001/002,lp1 lpsbxenfind003/004,Postgres lpxenppg083/084 | Scheduled | 07.12.2022 09:00:00 | 16.12.2022 18:00:00 | TAS000006778770,TAS000006784931,TAS000006808164 | server-unix-std:global¦06¦070c-modify-system | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 16:00:00 | os-unix-std-06:global:2nd
CRQ000002149130 | IPS-I-P01-PROD- Update Masterrelease | Scheduled | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | TAS000006785810,TAS000006785812,TAS000006785813,TAS000006785814,TAS000006785815 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Pending | Assignment | 05.01.2023 11:00:00 | 05.01.2023 13:00:00 | os-unix-std-06:global:2nd
CRQ000002151041 | IPS-I-P03-PROD - Update Masterrelease | Scheduled | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | TAS000006789865,TAS000006789865,TAS000006789866,TAS000006789868,TAS000006789869,TAS000006789870,TAS000006789867 | server-unix-std:global¦06¦101a-Masterrelease Update (VM) | Assigned |  | 30.12.2022 11:00:00 | 30.12.2022 13:00:00 | os-unix-std-06:global:2nd | Rahul Tiwari (EXT)
CRQ000002135571 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18 | Implementation In Progress | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | TAS000006752320,TAS000006752321,TAS000006752953,TAS000006752954,TAS000006753624,TAS000006752955 | server-unix-std:global¦06¦085c-move-farm-exec | Assigned |  | 30.12.2022 18:00:00 | 30.12.2022 22:00:00 | os-unix-std-06:global:2nd | Makkena Raghava (EXT)

## Sheet6
CRQ Number | Linux Tasks in CRQ | CRQ Start Date | CRQ End Date | CRQ Description
CRQ000002128057 | TAS000006735031 | 01.01.2023 17:00:00 | 02.01.2023 00:00:00 | *MR+VERITAS* *ESP* lp19d23/24 install Masterrelease
CRQ000002140014 | TAS000006763162,TAS000006763160,TAS000006763163 | 30.12.2022 07:00:00 | 30.12.2022 17:00:00 | *MR* *GSP* lp03d11/12 install Masterrelease
CRQ000002141968 | TAS000006768672,TAS000006769021 | 30.12.2022 06:00:00 | 30.12.2022 14:00:00 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp03db001/002
CRQ000002143251 | TAS000006771849,TAS000006771851 | 05.01.2023 08:30:00 | 05.01.2023 15:30:00 | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* for lp02dbipsq001/002
CRQ000002152537 | TAS000006793062,TAS000006793201,TAS000006793063 | 29.12.2022 01:00:00 | 10.01.2023 05:00:00 | *PKG-MOVE+Package domain change * *GSP* MOVE packages dbqarow1 from lp01d69/70 to lp01db005/006
CRQ000002145576 | TAS000006806223,TAS000006777082,TAS000006805721,TAS000006806222,TAS000006806224,TAS000006806225,TAS000006806227,TAS000006805783,TAS000006805784 | 02.01.2023 00:00:00 | 05.01.2023 00:00:00 | W6 Run BTRFS Balancer on productive IPS/PCS servers
CRQ000002146005 | TAS000006805684,TAS000006804612,TAS000006777852,TAS000006805685,TAS000006805762,TAS000006804607,TAS000006805688,TAS000006805691,TAS000006804611,TAS000006805695,TAS000006805764,TAS000006805714,TAS000006805765,TAS000006805717,TAS000006805718,TAS000006805719,TAS000006805720 | 26.12.2022 00:00:00 | 05.01.2023 00:00:00 | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers
CRQ000002148197 | TAS000006784410 | 31.12.2022 00:00:00 | 31.12.2022 12:00:00 | W6.11 Run BTRFS Balancer on productive IPS/PCS servers
CRQ000002155246 | TAS000006800388 | 31.12.2022 22:00:00 | 01.01.2023 06:00:00 | Critical BTRFS Balancing (lp19intra12001vm.bmwgroup.net)
CRQ000002159131 | TAS000006810397 | 01.01.2023 08:00:00 | 01.01.2023 10:00:00 | Critical BTRFS Balancing (lp05ipm12w5vm)
CRQ000002143662 | TAS000006775528 | 29.12.2022 09:00:00 | 23.01.2023 17:00:00 | SAN_MIG ¦ BEJ401 ¦ lp19xentw007/008_lp19xentwa2020/2021_lp19crmtomat03/04
CRQ000002143663 | TAS000006775649 | 30.12.2022 09:00:00 | 23.01.2023 17:00:00 | SAN_MIG ¦ BEJ401 ¦ lp19xenppgdk001/002_lp19xenppgdk005/006_lp19xenpw009/010
CRQ000002126431,CRQ000002127316,CRQ000002144399,CRQ000002145308 | TAS000006730901,TAS000006730905,TAS000006731997,TAS000006774918,TAS000006775722,TAS000006775318,TAS000006775822 | 05.12.2022 08:00:00 | 31.01.2023 18:00:00 | Colo Group Project Moving server <lpsbdbs012><lpdbs134><lpdbs140><lpsbdbs014> ONLY SAN Change (No physical Move of server)
CRQ000002127315,CRQ000002144918,CRQ000002145059,CRQ000002145911,CRQ000002146003 | TAS000006731820,TAS000006775235,TAS000006775239,TAS000006776763,TAS000006776407,TAS000006777840 | 22.11.2022 08:00:00 | 16.01.2023 18:00:00 | Colo Group Project Moving server <lpdbs131><lpdbs139><lpdbs141><lpdbs145><lpdbs147> to new location
CRQ000002121895,CRQ000002144350,CRQ000002144383,CRQ000002145283 | TAS000006722161,TAS000006722157,TAS000006773880,TAS000006775333,TAS000006776680 | 09.11.2022 08:00:00 | 31.01.2023 18:00:00 | Colo Group Project Moving server <lpsbdbs011><lpdbs129><lpsbdbs013><lpsbdbs015> to new location - Staging in Progress
CRQ000002146522,CRQ000002148715,CRQ000002157576 | TAS000006778770,TAS000006784931,TAS000006808164 | 07.12.2022 09:00:00 | 16.12.2022 18:00:00 | [VLAN tagging] lp1 lpsbxenfind001/002,lp1 lpsbxenfind003/004,Postgres lpxenppg083/084
CRQ000002143988,CRQ000002144628,CRQ000002144629,CRQ000002144959,CRQ000002145207,CRQ000002145208,CRQ000002145309,CRQ000002147667 | TAS000006774240,TAS000006774637,TAS000006774638,TAS000006775759,TAS000006775827,TAS000006775758,TAS000006775757,TAS000006782516 | 09.12.2022 11:00:00 | 30.12.2022 20:00:00 | VLAN tagging lpsbxensor003/4,lp10xen29/30,lp10xen23/24,lpxensdi36,lpxensdi38,lpxensdi41,ltxensor28,lp05xen18 -Staging in Progress
CRQ000002149130 | TAS000006785810,TAS000006785812,TAS000006785813,TAS000006785814,TAS000006785815 | 05.01.2023 10:00:00 | 05.01.2023 22:00:00 | IPS-I-P01-PROD- Update Masterrelease
CRQ000002151041 | TAS000006789865,TAS000006789865,TAS000006789866,TAS000006789868,TAS000006789869,TAS000006789870,TAS000006789867 | 30.12.2022 10:00:00 | 30.12.2022 20:00:00 | IPS-I-P03-PROD - Update Masterrelease
CRQ000002135571 | TAS000006752320,TAS000006752321,TAS000006752953,TAS000006752954,TAS000006753624,TAS000006752955 | 02.12.2022 09:00:00 | 17.12.2022 09:00:00 | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18

## Sheet7
CRQ Number | Linux Tasks in CRQ | CRQ Start Date | CRQ End Date | CRQ Description, Additional Information
CRQ000002128057 | TAS000006735031 | 01-Jan-23,Sunday, 5:00:00 PM | 02-Jan-23,Monday, 12:00:00 AM | *MR+VERITAS* *ESP* lp19d23/24 install Masterrelease
CRQ000002140014 | TAS000006763162,TAS000006763160,TAS000006763163 | 30-Dec-22,Friday, 7:00:00 AM | 30-Dec-22,Friday, 5:00:00 PM | *MR* *GSP* lp03d11/12 install Masterrelease
CRQ000002141968 | TAS000006768672,TAS000006769021 | 30-Dec-22,Friday, 6:00:00 AM | 30-Dec-22,Friday, 2:00:00 PM | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp03db001/002
CRQ000002143251 | TAS000006771849,TAS000006771851 | 05-Jan-23,Thursday, 8:30:00 AM | 05-Jan-23,Thursday, 3:30:00 PM | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* for lp02dbipsq001/002
CRQ000002152537 | TAS000006793062,TAS000006793201,TAS000006793063 | 29-Dec-22,Thursday, 1:00:00 AM | 10-Jan-23,Tuesday, 5:00:00 AM | *PKG-MOVE+Package domain change * *GSP* MOVE packages dbqarow1 from lp01d69/70 to lp01db005/006
CRQ000002145576 | TAS000006806223,TAS000006777082,TAS000006805721,TAS000006806222,TAS000006806224,TAS000006806225,TAS000006806227,TAS000006805783,TAS000006805784 | 02-Jan-23,Monday, 12:00:00 AM | 05-Jan-23,Thursday, 12:00:00 AM | W6 Run BTRFS Balancer on productive IPS/PCS servers
CRQ000002146005 | TAS000006805684,TAS000006804612,TAS000006777852,TAS000006805685,TAS000006805762,TAS000006804607,TAS000006805688,TAS000006805691,TAS000006804611,TAS000006805695,TAS000006805764,TAS000006805714,TAS000006805765,TAS000006805717,TAS000006805718,TAS000006805719,TAS000006805720 | 26-Dec-22,Monday, 12:00:00 AM | 05-Jan-23,Thursday, 12:00:00 AM | W1/W0 Run BTRFS Balancer on productive IPS/PCS servers
CRQ000002148197 | TAS000006784410 | 31-Dec-22,Saturday, 12:00:00 AM | 31-Dec-22,Saturday, 12:00:00 PM | W6.11 Run BTRFS Balancer on productive IPS/PCS servers
CRQ000002155246 | TAS000006800388 | 31-Dec-22,Saturday, 10:00:00 PM | 01-Jan-23,Sunday, 6:00:00 AM | Critical BTRFS Balancing (lp19intra12001vm.bmwgroup.net)
CRQ000002159131 | TAS000006810397 | 01-Jan-23,Sunday, 8:00:00 AM | 01-Jan-23,Sunday, 10:00:00 AM | Critical BTRFS Balancing (lp05ipm12w5vm)
CRQ000002143662 | TAS000006775528 | 29-Dec-22,Thursday, 9:00:00 AM | 23-Jan-23,Monday, 5:00:00 PM | SAN_MIG ¦ BEJ401 ¦ lp19xentw007/008_lp19xentwa2020/2021_lp19crmtomat03/04
CRQ000002143663 | TAS000006775649 | 30-Dec-22,Friday, 9:00:00 AM | 23-Jan-23,Monday, 5:00:00 PM | SAN_MIG ¦ BEJ401 ¦ lp19xenppgdk001/002_lp19xenppgdk005/006_lp19xenpw009/010
CRQ000002126431,CRQ000002127316,CRQ000002144399,CRQ000002145308 | TAS000006730901,TAS000006730905,TAS000006731997,TAS000006774918,TAS000006775722,TAS000006775318,TAS000006775822 | 05-Dec-22,Monday, 8:00:00 AM | 31-Jan-23,Tuesday, 6:00:00 PM | Colo Group Project Moving server <lpsbdbs012><lpdbs134><lpdbs140><lpsbdbs014> ONLY SAN Change (No physical Move of server)
CRQ000002127315,CRQ000002144918,CRQ000002145059,CRQ000002145911,CRQ000002146003 | TAS000006731820,TAS000006775235,TAS000006775239,TAS000006776763,TAS000006776407,TAS000006777840 | 22-Nov-22,Tuesday, 8:00:00 AM | 16-Jan-23,Monday, 6:00:00 PM | Colo Group Project Moving server <lpdbs131><lpdbs139><lpdbs141><lpdbs145><lpdbs147> to new location
CRQ000002121895,CRQ000002144350,CRQ000002144383,CRQ000002145283 | TAS000006722161,TAS000006722157,TAS000006773880,TAS000006775333,TAS000006776680 | 09-Nov-22,Wednesday, 8:00:00 AM | 31-Jan-23,Tuesday, 6:00:00 PM | Colo Group Project Moving server <lpsbdbs011><lpdbs129><lpsbdbs013><lpsbdbs015> to new location - Staging in Progress
CRQ000002146522,CRQ000002148715,CRQ000002157576 | TAS000006778770,TAS000006784931,TAS000006808164 | 07-Dec-22,Wednesday, 9:00:00 AM | 16-Dec-22,Friday, 6:00:00 PM | [VLAN tagging] lp1 lpsbxenfind001/002,lp1 lpsbxenfind003/004,Postgres lpxenppg083/084
CRQ000002143988,CRQ000002144628,CRQ000002144629,CRQ000002144959,CRQ000002145207,CRQ000002145208,CRQ000002145309,CRQ000002147667 | TAS000006774240,TAS000006774637,TAS000006774638,TAS000006775759,TAS000006775827,TAS000006775758,TAS000006775757,TAS000006782516 | 09-Dec-22,Friday, 11:00:00 AM | 30-Dec-22,Friday, 8:00:00 PM | VLAN tagging lpsbxensor003/4,lp10xen29/30,lp10xen23/24,lpxensdi36,lpxensdi38,lpxensdi41,ltxensor28,lp05xen18 -Staging in Progress
CRQ000002149130 | TAS000006785810,TAS000006785812,TAS000006785813,TAS000006785814,TAS000006785815 | 05-Jan-23,Thursday, 10:00:00 AM | 05-Jan-23,Thursday, 10:00:00 PM | IPS-I-P01-PROD- Update Masterrelease
CRQ000002151041 | TAS000006789865,TAS000006789865,TAS000006789866,TAS000006789868,TAS000006789869,TAS000006789870,TAS000006789867 | 30-Dec-22,Friday, 10:00:00 AM | 30-Dec-22,Friday, 8:00:00 PM | IPS-I-P03-PROD - Update Masterrelease
CRQ000002135571 | TAS000006752320,TAS000006752321,TAS000006752953,TAS000006752954,TAS000006753624,TAS000006752955 | 02-Dec-22,Friday, 9:00:00 AM | 17-Dec-22,Saturday, 9:00:00 AM | Farm replacement - Source Farm lp05xen15/16 to Target Host lp05xen17/18