## Sheet1
CRQ Number | Linux Tasks in CRQ | CRQ Start Date | CRQ End Date | CRQ Description, Additional Information | TASK_NAME | T_SCHEDULED_START_DATE | T_SCHEDULED_END_DATE
CRQ000002199348 | TAS000006911126 | Tuesday, 28-Mar-2023, 9:00:00 AM | Wednesday, 26-Apr-2023, 5:00:00 PM | SAN_MIG ¦ OXF401 ¦ lp34xen25/26 | MIG_SERVER: Verification during SAN migration | 2023-04-09 14:00:00 | 2023-04-09 17:00:00
CRQ000002209751 | TAS000006933024 | Tuesday, 14-Mar-2023, 9:55:00 AM | Monday, 31-Jul-2023, 6:00:00 PM | Moving server <lp19xenppg022;LP19XENTPG014;LP19XENTPG012> to new location | readyops:global¦Supervise-servermove_unix-farm-san | 2023-04-10 11:00:00 | 2023-04-10 16:00:00
CRQ000002215126 | TAS000006947354 | Sunday, 02-Apr-2023, 1:00:00 PM | Sunday, 02-Apr-2023, 8:00:00 PM | *MR+VERITAS* *AWP* lpawp28 install Masterrelease | server-unix-std:global¦06¦101a-Masterrelease Update(Physical) | 2023-04-09 13:00:00 | 2023-04-09 20:00:00
CRQ000002213927 | TAS000006942264 | Monday, 20-Mar-2023, 9:00:00 AM | Friday, 28-Apr-2023, 6:00:00 PM | $1 "Colo Group Project" Moving server <ltdc31.bmwgroup.net> to new location | readyops:global¦Supervise-servermove_unix-single-no-san | 2023-04-12 08:30:00 | 2023-04-12 14:00:00
CRQ000002215011 | TAS000006945536 | Wednesday, 12-Apr-2023, 4:00:00 AM | Sunday, 23-Apr-2023, 5:00:00 AM | *PKG-MOVE* *GSP* MOVE packages from lp06d27/28 to lp06db003/004 | server-unix-std:global¦06¦022c-cluster-prepare-migrate-package | 2023-04-12 04:00:00 | 2023-04-15 04:00:00
CRQ000002214786 | TAS000006945693 | Wednesday, 12-Apr-2023, 1:00:00 AM | Sunday, 23-Apr-2023, 2:00:00 AM | *PKG-MOVE* *GSP* MOVE package dbscow6 from lp06d31/32 to lp06db003/004 | server-unix-std:global¦06¦022c-cluster-prepare-migrate-package | 2023-04-12 01:00:00 | 2023-04-15 01:00:00
CRQ000002215176 | TAS000006947770 | Wednesday, 05-Apr-2023, 2:00:00 PM | Monday, 17-Apr-2023, 11:00:00 PM | *PKG-MOVE* *GSP* MOVE package dbancow6 from lp06d31/32 to lp06db001/002 | server-unix-std:global¦06¦023c-cluster-migrate-package | 2023-04-09 08:00:00 | 2023-04-09 12:00:00
| TAS000006947772 | Wednesday, 05-Apr-2023, 2:00:00 PM | Monday, 17-Apr-2023, 11:00:00 PM | *PKG-MOVE* *GSP* MOVE package dbancow6 from lp06d31/32 to lp06db001/002 | server-unix-std:global¦06¦050c-network-mgmt | 2023-04-09 08:00:00 | 2023-04-09 12:00:00
| TAS000006947771 | Wednesday, 05-Apr-2023, 2:00:00 PM | Monday, 17-Apr-2023, 11:00:00 PM | *PKG-MOVE* *GSP* MOVE package dbancow6 from lp06d31/32 to lp06db001/002 | server-unix-std:global¦06¦024c-cluster-migrate-cleanup-(NSTC) | 2023-04-10 14:00:00 | 2023-04-17 23:00:00
CRQ000002215725 | TAS000006947242 | Monday, 03-Apr-2023, 11:00:00 PM | Saturday, 15-Apr-2023, 11:00:00 PM | *PKG-MOVE* *GSP* MOVE package dbipstw6,dbpsatw6 from lp06d29/30 to lp06db001/002 | server-unix-std:global¦06¦023c-cluster-migrate-package | 2023-04-07 13:00:00 | 2023-04-07 17:00:00
| TAS000006947244 | Monday, 03-Apr-2023, 11:00:00 PM | Saturday, 15-Apr-2023, 11:00:00 PM | *PKG-MOVE* *GSP* MOVE package dbipstw6,dbpsatw6 from lp06d29/30 to lp06db001/002 | server-unix-std:global¦06¦050c-network-mgmt | 2023-04-07 13:00:00 | 2023-04-07 17:00:00
| TAS000006947243 | Monday, 03-Apr-2023, 11:00:00 PM | Saturday, 15-Apr-2023, 11:00:00 PM | *PKG-MOVE* *GSP* MOVE package dbipstw6,dbpsatw6 from lp06d29/30 to lp06db001/002 | server-unix-std:global¦06¦024c-cluster-migrate-cleanup-(NSTC) | 2023-04-08 23:00:00 | 2023-04-15 23:00:00
CRQ000002218077 | TAS000006955327 | Monday, 03-Apr-2023, 8:00:00 AM | Saturday, 15-Apr-2023, 9:00:00 AM | *PKG-MOVE + Package Domain Change* *GSP* MOVE package dbprofw6, dbqariw6, dbqarow6, dbanw6, dbpwow6 | server-unix-std:global¦06¦023c-cluster-migrate-package | 2023-04-07 08:00:00 | 2023-04-07 12:00:00
| TAS000006955343 | Monday, 03-Apr-2023, 8:00:00 AM | Saturday, 15-Apr-2023, 9:00:00 AM | *PKG-MOVE + Package Domain Change* *GSP* MOVE package dbprofw6, dbqariw6, dbqarow6, dbanw6, dbpwow6 | server-unix-std:global¦06¦050c-network-mgmt | 2023-04-07 08:00:00 | 2023-04-07 12:00:00
| TAS000006955323 | Monday, 03-Apr-2023, 8:00:00 AM | Saturday, 15-Apr-2023, 9:00:00 AM | *PKG-MOVE + Package Domain Change* *GSP* MOVE package dbprofw6, dbqariw6, dbqarow6, dbanw6, dbpwow6 | server-unix-std:global¦06¦024c-cluster-migrate-cleanup-(NSTC) | 2023-04-08 08:00:00 | 2023-04-15 08:00:00
CRQ000002203378 | TAS000006917792 | Monday, 03-Apr-2023, 11:00:00 AM | Friday, 07-Apr-2023, 8:00:00 PM | VLAN tagging lp05xen17 | server-unix-std:global¦06¦070c-modify-system | 2023-04-10 11:00:00 | 2023-04-10 15:00:00
CRQ000002219862 | TAS000006959483 | Monday, 03-Apr-2023, 8:00:00 AM | Monday, 24-Apr-2023, 12:00:00 PM | STARD: SNP CS migration + DI replacement + ASCS split - preparation | server-unix-std:global¦06¦001s-user-mgmt-(NSTC) | 2023-04-06 08:00:00 | 2023-04-10 18:00:00
| TAS000006957674 | Monday, 03-Apr-2023, 8:00:00 AM | Monday, 24-Apr-2023, 12:00:00 PM | STARD: SNP CS migration + DI replacement + ASCS split - preparation | server-unix-std:global¦06¦001s-user-mgmt-(NSTC) | 2023-04-06 08:00:00 | 2023-04-10 18:00:00
CRQ000002219014 | TAS000006955350 | Wednesday, 05-Apr-2023, 12:00:00 AM | Monday, 17-Apr-2023, 9:00:00 AM | *PKG-MOVE + Package Domain Change* *GSP* MOVE packages dbipm1w6 from lp06d27/28 to lp06db001/002 | server-unix-std:global¦06¦023c-cluster-migrate-package | 2023-04-07 08:00:00 | 2023-04-07 12:00:00
| TAS000006955352 | Wednesday, 05-Apr-2023, 12:00:00 AM | Monday, 17-Apr-2023, 9:00:00 AM | *PKG-MOVE + Package Domain Change* *GSP* MOVE packages dbipm1w6 from lp06d27/28 to lp06db001/002 | server-unix-std:global¦06¦050c-network-mgmt | 2023-04-07 08:00:00 | 2023-04-07 12:00:00
| TAS000006955351 | Wednesday, 05-Apr-2023, 12:00:00 AM | Monday, 17-Apr-2023, 9:00:00 AM | *PKG-MOVE + Package Domain Change* *GSP* MOVE packages dbipm1w6 from lp06d27/28 to lp06db001/002 | server-unix-std:global¦06¦024c-cluster-migrate-cleanup-(NSTC) | 2023-04-10 08:00:00 | 2023-04-17 08:00:00
CRQ000002197018 | TAS000006902141 | Friday, 24-Feb-2023, 8:00:00 AM | Friday, 31-Mar-2023, 6:00:00 PM | $1 "Colo Group Project" <ltdbs009> No physical move. Only SAN will Change GMA311 > GMA401 | readyops:global¦SAN-mirror-unix-single | 2023-04-06 08:00:00 | 2023-04-06 18:00:00
CRQ000002211306 | TAS000006935410 | Monday, 20-Mar-2023, 8:00:00 AM | Friday, 28-Apr-2023, 6:00:00 PM | $1 "Colo Group Project" Moving server <lpplw13> to new location | readyops:global¦Pre-check-OS-team_unix-single-san-complex | 2023-04-10 08:00:00 | 2023-04-10 18:00:00
CRQ000002194248 | TAS000006896272 | Tuesday, 21-Feb-2023, 8:00:00 AM | Friday, 31-Mar-2023, 6:00:00 PM | $3 "Colo Group Project" <ltdbs017, 018, 019> No physical move, only SAN change | readyops:global¦Supervise-servermove_unix-single-san-complex | 2023-04-06 09:30:00 | 2023-04-06 15:00:00
| TAS000006896276 | Tuesday, 21-Feb-2023, 8:00:00 AM | Friday, 31-Mar-2023, 6:00:00 PM | $3 "Colo Group Project" <ltdbs017, 018, 019> No physical move, only SAN change | readyops:global¦SAN-mirror-unix-single | 2023-04-11 08:00:00 | 2023-04-11 18:00:00
CRQ000002222419 | TAS000006961680 | Wednesday, 05-Apr-2023, 11:00:00 PM | Sunday, 30-Apr-2023, 11:00:00 PM | *MR+DLV/DGV* *GMA* lpproflexdb01/02 install Masterrelease | server-unix-std:global¦06¦023c-cluster-migrate-package | 2023-04-09 14:00:00 | 2023-04-09 17:00:00
CRQ000002193709 | TAS000006894844 | Friday, 07-Apr-2023, 11:00:00 PM | Saturday, 08-Apr-2023, 10:00:00 AM | *MR+Veritas* *ESP* lp10d49/50 install Masterrelease | *ESP* *OID* *4EYE* DNS (before MR+Veritas) update for oraoid2.w10 | 2023-04-07 23:00:00 | 2023-04-08 01:00:00
| TAS000006894746 | Friday, 07-Apr-2023, 11:00:00 PM | Saturday, 08-Apr-2023, 10:00:00 AM | *MR+Veritas* *ESP* lp10d49/50 install Masterrelease | server-unix-std:global¦06¦Post-SLES12-Veritas-Upgrade-Cleanup | 2023-04-08 01:00:00 | 2023-04-08 07:00:00
| TAS000006894847 | Friday, 07-Apr-2023, 11:00:00 PM | Saturday, 08-Apr-2023, 10:00:00 AM | *MR+Veritas* *ESP* lp10d49/50 install Masterrelease | *ESP* *OID* *4EYE* DNS (After MR+Veritas) update for oraoid2.w10 | 2023-04-08 07:00:00 | 2023-04-08 09:00:00
CRQ000002193710 | TAS000006894104 | Sunday, 09-Apr-2023, 5:00:00 AM | Sunday, 09-Apr-2023, 3:00:00 PM | *MR+VERITAS* *ESP* lp10d51/52 install Masterrelease | *ESP* *OID* *4EYE* DNS (before MR+Veritas) update for oraoid2.w10 | 2023-04-09 05:00:00 | 2023-04-09 07:00:00
| TAS000006895035 | Sunday, 09-Apr-2023, 5:00:00 AM | Sunday, 09-Apr-2023, 3:00:00 PM | *MR+VERITAS* *ESP* lp10d51/52 install Masterrelease | server-unix-std:global¦06¦Post-SLES12-Veritas-Upgrade-Cleanup | 2023-04-09 07:00:00 | 2023-04-09 13:00:00
| TAS000006894107 | Sunday, 09-Apr-2023, 5:00:00 AM | Sunday, 09-Apr-2023, 3:00:00 PM | *MR+VERITAS* *ESP* lp10d51/52 install Masterrelease | *ESP* *OID* *4EYE* DNS (After MR+Veritas) update for oraoid2.w10 | 2023-04-09 13:00:00 | 2023-04-09 15:00:00
CRQ000002193631 | TAS000006895222 | Saturday, 08-Apr-2023, 4:00:00 AM | Saturday, 08-Apr-2023, 11:00:00 AM | *MR+VERITAS* *ESP* lp10d55_lp10d56 install Masterrelease | server-unix-std:global¦06¦Post-SLES12-Veritas-Upgrade-Cleanup | 2023-04-08 04:00:00 | 2023-04-08 10:00:00
CRQ000002201127 | TAS000006911630 | Sunday, 09-Apr-2023, 12:00:00 AM | Sunday, 09-Apr-2023, 9:00:00 AM | *MR+VERITAS* *GMA* lpsbdbs07_08 install Masterrelease | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | 2023-04-09 00:00:00 | 2023-04-09 06:00:00
CRQ000002201176 | TAS000006911711 | Sunday, 09-Apr-2023, 6:00:00 AM | Sunday, 09-Apr-2023, 12:00:00 PM | *MR+Veritas* *GSP* lp01db003/004 install Masterrelease | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | 2023-04-09 06:00:00 | 2023-04-09 12:00:00
CRQ000002210591 | TAS000006935835 | Sunday, 09-Apr-2023, 6:00:00 AM | Sunday, 09-Apr-2023, 3:00:00 PM | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp02db001/002 | server-unix-std:global¦06¦050c-network-mgmt | 2023-04-09 06:00:00 | 2023-04-09 13:00:00
| TAS000006935836 | Sunday, 09-Apr-2023, 6:00:00 AM | Sunday, 09-Apr-2023, 3:00:00 PM | *Package Domain Change and creation of alias + MR+VERITAS* *GSP* lp02db001/002 | server-unix-std:global¦06¦101a-Masterrelease Update(Veritas Cluster) | 2023-04-09 06:00:00 | 2023-04-09 13:00:00
CRQ000002225328 | TAS000006969101 | Wednesday, 05-Apr-2023, 12:00:00 AM | Monday, 17-Apr-2023, 9:00:00 AM | *PKG-MOVE + Package Domain Change* *GSP* MOVE packages dbipscw3 from lp03d11/12 to lp03db001/002 | server-unix-std:global¦06¦023c-cluster-migrate-package | 2023-04-08 08:00:00 | 2023-04-08 12:00:00
| TAS000006969103 | Wednesday, 05-Apr-2023, 12:00:00 AM | Monday, 17-Apr-2023, 9:00:00 AM | *PKG-MOVE + Package Domain Change* *GSP* MOVE packages dbipscw3 from lp03d11/12 to lp03db001/002 | server-unix-std:global¦06¦050c-network-mgmt | 2023-04-08 08:00:00 | 2023-04-08 12:00:00
| TAS000006969102 | Wednesday, 05-Apr-2023, 12:00:00 AM | Monday, 17-Apr-2023, 9:00:00 AM | *PKG-MOVE + Package Domain Change* *GSP* MOVE packages dbipscw3 from lp03d11/12 to lp03db001/002 | server-unix-std:global¦06¦024c-cluster-migrate-cleanup-(NSTC) | 2023-04-09 08:00:00 | 2023-04-17 08:00:00
CRQ000002220405 | TAS000006958534 | Friday, 31-Mar-2023, 9:00:00 PM | Tuesday, 11-Apr-2023, 10:00:00 PM | *PKG-MOVE* *GSP* MOVE packages from li02d09/10 to lt02db003 | server-unix-std:global¦06¦050c-network-mgmt | 2023-04-10 03:00:00 | 2023-04-10 10:00:00
| TAS000006967654 | Friday, 31-Mar-2023, 9:00:00 PM | Tuesday, 11-Apr-2023, 10:00:00 PM | *PKG-MOVE* *GSP* MOVE packages from li02d09/10 to lt02db003 | server-unix-std:global¦06¦023c-cluster-migrate-package | 2023-04-10 15:00:00 | 2023-04-10 20:00:00
| TAS000006967658 | Friday, 31-Mar-2023, 9:00:00 PM | Tuesday, 11-Apr-2023, 10:00:00 PM | *PKG-MOVE* *GSP* MOVE packages from li02d09/10 to lt02db003 | server-unix-std:global¦06¦050c-network-mgmt | 2023-04-10 15:00:00 | 2023-04-10 20:00:00
| TAS000006967444 | Friday, 31-Mar-2023, 9:00:00 PM | Tuesday, 11-Apr-2023, 10:00:00 PM | *PKG-MOVE* *GSP* MOVE packages from li02d09/10 to lt02db003 | server-unix-std:global¦06¦023c-cluster-migrate-package | 2023-04-11 00:00:00 | 2023-04-11 05:00:00
| TAS000006967445 | Friday, 31-Mar-2023, 9:00:00 PM | Tuesday, 11-Apr-2023, 10:00:00 PM | *PKG-MOVE* *GSP* MOVE packages from li02d09/10 to lt02db003 | server-unix-std:global¦06¦050c-network-mgmt | 2023-04-11 00:00:00 | 2023-04-11 05:00:00
| TAS000006958532 | Friday, 31-Mar-2023, 9:00:00 PM | Tuesday, 11-Apr-2023, 10:00:00 PM | *PKG-MOVE* *GSP* MOVE packages from li02d09/10 to lt02db003 | server-unix-std:global¦06¦023c-cluster-migrate-package | 2023-04-11 03:00:00 | 2023-04-11 10:00:00
| TAS000006958533 | Friday, 31-Mar-2023, 9:00:00 PM | Tuesday, 11-Apr-2023, 10:00:00 PM | *PKG-MOVE* *GSP* MOVE packages from li02d09/10 to lt02db003 | server-unix-std:global¦06¦024c-cluster-migrate-cleanup-(NSTC) | 2023-04-11 21:00:00 | 2023-04-17 21:00:00
CRQ000002216255 | TAS000006950349 | Saturday, 01-Apr-2023, 8:00:00 PM | Sunday, 02-Apr-2023, 1:00:00 AM | Alarming issues in OS BTRFS filesystem on server lpdbs103 | server-unix-std:global¦06¦btrfs-balancing | 2023-04-08 20:00:00 | 2023-04-09 00:00:00
CRQ000002200712 | TAS000006910538 | Wednesday, 01-Mar-2023, 12:00:00 AM | Wednesday, 15-Mar-2023, 12:00:00 AM | ATLAS#CD Update (no downtime/no communication) | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | 2023-04-12 14:00:00 | 2023-04-12 17:00:00
| TAS000006909861 | Wednesday, 01-Mar-2023, 12:00:00 AM | Wednesday, 15-Mar-2023, 12:00:00 AM | ATLAS#CD Update (no downtime/no communication) | server-unix-std:global¦06¦Upgrade-Rudder-Existing-Software-Bundle | 2023-04-12 14:00:00 | 2023-04-12 17:00:00
CRQ000002200814 | TAS000006910808 | Wednesday, 01-Mar-2023, 2:24:26 PM | Saturday, 04-Mar-2023, 2:24:26 PM | FXM SAP System | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | 2023-04-06 08:00:00 | 2023-04-06 13:00:00
CRQ000002222165 | TAS000006964131 | Friday, 31-Mar-2023, 5:30:00 PM | Thursday, 29-Jun-2023, 8:30:00 PM | GTP/GTI Server decommission subtasks | server-unix-std:global¦06¦026c-cluster-startstop-package | 2023-04-06 09:30:00 | 2023-04-08 09:30:00
CRQ000002209151 | TAS000006967293 | Friday, 07-Apr-2023, 1:00:00 PM | Monday, 10-Apr-2023, 4:00:00 PM | IPS-I-P10-PROD- Update IPSI to 3.7.7 | server-unix-std:global¦06¦btrfs-balancing | 2023-04-07 14:30:00 | 2023-04-07 16:30:00
| TAS000006967294 | Friday, 07-Apr-2023, 1:00:00 PM | Monday, 10-Apr-2023, 4:00:00 PM | IPS-I-P10-PROD- Update IPSI to 3.7.7 | server-unix-std:global¦06¦btrfs-balancing | 2023-04-07 14:30:00 | 2023-04-07 16:30:00
| TAS000006967296 | Friday, 07-Apr-2023, 1:00:00 PM | Monday, 10-Apr-2023, 4:00:00 PM | IPS-I-P10-PROD- Update IPSI to 3.7.7 | server-unix-std:global¦06¦btrfs-balancing | 2023-04-07 14:30:00 | 2023-04-07 16:30:00
| TAS000006967295 | Friday, 07-Apr-2023, 1:00:00 PM | Monday, 10-Apr-2023, 4:00:00 PM | IPS-I-P10-PROD- Update IPSI to 3.7.7 | server-unix-std:global¦06¦btrfs-balancing | 2023-04-07 14:30:00 | 2023-04-07 16:30:00
| TAS000006967727 | Friday, 07-Apr-2023, 1:00:00 PM | Monday, 10-Apr-2023, 4:00:00 PM | IPS-I-P10-PROD- Update IPSI to 3.7.7 | server-unix-std:global¦06¦btrfs-balancing | 2023-04-07 14:30:00 | 2023-04-07 16:30:00
| TAS000006967730 | Friday, 07-Apr-2023, 1:00:00 PM | Monday, 10-Apr-2023, 4:00:00 PM | IPS-I-P10-PROD- Update IPSI to 3.7.7 | server-unix-std:global¦06¦btrfs-balancing | 2023-04-07 14:30:00 | 2023-04-07 16:30:00
CRQ000002218904 | TAS000006955256 | Sunday, 09-Apr-2023, 12:00:00 AM | Sunday, 09-Apr-2023, 7:30:00 AM | KLP SLES 12 SP5 In-Place Upgrade on DI Instances of KLP System | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Cluster) | 2023-04-09 01:00:00 | 2023-04-09 06:00:00
| TAS000006955274 | Sunday, 09-Apr-2023, 12:00:00 AM | Sunday, 09-Apr-2023, 7:30:00 AM | KLP SLES 12 SP5 In-Place Upgrade on DI Instances of KLP System | server-unix-std:global¦06¦025c-cluster-switch-package | 2023-04-09 08:00:00 | 2023-04-09 11:00:00
CRQ000002213059 | TAS000006941262 | Friday, 17-Mar-2023, 2:22:00 PM | Wednesday, 10-May-2023, 7:00:00 PM | Moving server <LP19XENTWA2023 ;LP19XENINF04; LP19XENINF02> to new location | readyops:global¦Pre-check-OS-team_unix-farm-san | 2023-04-10 09:00:00 | 2023-04-11 19:00:00
CRQ000002224118 | TAS000006966252 | Monday, 03-Apr-2023, 3:00:00 PM | Monday, 10-Apr-2023, 6:00:00 PM | NMS NRP Cluster failover test | server-unix-std:global¦06¦025c-cluster-switch-package | 2023-04-08 20:00:00 | 2023-04-08 23:00:00
CRQ000002092947 | TAS000006652894 | Thursday, 22-Sep-2022, 11:29:34 AM | Sunday, 25-Sep-2022, 11:29:34 AM | NRP SAP System | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | 2023-04-07 23:00:00 | 2023-04-08 03:00:00
CRQ000002195465 | TAS000006898800 | Sunday, 09-Apr-2023, 7:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | P10 - In-Place Sles Upgrade - Master Release Upgrade - Cluster switch test after upgrade. | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Cluster) | 2023-04-10 08:00:00 | 2023-04-10 13:00:00
| TAS000006898714 | Sunday, 09-Apr-2023, 7:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | P10 - In-Place Sles Upgrade - Master Release Upgrade - Cluster switch test after upgrade. | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Physical) | 2023-04-10 08:00:00 | 2023-04-10 12:00:00
| TAS000006898769 | Sunday, 09-Apr-2023, 7:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | P10 - In-Place Sles Upgrade - Master Release Upgrade - Cluster switch test after upgrade. | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Physical) | 2023-04-10 08:00:00 | 2023-04-10 12:00:00
| TAS000006898747 | Sunday, 09-Apr-2023, 7:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | P10 - In-Place Sles Upgrade - Master Release Upgrade - Cluster switch test after upgrade. | server-unix-std:global¦06¦025c-cluster-switch-package | 2023-04-10 14:30:00 | 2023-04-10 16:30:00
CRQ000002206916 | TAS000006925550 | Monday, 03-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 11:00:00 AM | P20 - In-Place Sles Upgrade - Master Release Upgrade - Cluster switch test after upgrade. | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Physical) | 2023-04-09 08:00:00 | 2023-04-09 12:00:00
| TAS000006925551 | Monday, 03-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 11:00:00 AM | P20 - In-Place Sles Upgrade - Master Release Upgrade - Cluster switch test after upgrade. | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Cluster) | 2023-04-09 08:00:00 | 2023-04-09 13:00:00
| TAS000006925539 | Monday, 03-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 11:00:00 AM | P20 - In-Place Sles Upgrade - Master Release Upgrade - Cluster switch test after upgrade. | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Physical) | 2023-04-09 08:00:00 | 2023-04-09 12:00:00
| TAS000006925546 | Monday, 03-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 11:00:00 AM | P20 - In-Place Sles Upgrade - Master Release Upgrade - Cluster switch test after upgrade. | server-unix-std:global¦06¦025c-cluster-switch-package | 2023-04-09 14:30:00 | 2023-04-09 16:30:00
CRQ000002223260 | TAS000006964716 | Monday, 10-Apr-2023, 8:00:00 AM | Monday, 10-Apr-2023, 4:00:00 PM | SAN #Data: SAN_MICROCODE_UPGRADE GMA411 | NTT Unix: SAN #Data: SAN_MICROCODE_UPGRADE GMA411 | 2023-04-10 08:00:00 | 2023-04-10 16:00:00
CRQ000002223174 | TAS000006965199 | Monday, 10-Apr-2023, 8:00:00 AM | Monday, 10-Apr-2023, 4:00:00 PM | SAN #Data: SAN_MICROCODE_UPGRADE RGB401 | SAN #Data: SAN_MICROCODE_UPGRADE RGB401 | 2023-04-10 08:00:00 | 2023-04-10 16:00:00
CRQ000002208307 | TAS000006928100 | Monday, 20-Mar-2023, 4:00:00 AM | Friday, 31-Mar-2023, 5:00:00 AM | SAN Cleanup - lp10g3p08 lp10g3p09 | SAN Cleanup - lp10g3p08 lp10g3p09 | 2023-04-10 05:00:00 | 2023-04-20 05:00:00
CRQ000002207672 | TAS000006928377 | Tuesday, 11-Apr-2023, 9:00:00 AM | Wednesday, 26-Apr-2023, 5:00:00 PM | SAN_MIG ¦ GMA411 ¦ lplaas19_lplaas20_lpxenpgag005/006 | MIG_SERVER: Precheck for SAN-Migration | 2023-04-11 09:00:00 | 2023-04-13 17:00:00
CRQ000002207673 | TAS000006928384 | Wednesday, 12-Apr-2023, 9:00:00 AM | Thursday, 27-Apr-2023, 5:00:00 PM | SAN_MIG ¦ GMA411 ¦ lpxentwb2028/2029_ltxenpgag203/204_lpxentbigd05/06 | MIG_SERVER: Precheck for SAN-Migration | 2023-04-12 09:00:00 | 2023-04-14 17:00:00
CRQ000002206054 | TAS000006924325 | Wednesday, 22-Mar-2023, 9:00:00 AM | Tuesday, 02-May-2023, 5:00:00 PM | SAN_MIG ¦ RGB401 ¦ lp06kwom02_lp06kwom03 | MIG_SERVER: Verification during SAN migration | 2023-04-12 11:00:00 | 2023-04-12 14:00:00
CRQ000002221993 | TAS000006962738 | Wednesday, 05-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | STARD TDP SLES12 SP5 In-place upgrade | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Physical) | 2023-04-09 09:00:00 | 2023-04-09 14:00:00
| TAS000006962206 | Wednesday, 05-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | STARD TDP SLES12 SP5 In-place upgrade | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Physical) | 2023-04-09 09:00:00 | 2023-04-09 14:00:00
| TAS000006962208 | Wednesday, 05-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | STARD TDP SLES12 SP5 In-place upgrade | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Cluster) | 2023-04-09 09:00:00 | 2023-04-09 14:00:00
| TAS000006962210 | Wednesday, 05-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | STARD TDP SLES12 SP5 In-place upgrade | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Physical) | 2023-04-09 09:00:00 | 2023-04-09 14:00:00
| TAS000006962213 | Wednesday, 05-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | STARD TDP SLES12 SP5 In-place upgrade | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Physical) | 2023-04-09 09:00:00 | 2023-04-09 14:00:00
| TAS000006962214 | Wednesday, 05-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | STARD TDP SLES12 SP5 In-place upgrade | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Physical) | 2023-04-09 09:00:00 | 2023-04-09 14:00:00
| TAS000006962648 | Wednesday, 05-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | STARD TDP SLES12 SP5 In-place upgrade | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Physical) | 2023-04-09 09:00:00 | 2023-04-09 14:00:00
CRQ000002215397 | TAS000006947925 | Wednesday, 05-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | STARD TFP Kernel + Oracle upgrade + SLES12 SP5 IPU | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Cluster) | 2023-04-09 15:00:00 | 2023-04-09 20:00:00
| TAS000006947926 | Wednesday, 05-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | STARD TFP Kernel + Oracle upgrade + SLES12 SP5 IPU | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Physical) | 2023-04-09 15:00:00 | 2023-04-09 20:00:00
| TAS000006947927 | Wednesday, 05-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | STARD TFP Kernel + Oracle upgrade + SLES12 SP5 IPU | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Physical) | 2023-04-09 15:00:00 | 2023-04-09 20:00:00
| TAS000006947928 | Wednesday, 05-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | STARD TFP Kernel + Oracle upgrade + SLES12 SP5 IPU | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Physical) | 2023-04-09 15:00:00 | 2023-04-09 20:00:00
| TAS000006947846 | Wednesday, 05-Apr-2023, 10:00:00 AM | Monday, 10-Apr-2023, 10:00:00 AM | STARD TFP Kernel + Oracle upgrade + SLES12 SP5 IPU | server-unix-std:global¦06¦OS SLES In-Place Upgrade Implementation (Physical) | 2023-04-09 15:00:00 | 2023-04-09 20:00:00
CRQ000002212120 | TAS000006938144 | Friday, 07-Apr-2023, 5:00:00 AM | Friday, 14-Apr-2023, 6:00:00 PM | STARD: SND CS migration + DI replacement + ASCS split - implementation | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | 2023-04-07 09:00:00 | 2023-04-07 13:00:00
CRQ000002165250 | TAS000006825281 | Friday, 07-Apr-2023, 5:00:00 AM | Friday, 14-Apr-2023, 6:00:00 PM | STARD: TZQ CS migration + DI replacement - implementation | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | 2023-04-07 09:00:00 | 2023-04-07 13:00:00
CRQ000002221997 | TAS000006964132 | Friday, 31-Mar-2023, 5:30:00 PM | Thursday, 29-Jun-2023, 8:30:00 PM | WSP/WSQ Server decommission subtasks | server-unix-std:global¦06¦026c-cluster-startstop-package | 2023-04-06 09:30:00 | 2023-04-08 09:30:00
CRQ000002180031 | TAS000006864249 | Thursday, 02-Feb-2023, 5:04:20 PM | Sunday, 05-Feb-2023, 5:04:20 PM | YSP SAP System | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | 2023-04-09 02:00:00 | 2023-04-09 06:00:00
CRQ000002175342 | TAS000006850274 | Thursday, 26-Jan-2023, 7:59:16 PM | Sunday, 29-Jan-2023, 7:59:16 PM | ZXD SAP System | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | 2023-04-07 22:00:00 | 2023-04-08 02:00:00
CRQ000002174933 | TAS000006850633 | Thursday, 26-Jan-2023, 7:59:15 PM | Sunday, 29-Jan-2023, 7:59:15 PM | ZXS SAP System | server-unix-std:global¦06¦SAP OS AB DB_IMPORT Migration exec | 2023-04-07 17:00:00 | 2023-04-07 21:00:00
CRQ000002226435 | TAS000006971089 | Wednesday, 05-Apr-2023, 5:00:00 PM | Wednesday, 12-Apr-2023, 5:00:00 PM | Language pack install - lpsapstudio02 | server-linux-std:global:000-default | 2023-04-07 17:00:00 | 2023-04-11 17:00:00
CRQ000002226078 | TAS000006971546 | Thursday, 06-Apr-2023, 8:00:00 AM | Monday, 10-Apr-2023, 8:00:00 AM | OTD Nexus disk space enlargement | server-unix-std:global¦06¦030s-san-change-filesystem-(NSTC) | 2023-04-06 08:00:00 | 2023-04-10 08:00:00
CRQ000002225818 | TAS000006970754 | Monday, 10-Apr-2023, 10:00:00 AM | Monday, 24-Apr-2023, 5:00:00 PM | SAN: Cleanup LDEV 00:00:00 | lptup30 lptup31 Cleanup LDEV 00:00:00 | 2023-04-10 10:00:00 | 2023-04-24 17:00:00
| TAS000006970667 | Monday, 10-Apr-2023, 10:00:00 AM | Monday, 24-Apr-2023, 5:00:00 PM | SAN: Cleanup LDEV 00:00:00 | lt12db001 Cleanup LDEV 00:00:00 | 2023-04-10 10:00:00 | 2023-04-24 17:00:00
| TAS000006970755 | Monday, 10-Apr-2023, 10:00:00 AM | Monday, 24-Apr-2023, 5:00:00 PM | SAN: Cleanup LDEV 00:00:00 | lpxendb075 lpxendb076 Cleanup LDEV 00:00:00 | 2023-04-11 10:00:00 | 2023-04-25 17:00:00